Victorian Electoral Commission

| Re-issued April 26 October 2013 2013 | Report on Conduct of the 2012 Local Government Elections |
| --- | --- |

Errata Note

This report was originally published by the Victorian Electoral Commission (VEC) on 26 April 2013. The following updates were made since its original release:

| Release | Page/s | Correction |
| --- | --- | --- |
| October 2013 | 39 | The 2012 turnout rates for ‘All Councils (inc Melbourne Leadership Team and Geelong Mayor)’ and ‘Postal (inc Melbourne Leadership Team and Geelong Mayor)’ in Figure 5 were updated. |
|  | 40 | The 2012 informal voting rates in Figure 7 were updated. |
|  | 148-50 | The tables showing ‘All Councils’, ‘Melbourne City Council’, ‘Greater Geelong City Council’, and ‘Attendance elections – metropolitan’ in Appendix 15 were updated. |

Contents

Foreword by the Acting Electoral Commissioner	v

Summary	vi

Summary of recommendations	vii

1	LEGISLATIVE FRAMEWORK	1

1.1	Changes in legislation	1

2	REGULATORY FRAMEWORK	3

3	RESPONSIBILITIES	4

3.1	Victorian Electoral Commission and the Electoral Commissioner	4

3.2	Returning Officer	5

3.3	Councils and the Local Government Investigations and Compliance Inspectorate	6

4	INITIATIVES	6

4.1	Electronic roll marking	6

4.2	Social media	6

4.3	Electronic ballot paper scanning – discontinued	6

5	MUNICIPAL VOTERS’ ROLL	7

5.1	Local government voting entitlements	7

5.2	Roll production	8

5.3	Roll production challenges	10

5.4	Dates of birth on the Chief Executive Officer’s List	11

5.5	Voters’ rolls	11

5.6	Enrolment	12

6	LOCAL GOVERNMENT ELECTIONS 2012 IN REVIEW	13

6.1	Planning and preparation	13

6.2	Selection of an election service provider	14

6.3	Choice of attendance or postal elections	15

6.4	Appointment of Returning Officers	16

6.5	Election offices	16

6.6	Human resources	18

6.7	Support services for Returning Officers	18

6.8	Election Management System	19

6.9	Information sessions for prospective candidates	20

6.10	Nominations	20

6.11	Ballot packs and voter notices	27

6.12	Fraud prevention initiative	29

6.13	Voting centres for attendance elections	30

6.14	Postal voting and early voting at attendance elections	30

6.15	Electronic Roll marking	32

6.16	Services for the people who are blind or with low vision	32

6.17	Services for people experiencing homelessness	33

6.18	Close of voting	34

6.19	Counting arrangements	35

6.20	Recounts	37

6.21	Declaration of results	38

6.22	Reports to Councils	38

6.23	Successful candidates	39

6.24	Voter turnout	39

6.25	Informal voting rates	39

6.26	Communication campaigns	41

6.27	Compulsory voting enforcement	52

6.28	Complaints	54

6.29	Applications to the Municipal Electoral Tribunal	56

6.30	Election Costs	58

7	DEBRIEFING AND EVALUATION	59

7.1	Debriefing	59

7.2	Evaluation surveys	60

8	APPENDICES	71

Appendix 1: Local government election timelines	71

Appendix 2: Municipal voter count by ward	75

Appendix 3: Details of Returning Officers and election offices	88

Appendix 4: Details of information sessions for candidates	91

Appendix 5: VEC discussion paper: Conformity with how-to-vote cards	95

Appendix 6: Sample ballot pack	101

Appendix 7: Sample EasyVote letter	102

Appendix 8: Sample State-wide advertising	103

Appendix 9: Sample Council-specific advertising	108

Appendix 10: Sample uncontested election leaflet	114

Appendix 12: Details of counting arrangements	118

Appendix 13: Dates of declarations of results	121

Appendix 14: Election details	123

Appendix 15: Snapshot of results	148

Foreword by the Acting Electoral Commissioner

I am pleased to present the Victorian Electoral Commission Report of the 2012 Local Government Elections, held in October 2012.

The conduct of these elections brought to fruition over 18 months of planning and activity at the Victorian Electoral Commission (VEC). After extensive consultation, planning and preparation, and a rigorous procurement process with councils, the VEC provided election services to 78 of Victoria’s 79 councils, which involved over 2,000 candidates and more than four million enrolled voters.

The only council not to hold a general election in 2012 was Brimbank City Council, which has been re-scheduled to take place in March 2015.

This report provides an overview of the elections and an insight into the way the VEC managed the logistical challenges presented by conducting elections for each of the 78 councils concurrently. The report details innovations in the VEC’s processes, products and services, and reports on key figures and results. The evaluation of the VEC’s services was informed by an extensive program that included debriefing with councils, key suppliers and staff, as well as online surveys allowing direct feedback from candidates and voters.

The report puts forward a number of recommendations that the VEC considers will facilitate improvements to administrative processes at local government elections. The recommendations in this report are intended to benefit the sector’s discussions on the future of local government elections. The VEC looks forward to assisting with these discussions wherever possible.

I would like to acknowledge the work of the former Electoral Commissioner, Steve Tully, who had a close relationship with the local government sector and handed over to me a local government election program that was focused on delivering high quality and cost efficient elections to the VEC’s local government clients.

I extend the VEC’s appreciation to our contractors and suppliers for their exceptional service and support, which is invaluable to the success of Victoria’s electoral activities. I also express my sincere appreciation and congratulations to the VEC’s staff and election officials for their efforts in ensuring that the program is carried out with care and diligence. The commitment and passion of all of these people to deliver to Victorians the opportunity to participate in our democracy at this important level of government were critical to our successful completion of Victoria’s local government general elections in 2012.

Liz Williams

Acting Electoral Commissioner

Summary

In October 2012, the VEC conducted elections on behalf of 78 of Victoria’s 79 Councils under the provisions of the Local Government Act 1989 and the City of Melbourne Act 2001. There were contested elections in 245 wards and unsubdivided municipalities, with uncontested elections in 28 electorates.

Eight councils chose to conduct their elections by attendance election, while the remaining 70 councils conducted postal elections.

Features of the elections included:

- 146 multi-councillor wards and unsubdivided councils were counted using proportional representation (6 were uncontested)

- 126 single-councillor wards were counted using the preferential method (21 were uncontested)

- 16 councils had a combination of ward structures, and both preferential and proportional representation counts

- 4,098,007 people were enrolled voters at the close of rolls (3,987,726 in 2008)

- 2,004 candidates nominated for 631 positions (1,953 for 629 in 2008)

- 506 how-to-vote cards were registered (625 in 2008)

- The participation rate for all elections was 70.96% (74.68% in 2008)

- The participation rate for postal elections was 72.53% (75.96% in 2008)

- The participation rate for attendance elections was 63.62% (70.03% in 2008)

- The informal voting rate for all elections was 5.39% (4.99% in 2008)

- The informal voting rate for postal elections was 4.66% (3.75% in 2008)

- The informal voting rate for attendance elections 10.09% (9.90% in 2008)

- 173 voting centres were established for attendance elections held on Saturday, 27 October, and 22 early voting centres were established for early voting

- 64 computer counting venues and 26 manual counting venues were established across the State

- The results for 77 councils were declared on or by Wednesday, 31 October, with all elections declared by Friday, 2 November

- the VEC was appointed by 73 councils to follow-up non-voters, and a total of 505,582 Apparent Failure to Vote Notices were sent

- five applications were lodged with the Municipal Election Tribunal (12 in 2008)

- a report on each council’s election was delivered to the respective council in late January 2013, in accordance with legislation.

Summary of recommendations

A number of matters raised in this report have been highlighted for further consideration. Where appropriate, the VEC would welcome the opportunity to be involved in further consideration of these matters prior to commencing planning for the Brimbank City Council elections in March 2015 and the local government elections in October 2016.

The VEC recommends that the Government:

- Notes that the terms ‘resident’ and ‘non-resident’ for the purposes of a municipal voters’ roll can lead to uncertainty among voters when considering their voting entitlement(s) and obligations (see page 8).

- Considers an appropriate mechanism to capture changes to the postal addresses of non-resident ratepayers, who are automatically enrolled on the municipal voters’ roll, for the purpose of maintaining a Chief Executive Officer’s List (see page 11).

- Considers regulating the method of displaying the exhibition roll to maximise security of voters’ personal details at display locations during the display period (see page 12).

- Considers legislating an election service provider as the default election service provider for local government elections and codifies a suitable costing arrangement that exempts the service provider from councils’ general procurement requirements (see page 15).

- Considers amending clause 6(3A) of Schedule 2 of the LG Act to permit the Returning Officer to reject a nomination from a person who is not on the voters’ roll for the municipality (see page 21).

- Considers legislation to allow candidates to electronically submit their candidate statements and indication of preferences to the Returning Officer (see page 24).

- Considers requiring the publication of all registered how-to-vote cards in relation to a local government election on a website administered by (or on behalf of) the Returning Officer as soon as practicable after the completion of the period for registration (see page 25).

- Considers removing the requirement for how-to-vote cards to be registered for distribution at early voting centres (see page 25).

- Notes that mail delivery patterns have changed affecting the dispatch and return of standard mail services (see page 28).

- Amends Regulation 44(4) of the Local Government (Electoral) Regulations 2005 to allow voters to electronically lodge a postal voting application in relation to voting at an attendance election (see page 31).

- Considers a legislative provision that exempts voters who request a Braille ballot paper at an attendance election and who are not already registered as a General Postal Voter from the requirement to complete a written application (see page 33).

- Considers removing the requirement for a Council to pass a resolution in accordance with Regulation 93(2) of the Local Government (Electoral) Regulations 2005 thereby providing for circumstances where a Returning Officer (or election service provider) cannot secure a suitable counting venue within the municipal district (see page 37).

- Considers a mechanism for a Returning Officer (or election service provider) at a local government election to refer a matter of concern in relation to that election to the Municipal Electoral Tribunal (see page 58).

# LEGISLATIVE FRAMEWORK

Local government elections are conducted within a legislative and regulatory framework. Section 74A(1) of the Constitution Act 1975 provides that local government is a distinct and essential tier of government, consisting of democratically elected councils.

The Local Government Act 1989 (LG Act) is the principal legislation for the conduct of local government elections in Victoria. Detailed provisions for the elections are contained in the Local Government (Electoral) Regulations 2005 (LGR).

The City of Melbourne Act 2001 (CoM Act) makes provisions for the conduct of elections for the Melbourne City Council.

## Changes in legislation

Local government elections were aligned across all of Victoria’s 79 councils for the first time at the 2008 local government elections. The LG Act requires elections to be conducted every four years.

A number of legislative amendments that affected the 2012 local government elections were made between the 2008 and 2012 local government elections. Some of these amendments reflected recommendations from the VEC’s report following the 2008 local government elections.

The key amendments to local government legislation relating to the conduct of elections include those detailed below.

Local Government Amendment (Elections) Act 2008

- Amended the LG Act and the CoM Act to facilitate the holding of local government elections.

Local Government Amendment (Conflicting Duties) Act 2009

- Amended the LG Act to provide for conflicting duties of persons who are or want to be Councillors and for other purposes.

Local Government (Brimbank City Council) Act 2009

- Dismissed Brimbank City Council and provided for the appointment of a Panel of Administrators in its place.

Local Government Amendment (Electoral Matters) Act 2011

- Amended the LG Act to provide for local government general elections to be held on the fourth Saturday in October every four years, beginning from the fourth Saturday in October 2012.

- Amended the CoM Act to provide for regular reviews of electoral representation of Councillors of the Melbourne City Council, other than the Lord Mayor and the Deputy Lord Mayor.

- Consequentially amended the Local Government (Brimbank City Council) Act 2009 to provide for the general election of Brimbank City Council to be held on the fourth Saturday in October 2012. This provision was subject to further amendment by the Local Government (Brimbank City Council) Amendment Act 2012, as below.

City of Greater Geelong Amendment Act 2011

- Amended the City of Greater Geelong Act 1993 to enable the Mayor of the City of Greater Geelong to be directly elected to represent the municipal district as a whole.

Local Government (Brimbank City Council) Amendment Act 2012

- Amended the Local Government (Brimbank City Council) Act 2009 to provide for a general election of the Brimbank City Council to be held on the fourth Saturday in March 2015, rather than in October 2012.

City of Melbourne Amendment (Enrolment) Act 2012

- Amended the CoM Act to clarify the persons entitled to apply to be enrolled on the voters' roll for the City of Melbourne elections.

Local Government Legislation Amendment (Miscellaneous) Act 2012

- Repealed the offence of false and defamatory statements from the LG Act.

- Amended the LG Act to clarify the application of provisions regarding the distribution of printed electoral material to households within 400 metres of a voting centre (or early voting centre).

- Amended the LG Act to require the Chief Executive Officer of a council to publish a summary of campaign donation returns on the council’s website.

# REGULATORY FRAMEWORK

The LGR provides the framework for the conduct of local government elections. The Local Government (Electoral) Amendment Regulations 2012, amending the LGR, were made in June 2012 and were effective immediately at that time.

The amendments to the LGR are summarised below.

- Various time of day deadlines relating to lodgement of candidate statements and indication of preferences were brought forward from 4.00 pm to 12 noon (Regulations 34, 36, 37).

- Details of registered how-to-vote cards published on the VEC web site will include the names of submitters and organisations they represent, if any (Regulation 31).

- The requirement for candidates to supply additional registered how-to-vote cards for all voting centres was removed, however, copies must still be supplied to Returning Officer (Regulation 31).

- The deadline by which a voter can request the redirection of their postal ballot pack was brought forward from the close of nominations to the day that the voters’ roll is certified (opening of nominations) (Regulation 87).

- The penalty for making a false statement regarding a how-to-vote card, which was included as Regulation 28(5), was removed as it was covered by section 238A of the LG Act.

- Regulation 114(3), which required electoral records to be destroyed after four years, was removed. The disposal of such records is dealt with through the Public Records Act 1973.

- Part 11 of the LGR, which contained consequential amendments to the subordinate instrument under CoM Act, were revoked.

# RESPONSIBILITIES

## Victorian Electoral Commission and the Electoral Commissioner

The LG Act’s explicit requirements for the VEC are limited to its responsibility for the provision of a list of legislative assembly voters to the registrar of the voters roll at a local government election and conducting a periodic electoral representation or subdivision review of each municipality in Victoria.

In practice, however, the VEC assumes three additional areas of responsibility under the LG Act once it is formally engaged by a council to perform that function of the election. The areas include:

- The preparation of the municipal voters’ roll;

- The conduct of the election; and

- The enforcement of compulsory voting through non-voter follow up.

The VEC does not have any remaining responsibilities under the legislation.

### The preparation of the municipal voters’ roll

In the lead up to a council election, where the VEC is engaged by a council to prepare its exhibition and voters’ rolls, the Electoral Commissioner is required to appoint the Registrar for the purpose of preparing the rolls. The appointment is pursuant to the meaning of ‘Registrar’ in section 3 of the LG Act.

The VEC was engaged to prepare the rolls on behalf of 77 of the 78 councils that had an election in 2012. The VEC worked closely with Melbourne City Council to prepare the rolls for that council, but did not appoint the Registrar.

### The conduct of the election

As the VEC is considered to be an ‘electoral commission’ by the LG Act, it may be engaged to conduct a local government election. After being formally engaged by a council, the Electoral Commissioner is responsible for appointing the Returning Officer pursuant to clause 1(2)(c) of Schedule 2 of the LG Act.

The VEC supports its Returning Officers by:

- providing a voter information campaign

- providing all handbooks and forms

- providing office equipment and furniture

- providing training in local government election procedures

- arranging materials to be printed

- preparing the voters rolls by merging the Electoral Commissioner’s voters list of electors with the Chief Executive Officer’s voters list of ratepayers

- providing a computerised Election Management System to support the Returning Officer in the conduct of the election

- arranging for the secure dispatch of ballot packs

- providing progress reports to the council

- notifying the Minister for Local Government of the results of the election

- providing electoral information on the VEC’s website

- arranging legal advice as required

- refunding candidates’ nomination fees

- producing a list of non-voters

- organising the follow up of non-voters and

- preparing a report for council on the conduct of the elections.

The VEC was engaged to conduct the elections on behalf of 78 of Victoria’s 79 councils. Brimbank City Council did not have an election in 2012.

### The enforcement of compulsory voting through non-voter follow up

Where the VEC is formally engaged to carry out certain non-voter follow-up procedures, the Electoral Commissioner nominates a VEC officer as the ‘Prosecution Officer’ to undertake these tasks. The Chief Executive Officer of the council is required to formally appoint the ‘Prosecution Officer’ pursuant to section 40(2)(a) of the LG Act.

The VEC was engaged to conduct non-voter follow up on behalf of 73 of the 78 councils that had an election in 2012. The VEC was not engaged to conduct non-voter follow up for the Borough of Queenscliffe, Golden Plains Shire Council, Pyrenees Shire Council and Swan Hill Rural City Council.

## Returning Officer

The LG Act requires that a local government election must be conducted by a Returning Officer. The Returning Officer may be the Chief Executive Officer of the council, another member of council staff, or where an Electoral Commission is appointed to conduct the election, the Electoral Commission will appoint the Returning Officer.

The Returning Officer:

- is responsible for the management of the election

- is impartial and independent

- is required to appoint a Deputy Returning Officer and

- may delegate responsibilities (except the power of delegation) to a Deputy Returning Officer or authorised person.

The Returning Officer has no legislative authority to investigate breaches of the LG Act.

## Councils and the Local Government Investigations and Compliance Inspectorate

Where a council is not conducting its election, the Chief Executive Officer of the council is responsible for appointing an Electoral Commission to conduct the election. The council selects the method of election (postal or attendance) and negotiates the services to be provided with its electoral services provider.

The CEO is also responsible for the preparation of the section of the voters’ roll relating to ratepayers.

Responsibility for investigating and prosecuting alleged breaches of the LG Act rests with the Local Government Investigations and Compliance Inspectorate (LGICI), an agency of the Department of Planning and Community Development.

# INITIATIVES

## Electronic roll marking

For the local government elections in 2012, the VEC used electronic roll marking (see section 6.15).

Voters at attendance elections were marked off the roll electronically, with the vast majority of voters at voting centres and during early voting being recorded on Toshiba netbooks wirelessly connected to the VEC on the Next-G network.

The remainder of voters, those voting in postal elections, were directly marked off the roll using the VEC’s Election Management System (see Section 6.8).

## Social media

After the successful use of social media at the 2010 State election, the VEC introduced social media initiatives for the local government elections in 2012, promoting key electoral information on Facebook and Twitter, and using these platforms to seed conversations relating to the democratic process in Victoria.

## Electronic ballot paper scanning – discontinued

The VEC conducted a ballot paper scanning pilot program during the local government elections in 2008. Ballot papers were scanned and intelligent character recognition (ICR) was used to read ballot paper preferences before transferring them into the VEC’s computer count application, instead of being entered manually by data entry operators. The pilot included the Cities of Glen Eira, Stonnington and Yarra and though it was successful in many aspects, it was also considered that, at this stage, there were no significant benefits in terms of cost and time to justify a ballot paper scanning operation for 2012.

# MUNICIPAL VOTERS’ ROLL

## Local government voting entitlements

Voting entitlements for local government elections differ from those that apply in a State or Federal election. Voting entitlements for 78 of the 79 Victorian councils are specified under the LG Act, with CoM Act providing additional entitlement provisions for Melbourne City Council elections.

### General provisions

Voting entitlements to vote at a local government election fall into three groups:

- Residents in the municipality who are on the roll for the Legislative Assembly (section 12 of the LG Act) – Electoral Commissioner’s List

Enrolled residents who are 18 years and over, Australian citizens or entitled British subjects are listed on the Electoral Commissioner’s list. To enrol, an enrolment form must be completed, signed and witnessed prior to the entitlement date. Entitlement is based on the residential address on the enrolment form.

Since legislation was introduced in 2010, the VEC has commenced a direct enrolment program using reliable external data sources to enrol people who are entitled to enrol and have not completed an enrolment form or have not updated their address.

State enrolled voters form approximately 86% of the roll across all municipalities. The Electoral Commissioner’s list database has been designed and is maintained for the purpose of producing electoral rolls for the conduct of elections at State and local government levels.

- Non-resident ratepayers (section 13 of the LG Act) – Chief Executive Officer’s List)

A person who owns a rateable property in the municipal district (whether solely or jointly) and who is not a resident of the municipal district is automatically entitled to be enrolled on the voters roll in respect of that property. This entitlement is limited to two people per rateable property.

A notice of acquisition, which includes name and date of birth, is completed at the time of the purchase of a property. This is the only time council has any certainty regarding the residency status of a particular ratepayer in relation to the property, which may change over time.

This category forms about 14% of the roll across all municipalities. Records for these people are extracted from each council’s property database, which are designed for the purpose of collecting rates on a property and not primarily for extracting details of individuals for voting purposes. This can present difficulties for councils to ensure that all those who are entitled to vote are included on the Chief Executive Officer’s List.

- Other ratepayer entitlements (sections 14, 15 and 16 of the LG Act) – Chief Executive Officer’s List

Other council entitlements include non-citizen owner occupiers, company nominees and occupiers who pay the rates.

To be entitled to vote, this group must complete an application form, which includes up-to-date personal details, each election cycle. Council includes this group on its Chief Executive Officer’s List. This very small group makes up about 0.05% of the roll across all municipalities.

In relation to some of these entitlements, the LG Act uses the terms ‘resident’ and ‘non-resident’ to represent different levels of entitlement. This can create confusion and uncertainty for some groups of voters, particular during when applying for an unenrolled declaration vote and during compulsory voting enforcement activities. The VEC has observed that some tenants who are listed on the Electoral Commissioner’s List as Legislative Assembly voters do not believe that they are ‘residents’, as they are not homeowners.

Recommendation 1: Resident and non-resident The VEC recommends that the Government notes that the terms ‘resident’ and ‘non-resident’ for the purposes of a municipal voters’ roll can lead to uncertainty among voters when considering their voting entitlement(s) and obligations.

### Melbourne City Council voting entitlements

Voting entitlements at Melbourne City Council vary slightly from those that apply for all other councils in Victoria. In addition to the general entitlements listed in section 5.1.1, the following entitlements also apply:

- A person who occupies rateable property in the City of Melbourne municipal district and resides in the municipality, but they are not on the State electoral roll (including non-Australian citizens) and they made an application to Council for enrolment before the entitlement date. If the person is a resident occupier, they must have been a resident for at least one month prior to the entitlement date.

- A person who is a director or company secretary of a corporation (or holds an equivalent position) that owns or occupies a rateable property solely or jointly within the City of Melbourne. If the company does not appoint two voting representatives by the entitlement date, Melbourne City Council is required to enrol company officers using data provided by the Australian Securities and Investments Commission.

These entitlements are both on the Chief Executive Officer’s List.

## Roll production

The VEC was responsible for the preparation of the exhibition and certification rolls on behalf of 77 of the 78 councils that had an election in 2012. Due to the special requirements of the Melbourne City Council rolls detailed in section 5.1.2, the VEC and Melbourne City Council officers jointly prepared the exhibition and certification rolls for Melbourne City Council elections.

The Electoral Commissioner appointed Paul Strickland as the Registrar of the Voters’ Rolls for the 77 councils. At the time of the election, Mr Strickland was the VEC’s Manager of Electoral Enrolment Branch.

The VEC has provided roll production services to councils since 1995, and has developed sophisticated software tools and processing procedures for ensuring the quality of the voters roll. Software tools are updated for each election cycle to cater for legislative changes and to continuously improve processing and accuracy.

In preparation for the local government elections in 2012, extensive work was carried out by the VEC with all councils to ensure that council data were of high quality and included date of birth on as many council records as possible. This work occurred in the 18 months before the elections and resulted in faster and more accurate processing after the entitlement date, 4.00 pm on Friday, 31 August 2012.

Considerable time and effort is devoted to performing data matching and checking names and addresses in an effort to prepare voters rolls that are as accurate as possible. Roll preparation involves the receipt of an initial Chief Executive Officer’s List at exhibition roll date, an update to this List at the entitlement date and checking both against the entitlement provisions of the LG Act. The Electoral Commissioner’s List of State enrolled voters and the Chief Executive Officer’s List of ratepayers are combined to produce the list of entitled electors for each local government election. Every effort is made to identify voters that appear on both lists and, in accordance with the LG Act, the record from the Chief Executive Officer’s List is removed.

The roll preparation process commences six months before election day when preliminary data is provided by the council. This process uses sophisticated software to identify, where possible, people whose names appear on both the Electoral Commissioner’s List and the Chief Executive Officer’s List. Nevertheless, significant manual work is still required to investigate and resolve these duplicates. The aim is that all eligible voters are included on the final voters’ roll for the election, but that duplicate records are not included.

The preliminary process mirrors the process at the exhibition roll date and aims to identify and provide feedback to council on issues that will delay final processing or cause problems with the comprehensiveness and/or accuracy of the final voters’ roll. This detailed feedback, including possible duplicates and the names of deceased voters, is provided to council for action on their database so that the quality of the final data can be improved and processing delays minimised.

Within three working days following the exhibition roll date, each council provided data to the VEC containing details of the ratepayers who were entitled to be enrolled as at the exhibition roll date. These data were loaded into the VEC computer system and merged with the State roll data for the municipality. Matching routines were used to try to identify and remove duplicates and the names of deceased voters. Decisions on possible duplicates were made in conjunction with the relevant council. The exhibition rolls for each council were available for public exhibition at locations nominated by the councils for the display period, beginning on Monday, 27 August 2012 and closing at the entitlement date at 4.00 pm on Friday, 31 August 2012.

Matching the imported records against deceased electors resulted in 1,483 records being removed. Duplicate identification meant that a further 38,042 records were removed.

The exhibition rolls for the 77 councils included 506,230 Chief Executive Officer’s List voters and only 39,525 records (7.2%) had to be removed from the council extracts for exhibition, compared with 7.6% in 2008 and 25% of records in 2005. Improvements to software and council business processes that were put in place for the local government elections in 2008 have been maintained, allowing the VEC to produce high quality rolls within the tight legislative timeline.

After the entitlement date, changes to the Chief Executive Officer’s List between the exhibition roll extract and the entitlement date were received from each council. These changes were processed, along with changes to the Electoral Commissioner’s List, to produce the rolls for certification.

The Chief Executive Officer of each council then certified the voters’ roll for their municipality. The certified voters’ roll was used for the election.

## Roll production challenges

The ability to produce an accurate roll relies on the VEC’s capacity to identify, match and remove duplicates, as well as removing deceased electors’ names from the merged data. This requires significant effort and resources from council and the VEC. There is no unique identifier available in both the State enrolment register and the council ratings system register to determine that a record appearing in both registers relates to the same person. The availability of personal details (particularly date of birth data) that are as up-to-date and complete as possible are critical to the matching process.

Electors listed on the State roll (first entitlement category) are required to provide complete personal details at the time of enrolment, and also when any details change, such as a change of name or address.

Electors in the second entitlement category (automatically entitled non-resident ratepayers) provide the prescribed details at the time of purchase of a property. This includes their current contact details and whether the property is to be their principal place of residence. There is no legislative requirement for a property owner to notify a council of any entitlement changes, i.e. a change from resident to non-resident status. The ability of the council and VEC to identify such changes is therefore dependent on the ability to match a council record with a State roll record. This group comprises approximately 12.5% of the roll but makes up 80% of processing. Where multiple records are identified as relating to the one person and different addresses are identified, it can be difficult to determine which address is the most appropriate to use.

Electors in the third entitlement category (non-citizen owner occupiers and company nominees) are required to update their details when they apply for enrolment at each election. This leaves no doubt about entitlements and currency of details.

Recommendation 2: Property owners changing address The VEC recommends that the Government considers an appropriate mechanism to capture changes to the postal addresses of non-resident ratepayers, who are automatically enrolled on the municipal voters’ roll, for the purpose of maintaining a Chief Executive Officer’s List.

## Dates of birth on the Chief Executive Officer’s List

Regulation 15(2)(vii) of the Local Government (General) Regulations 2004 requires property purchasers to provide date of birth information to councils for the purpose of preparing voters’ rolls. This additional personal information greatly improves the VEC’s ability to match council records with the Electoral Commissioner’s List. The Regulation applied to property purchases made from the date that it came into force, so compliance levels are not yet optimal.

For some years the VEC has encouraged councils to include date of birth information on older property records where possible. Most councils have put administrative processes in place to collect date of birth whenever there is any contact with a ratepayer, for confirmation of identity and for addition to the records.

The VEC once again matched entire database extracts from councils with the State roll database and provided dates of birth where definite matches occurred. Most councils participated in this exercise, which resulted in an increased percentage of council records with date of birth information (78.7% of all council records provided for the local government elections in 2012 compared with 65.2% in 2008). Seven councils had dates of birth on more than 90% of their CEO List records (only one in 2008) and only two councils had less than 60% of records with dates of birth (18 in 2008). There were 40 councils that exceeded the 80% target set by the VEC.

## Voters’ rolls

The legislated period for the production of final voters’ rolls is short. The VEC began work with councils in March 2012 to ensure the production of voters’ rolls of the best possible quality.

### Exhibition rolls

The exhibition roll for each council was available for public inspection from Monday, 27 August 2012 until the entitlement date at 4.00 pm on Friday, 31 August 2012.

Each council was asked to nominate one or more display locations within their council. Most locations were council service centres and libraries, however, in country areas, councils also nominated post offices and general stores as display locations. The number of display locations within each municipality varied from one up to 18 locations.

The exhibition period and display locations were advertised with information on council roll entitlements through the public notice of entitlement and on the VEC’s website. The notice included details on how a person can go about objecting to an error or omission in an exhibition roll by contacting the Registrar. The Registrar was not advised of any errors or omissions in the roll.

After the entitlement date, the VEC arranged for councils to withdraw the exhibition rolls from each of the display locations. Council officers organised collection and secure destruction of the exhibition rolls from the display locations within their municipality. During the collection process, the VEC was notified of three instances where exhibition rolls had been removed from a display location before the authorised person was able to collect them. The issue was promptly reported to the local Police and the VEC advised the Privacy Commissioner.

Recommendation 3: Security of display rolls The VEC recommends that the Government considers regulating the method of displaying the exhibition roll to maximise security of voters’ personal details at display locations during the display period.

## Enrolment

A total of 4,098,007 voters were enrolled at the close of rolls for the local government elections in 2012. The table in Appendix 2 shows Municipal voter count by electorate.

### Amendments to the certified voters’ rolls

Across all 78 councils that had an election in 2012, there were 338 additions and 499 deletions made to the municipal voters’ rolls after the certification date. These amendments were made pursuant to the process provided by section 24A of the LG Act and were signed by the Returning Officer for the election and the Chief Executive Officer of the relevant council.

Details of these can be found in the table in Appendix 2.

# LOCAL GOVERNMENT ELECTIONS 2012 IN REVIEW

## Planning and preparation

The time required for preparation and planning for the management of the local government elections is approximately 18 months – equivalent to that required for the management of a State election. Preparation for the local government elections in 2012 commenced early in 2011.

One of the major challenges faced by the VEC is ensuring that contract arrangements were understood and in place in sufficient time to prepare adequately for their implementation. For example, many councils were unable to provide space for election office accommodation and contracts needed to be in place between the VEC and these councils before the VEC could enter into a leasing arrangements for commercial office accommodation. Protracted contract negotiations also meant that the VEC was unable to finalise some service requirements until later than anticipated.

Further challenges included the preparation of 78 voters rolls within legislative timelines without compromising the quality of the rolls, and the preparation and dispatch of over three million ballot packs for up to 238 postal elections, and approximately 690,000 EasyVote letters for 36 attendance elections, within the specified timelines.

### Service plan

The VEC conducted workshops with staff and service providers to determine capabilities and requirements. As a result, the VEC enhanced its processes and systems, and standardised some services to ensure that the large volumes of electoral materials could be managed within legislative timelines. A proposed service plan was developed to ensure that the organisation was in a position to offer an election service to all councils. Using its experience from previous elections, the VEC considered the volume of products and materials, timelines, cost, quality, identified risks, and council and voter expectations. The proposed service plan included some standardisation of services as well as a limited number of optional services for councils to select.

### Council consultation

The VEC conducted eight information and consultation sessions for councils in October 2011 to present the proposed service plan and the timelines that would need to be met by the VEC and councils. Of the 79 councils due to hold elections, 77 were represented at these sessions. The proposed service plan was discussed separately with councils who were unable to attend.

Feedback was received from councils, with most of these indicating that they were satisfied with the proposed service plan, and amendments were made in response to feedback. A small number of councils indicated concern with the VEC’s proposed count and declaration timetable proposing that results and declarations should take place within a shorter timeframe. Further information on the count and declaration timetable is included in sections 6.19 and 6.21 of this report.

The final service plan, with estimated costs, was distributed to councils in December 2011.

The VEC also participated in other meetings conducted by local government bodies including workshops with council revenue managers to discuss roll preparation arrangements.

## Selection of an election service provider

Councils are required to tender for the provision of any goods or services if the cost of the goods or services is expected to exceed $150,000. The VEC provided councils with estimates for their elections in December 2011, which assisted councils with budgeting and determining their tendering responsibilities in relation to finding an election service provider. The estimates showed that most council elections were expected to meet or exceed $150,000 and these councils would need to tender for their elections. Councils whose election services were estimated to cost under $150,000 were still expected to follow a procurement process consistent with the purchasing requirements by the LG Act.

Although there is no legislative requirement for an electoral commission to tender for, or conduct, local government elections in Victoria, the VEC has been the only tenderer for Victorian local government election services since March 2002.

In December 2011, the Minister for Local Government authorised an exemption from the tendering requirements for councils who appointed the VEC as their election service provider. The exemption was conditional on a quotation being accepted by the council and required the VEC to conduct all three service activities associated with a council’s elections, including preparation of the municipal voters’ roll, conduct of the elections and enforcement of compulsory voting. Councils were not obliged to use the exemption and many councils had already resolved to go to tender before receiving notice of the exemption.

The VEC notes that the exemption was specific to elections held on Saturday, 27 October 2012 and covers any consequential by-elections or countbacks within the subsequent term of council, however, it does not exempt councils from their requirement to tender for future general elections.

Between January and July 2012, 55 councils advertised tenders for their election services, including 54 councils that participated in a joint tender through an agency, and 24 councils requested quotations directly with the VEC. Councils generally provided their own specifications to assist with costing, which were then used as the basis of the contract, but in some instances, the VEC was able to assist councils with the preparation of their costing parameters. The quotations were prepared using the products and services in the VEC’s service plan and included the activities required by legislation as well as a limited range of optional/recommended products. These additional products included additional early voting centres for attendance elections, additional candidate information sessions, voting reminder notices, the inclusion of a multi-language voting instruction leaflet in ballot packs for postal elections, and responsibility for compulsory voting enforcement. Most councils requested a quotation for either an attendance or postal election, but some councils requested quotations for both methods of voting.

The quotations were provided in two parts:

- a schedule of marginal costs for election services, including service one (preparation of the municipal voters’ roll) and service two (conduct of the elections); and

- a schedule of marginal costs for the enforcement of compulsory voting.

The costs were accompanied by their qualifications and a list of prescribed variations, which explained the assumptions included in preparing the costs, such as the number of candidates and voters, voter turnout and recounts. Additional variations applied to attendance elections, including the number of voting centres, early voting centres and postal voting applications.

The VEC recognises that improvements in service planning and election preparations would be aided by certainty in the number of elections to be conducted by the VEC, as often certain activities cannot be finalised until negotiations with all councils have been completed. Although the VEC strives to find affordable and high quality suppliers, the ability to increase cost efficiencies would be improved by certainty within its local government work program.

Recommendation 4: Election service provider The VEC recommends that the Government considers legislating an election service provider as the default election service provider for local government elections and codifies a suitable costing arrangement that exempts the service provider from councils’ general procurement requirements. In relation to this recommendation, the VEC notes that these requirements exist in other Australian jurisdictions: section 55(3)(p) of the Local Government Act 1993 (NSW) section 259 of the Local Government Act (NT) and Regulation 13 of the corresponding Local Government (Electoral) Regulations (NT) section 8 of the Local Government Electoral Act 2011 (Qld) section 10(1) of the Local Government (Elections) Act 1993 (SA) section 264(1) of the Local Government Act 1993 (Tas) sections 4.20(4) and 4.28(c) of the Local Government Act 1995 (WA)

## Choice of attendance or postal elections

At least eight months before a general election, councils may resolve to change the method of election to be used at the election. At the local government elections in 2012, 70 councils used the postal method of voting, where ballot material was mailed out to all voters on the municipal voters roll and was required to be returned to the Returning Officer by 6.00 pm on the day before election day. There were eight councils that used the attendance method of voting, when most voters complete their ballot papers at a voting centre operating on election day. Early voting and postal voting are also available at attendance elections.

Two councils resolved to change the method of election for the 2012 elections. Since postal elections were introduced to local government in Victoria, there has been a trend towards the postal method. This is believed to be due to the acknowledged benefits of postal voting, such as lower cost, lower rates of informal voting, and generally higher turnout rates. Figure 1 highlights the number councils using each method over the last 10 years.

|  | 2003 | 2004 | 2005 | 2008 | 2012 |
| --- | --- | --- | --- | --- | --- |
| Postal elections | 47 (87%) | 22 (88%) | 48 (89%) | 70 (89%) | 70 (90%) |
| Attendance elections | 7 (13%) | 3 (12%) | 6 (11%) | 9 (11%) | 8 (10%) |

Figure 1: Choice of election method over time

## Appointment of Returning Officers

As discussed earlier in this report, the LG Act requires a Returning Officer to conduct a local government election. The legislation allows a Returning Officer to be the Chief Executive Officer of the council, a member of council staff appointed by the Chief Executive Officer of the council, or, if an Electoral Commission or another council is appointed to conduct the election, a person appointed by the Electoral Commission or council to be the Returning Officer.

Once a council had officially engaged the VEC as its election service provider, the Electoral Commissioner appointed a Returning Officer for that election. The VEC’s Returning Officers (and Deputy Returning Officers) are appointed from its pool of trained senior election officials located across Victoria who work on State and local government elections.

See Appendix 3 for a list of Returning Officers appointed at the local government elections in 2012.

## Election offices

Election offices were established for the conduct of the local government elections in 2012. These offices were either leased by the VEC or located in space provided by the council. A full list of election office addresses at the 2012 local government elections is included in Appendix 3.

When it was required to lease premises, the VEC experienced some difficulty securing suitable accommodation due to the relatively short lease time (three to four months) and the lack of venues meeting accessibility requirements. The complexity of negotiating a lease was greater because agents often required a minimum of a six month lease. This limited the number and type of available locations. The versatility required for normal operations in an election office was also a challenge for councils when considering whether they were able to provide accommodation.

Frequently, available venues had been vacant for some time and had ageing or inadequate building and telecommunication infrastructure. In some cases, these problems could only be identified after the VEC had entered into a lease for the premises and significant additional work was required at a number of election office locations to establish telecommunication lines. This proved difficult in some areas of the State because local exchanges were at capacity. To assist in addressing these issues at future elections, the VEC will consider extending its required tenure for election office leases.

The VEC established two election office configurations – stand-alone and hub/satellite offices. Each configuration involved different equipment, staffing, hardware, and software requirements, and ultimately, different costs. The election office configurations are detailed below.

As a result of continuing improvements in technology, the VEC will review office configurations for future local government elections.

### Stand-alone election offices

Stand-alone offices are fully resourced election offices allocated to a single municipality. The 29 metropolitan elections and nine of the larger regional elections had stand-alone election office configurations. Although stand-alone election offices are the most costly configuration, the resources available at a stand-alone election office are essential for large-scale elections.

### Hub and satellite election offices

The VEC provided a hub and satellite election office configuration to smaller sized councils that were conducting postal elections. A hub and satellite election office results in reduced resourcing costs and separates front office and back office processes. The VEC established 16 hub election offices and 24 satellite election offices across rural and regional Victoria.

A hub election office is fully resourced as an election office and shares those resources with one or more satellite election offices in neighbouring municipalities. At the local government elections in 2012, the processing of returned postal ballot paper envelopes and the telephone enquiry service were operated out of the hub election offices. Satellite offices were mostly located in council premises and provided a point of contact for candidates and face-to-face public enquiries about the election.

While the hub/satellite configuration is generally more complex for the VEC to administer, the resource costs have been considerably less because staffing, computer equipment and other infrastructure costs can be shared between participating councils.

## Human resources

### Contract Managers

The VEC provided a team of five contract managers to supervise the contracts for the 78 councils. The contract managers were the key liaison between councils and the VEC and were responsible for representing the VEC during contract negotiations, providing regular formal and informal feedback and reports, and managing any issues that arose. All contract managers were familiar with the legislative requirements and were available to provide advice and assistance to council officers throughout the election period.

### Election Support Officers

During the election period, each Returning Officer was supported by one of 10 election support officers (ESOs) operating from the VEC’s head office. The ESOs had considerable experience in successfully managing elections and were responsible for providing guidance and procedural advice to Returning Officers.

### Casual staff

In addition to the 78 Returning Officers who were appointed for the duration of the election, the VEC also employed 62 Deputy Returning Officers, including 15 that were appointed to more than one election, and nearly 6,500 casual staff during the election period. To reflect the additional workload of larger and more complex elections, more than one Deputy Returning Officer was appointed for each of six larger elections.

Staffing profiles were prepared for each individual election to allocate resources appropriately and reflect the peak work periods during the election timeline.

The VEC made an effort to employ a diverse range of people to fill roles in election offices and voting centres at the local government elections in 2012. Among our staff, 624 people noted fluency in a foreign language, 46 people identified themselves as having an Indigenous heritage and 80 people identified themselves as either having a disability or having special needs in the workplace.

### Disclosure of political activities

In accordance with section 17A of the Electoral Act 2002 and section 75 of the Equal Opportunity Act 2010, the VEC may discriminate against a person in relation to offering employment on the basis of that person’s political belief of activity. Prior to their appointment, all staff appointed to roles for the local government elections in 2012 was required to satisfactorily complete a disclosure of political activities. The disclosure could then be assessed to ensure that there could no perception of political bias in relation to their work.

## Support services for Returning Officers

The VEC’s support for Returning Officers at the local government elections in 2012 included the provision of dedicated ESOs, training programs, training and operational manuals, and a help desk for information and technical support.

### Training and manuals

Newly recruited senior election officials were required to attend four days of orientation training during October to December 2011.

Returning Officers and Deputy Returning Officers were then selected from the full pool of available senior election officials. All Returning Officers and Deputy Returning Officers attended a two-day training seminar during April and May 2012, specifically in relation to the local government elections. Two further training programs, of two and three days respectively, were conducted during July and August 2012 to provide training targeted specifically for postal elections and attendance elections. In addition to those senior election officials identified for appointment as Returning Officers or Deputy Returning Officers, a number of additional senior election officials were invited to complete the training to enable them to be back-ups, if required.

The VEC provided Returning Officers and Deputy Returning Officers with comprehensive manuals explaining all procedures for the elections.

Returning Officers for attendance elections were provided with the resources required to present localised training for Voting Centre Managers, Assistant Voting Centre Managers and Declaration Issuing Officers.

Materials were also provided to support the localised training of team leaders for the conduct of manual preferential counts. Training for computer count team leaders was provided centrally.

All staff appointed at voting centres for attendance elections were supplied with a comprehensive manual covering procedures relating to their specific tasks and explaining the VEC’s standards and values. In addition, all of these staff were required to complete online training provided by the VEC.

### Help desk – information and technical support

The VEC established a central help desk to provide support with the use of the VEC’s Election Management System and desktop software to Returning Officers and their staff. The help desk was responsible for all calls from election offices. Calls were logged and were responded to in the first instance by help desk staff, or were referred directly to the IT help desk or ESOs.

The help desk staff comprised two supervisors and five full-time staff. Staff selection was based on previous electoral experience, awareness of election procedures and knowledge of election-based computer software and processes.

## Election Management System

The VEC’s Election Management System (EMS) is the secure computerised system used to administer and manage elections.

Returning Officers are provided with EMS in one of two ways:

- The provision of an EMS server, computers and printers established as an office network and linked back to the VEC’s central servers; or

- A laptop with a secure wireless connection that allowed the user to access a limited subset of the EMS information and functions.

The latter arrangement was used at satellite election offices and removed the requirement for the VEC to install software and provide large-scale hardware at these locations.

Establishing election office hardware is a large-scale logistical exercise. All hardware is pre-configured at the VEC warehouse, then packaged and shipped to election offices. Technicians are required to set up the hardware at the offices and to ensure the link to the VEC is operational. Each hub or stand-alone office was provided with a server, at least four computers, a photocopier that was networked as a printer and a stand-alone A4 printer.

## Information sessions for prospective candidates

The VEC organised one or more information sessions to provide information and key messages on the election process to prospective candidates in each of the 78 Victorian municipalities going to election (93 sessions in total). These information sessions were conducted by the appointed Returning Officers for each election, and were held close to the opening of nominations. See Appendix 4 for details of the VEC’s information sessions for prospective candidates.

The VEC also participated in community and candidate information sessions organised by other agencies in the local government sector, including the Municipal Association of Victoria (MAV) and Victorian Local Governance Association (VLGA). The VEC provided a representative at these sessions who was able to provide information on the election process. In some cases, the MAV or VLGA sessions were scheduled to take place with the VEC sessions.

## Nominations

The nomination fee set by the LG Act is $250 for each candidate.

The VEC received 2,004 active nominations for the 631 vacancies (273 elections) across 78 municipalities, including 85 nominations for Casey City Council and 72 for Melton City Council. Three candidates retired after the close of nominations and one candidate died before election day, leaving 2,000 active nominations at the close of voting.

There were 1,729 nominations for postal elections in 70 municipalities (including the City of Melbourne) and 271 nominations for attendance elections in eight municipalities. Across the 78 municipalities, 28 wards and unsubdivided municipalities experienced uncontested elections because the number of candidates at the close of nominations was equal to the number of vacancies. There were no failed elections.

Nominations for postal and attendance elections opened on Thursday, 20 September 2012 and closed at 12 noon on Tuesday, 25 September 2012.

Returning Officers received an average of 500 nominations per day over a four day period, with 423 nominations processed in three hours on the last day. A list of all candidates for the local government elections in 2012 is provided on the compact disc accompanying this report.

### Candidate eligibility

A small number of prospective candidates were found to be ‘not on the roll’ at the time of nominating. Clause 6(3A) of Schedule 2 of the LG Act states that:

(3A)	The returning officer must reject as being void a nomination from a person who is not enrolled on the voters' roll for the municipality unless the nomination is accompanied by a statutory declaration stating—

(a)	that the person is entitled to be enrolled being an entitlement other than under section 12(1) or 12(2);

(b)	the grounds on which he or she claims to be entitled;

(c)	what steps he or she has taken to be enrolled.

The VEC has interpreted this clause to mean that if, after such a statutory declaration has been made, neither the VEC nor the council can determine that the stated enrolment steps have been taken, that person is considered to be not entitled to nominate as a candidate. However, there appears to be no mechanism for rejecting the nomination.

The VEC believes that the nomination process would benefit from clarification of this provision. The LG Act includes a mechanism for amending the voters roll if it is determined that a prospective candidate was omitted from the roll in error.

Recommendation 5: Rejecting a nomination by a person not on the roll The VEC recommends that the Government considers amending clause 6(3A) of Schedule 2 of the LG Act to permit the Returning Officer to reject a nomination from a person who is not on the voters’ roll for the municipality.

### Online completion of nomination forms

At the local government elections in 2008, the VEC developed an online candidate helper to assist with managing the large number of nominations. The online candidate helper was also available for the local government elections in 2012 and went live on Friday, 14 September 2012.

The online candidate helper assisted candidates to complete their nomination forms through the VEC website. Once candidates using the online candidate helper had completed their nomination form, the details on the form were securely stored in the database and the candidate printed a barcoded nomination form. The nomination form was lodged the candidate or their representative along with the nomination fee at the election office. The Returning Officer was then able to scan the barcode on the printed nomination form to upload the candidate’s nomination information directly into the nomination application. This significantly reduced nomination times and helped eliminate data errors.

Although the online candidate helper was useful for most council elections, the system could not be used by prospective Leadership Team candidates at the Melbourne City Council election. These candidates were required to complete a hard copy nomination form.

Approximately 65% (1,296) candidates completed their nomination using the online candidate helper, a 16% increase on the number that used the facility in 2008. Candidates were responsible for ensuring that the data provided on the nomination form was correct and were required to approve a final quality assurance form printed by the Returning Officer from the VEC’s EMS.

The VEC will consider enhancing this application for future elections to cover candidates for all elections, including the Leadership Team for Melbourne City Council, and an option for candidates to lodge photographs online.

### Candidate information

An information kit was made available to prospective candidates that contained:

- Candidate Handbook;

- Nomination Form;

- Scrutineer Handbook;

- form for appointment and declaration of scrutineer;

- form for submitting candidate’s statement (postal elections);

- sample candidate statement and indication of preferences (postal elections);

- application form for registration of how-to-vote card (attendance elections);

- election campaign donation returns form;

- information on becoming a councillor;

- key election dates;

- a map of the municipality; and

- Returning Officer’s contact details.

The table at Appendix 15 provides details of the number of candidates at the local government elections 2012 and 2008.

### Ballot draw

All candidate information was held in the VEC’s Election Management System. The order of names on ballot papers was determined by a single electronic random draw in all except one municipality, where the Returning Officer experienced connectivity issues and conducted a manual ballot draw by lot.

The electronic draw for the election of councillors for Melbourne City Council ordered groups in the first instance, secondly it confirmed all group candidates had been allocated an order within the group and finally it ordered the three ungrouped candidates, as required by legislation.

The ability to automate the generation of the ballot material artwork helped ensure that timelines for the production of this material for the 245 contested elections were met. One reprint was required in South Ward, Frankston City Council after a candidate retired from the election, after ballot paper printing had commenced.

### Candidate statements and preferences (postal elections)

The period for lodgement of candidates’ statements and photos closed at 12 noon on Wednesday, 26 September 2012.

The period for lodgement of indication of preferences closed at 12 noon on Friday, 28 September 2012. The majority of candidates submitted an indication of preferences.

Previously the closing time for these activities was 4.00 pm. In its report following the local government elections in 2008, the VEC recommended that the timeline for lodgement of candidates’ statements and preferences be amended to be 12 noon. These changes were made and the deadlines are now consistent with the 12 noon deadline for all other candidate-related deadlines.

The online candidate helper provided candidates with the opportunity to create their statements online, and to check and change details before final submission (except for Melbourne City Council, where candidates still had to complete hard copy forms for their statements and preferences). Once candidates were satisfied with the statement, the form was printed and issued with a barcode. After the ballot draw, candidates had the opportunity to enter their preferences online in the same way. Candidate statements and preferences still had to be lodged at the election office by the candidate or a person authorised by the candidate.

In one municipality, a small number of candidates missed the deadline to submit their completed indication of preferences form despite being in the election office and after a number of reminders of the 12 noon deadline by the Returning Officer.

Of the 1,671 candidate statements submitted (excluding those from the Melbourne City Council), 1,096 candidate statements were completed online (66%). Of the 1,511 indications of preferences submitted (excluding those from the Melbourne City Council), 325 were completed online (22%). Candidates were responsible for the content of their statements and for their indications of preferences. Final copies of statements and preferences were printed by the Returning Officer. The candidate or a person authorised by the candidate checked and signed the forms to confirm they had been reproduced as submitted.

Candidate statements were published as provided with no amendments to grammar or spelling by VEC staff. No discrepancy between what candidates submitted and what was published was reported. This ensured that all ballot material was able to be quality assured and sent to the printer a short time after the close of prefernces.

Candidate statements for the relevant election were provided to voters in their postal ballot packs. Candidates’ statements and preferences were also published on the VEC’s website, as required by Regulation 38 of the LGR, and where a candidate provided a public contact, these details were also published on the VEC’s website pursuant to clause 11(2) of Schedule 2 of the LG Act.

To assist with improving accessibility and efficiency for candidates at future local government elections, the VEC considers that a provision to permit candidates to submit their candidate statements and indications of preferences electronically at future local government elections would enhance existing provisions that require candidates (or their representatives) to attend the election office. This is particularly important for regional and rural municipalities where candidates are often required to travel long distances with each visit to the election office. If received electronically, the declaration that is required with a candidate statement could be compared with the candidate’s original signature on his or her nomination form.

Recommendation 6: Submitting candidate information electronically The VEC recommends that the Government considers legislation to allow candidates to electronically submit their candidate statements and indication of preferences to the Returning Officer.

### How-to-vote cards for attendance elections

Division 2 of the LGR provides for how-to-vote cards (HTVCs) for attendance elections. Only registered HTVCs can be handed out within 400 metres of a voting centre during early voting, or distributed within 400 metres of a voting centre during the hours of voting on election day.

In accordance with Regulation 27 of the LGR, candidates at local government elections using the attendance method of voting were able to register HTVCs from Wednesday, 26 September until 12 noon Friday, 19 October 2012. A total of 506 HTVCs were registered for the 271 candidates contesting attendance elections in eight municipalities.

The names of the candidates, persons or groups for whom HTVCs were registered were published on the VEC’s website in accordance with Regulation 31(1)(b) of the LGR.

Candidates commenced lodging HTVCs immediately after the opening of the registration period, with applications being received on a daily basis. This may indicate that candidates are aware that HTVCs had to be registered in order to be distributed at early voting centres. In accordance with Regulation 29 of the LGR, Returning Officers advised candidates before 12 noon on the next working day after lodgement whether a HTVC had been registered or refused to be registered.

Any person may apply to the Victorian Civil and Administrative Tribunal (VCAT) for review of a Returning Officer’s decision to register or not to register a HTVC. Such an application must be made by noon on the second working day after the day on which the Returning Officer made his or her decision. No applications were made to VCAT in relation to decisions made by Returning Officers for these elections. Appendix 14 contains a table showing the number of HTVCs registered during the local government elections in 2012.

Candidates generally find the process of registering HTVCs to be complicated and labour intensive. The requirement to register HTVCs for distribution at early voting centres puts pressure on candidates to finalise preference allocations and complete the registration process quickly. This often leads to candidates registering more than one card to cover a range of different preference allocations.

A few enquiries concerning registered and unregistered HTVCs were received by Returning Officers. The VEC also received requests to publish registered HTVCs on its website, however, these requests were declined as online publication is not provided for within the LG Act or LGR in the same way that candidates’ statements are published online for local government elections being conducted using the postal method of voting. The VEC accepts that an amendment to the legislation requiring the publication of registered HTVCs online would be complex to administer on a card-by-card basis given the timelines and number of cards involved.

An option would be to require registered HTVCs to be published at the conclusion of the registration period.

Recommendation 7: Online publication of how-to-vote cards The VEC recommends that the Government considers requiring the publication of all registered how-to-vote cards in relation to a local government election on a website administered by (or on behalf of) the Returning Officer as soon as practicable after the completion of the period for registration.

In relation to early voting at local government elections, the requirements to register HTVCs includes cards being handed out within 400 metres of early voting centres during the period of early voting. The VEC notes that while the Electoral Act 2002 requires that HTVCs must be registered for distribution within 400 metres of election day voting centres, there is no requirement to register HTVCs distributed at early voting centres for Victorian Parliamentary elections.

The LG Act contains provisions that prohibit the distribution of election material that is misleading or deceptive in addition to the provisions relating to the registration of HTVCs. There is also provision in the LG Act for a person to seek an injunction to restrain another person from distributing material that is misleading and deceptive. Therefore there is time during early voting for a person to object to the distribution of a particular card. The ability to challenge or stop the distribution of a card on election day is more restrictive.

Recommendation 8: How-to-vote cards during early voting The VEC recommends that the Government considers removing the requirement for how-to-vote cards to be registered for distribution at early voting centres.

### Study of how-to-vote card conformity

Voters at most local government elections in Victoria are required to complete their ballot papers using the full preferential voting system. This system means that voters must number every box on the ballot paper in order of their preference for their ballot paper to be considered formal. In unsubdivided councils and wards electing more than one councillor, there can often be large numbers of candidates on the ballot paper. The dynamics of the full preferential system encourage candidates to negotiate preference deals with each other so that they can benefit from preferences flowing from elected or excluded candidates. To maximise a candidate’s chances of election, he or she may issue directions to voters on how to allocate their preferences. In local government elections being conducted by postal voting, indications of preferences are printed with the candidates’ statements included in the ballot material that the VEC posts to every voter on the municipal voters’ roll. In attendance elections, candidates and their supporters are able to register and distribute HTVCs to voters outside voting centres on election day or early voting centres during the period of early voting.

For elections counted by computer, the VEC holds the preferences for each vote, which can be sorted by candidate and by conformity with how-to-vote instructions.

The VEC selected 14 elections to study – including 13 multi-councillor wards and one unsubdivided council. To ensure a representative sample, the sample included both attendance and postal elections, from inner suburban, outer suburban and regional areas, and covers a range of socio-economic variables.

In summary, the findings of this study of ballot papers for 14 elections are:

- 42.8% of voters followed how-to-vote instructions

- voters in postal elections (44.7%) were more likely than those in attendance elections (36.2%) to follow how-to-vote instructions

- there were no clear differences in behaviour between metropolitan and regional councils, nor between councils with high proportions of culturally and linguistically diverse voters and councils with low proportions

- the number of candidates in an election did not affect compliance with how-to-vote instructions

- voters for incumbent councillors and winning candidates were more likely to follow how-to-vote instructions, and voters for minor candidates (those who failed to regain their deposit) were less likely to do so. This tendency was stronger in attendance elections, but not apparent in regional elections.

A paper detailing the study and findings from the study can be found at Appendix 5 of this report.

## Ballot packs and voter notices

During the conduct of a postal election, the Returning Officer must send or deliver to each voter on the voters roll who is entitled to vote at the election—

- a postal vote declaration envelope

- the candidate statements and indications of preferences for the particular ward or municipal district

- a ballot paper for postal voting

- a prepaid envelope for the return of the ballot paper

- instructions about how to vote correctly

- notice of how and when the ballot paper must be returned

- any document prescribed for the purposes of this paragraph and

- any other material that the Returning Officer thinks is appropriate.

Some councils also requested a multi-language leaflet to be included in the ballot pack (see section 6.26.11 of this report).

### Design and printing of ballot papers

The VEC reviewed the design and colour of ballot papers for the local government elections in 2012. As for previous elections in subdivided municipalities, the ballot paper for each ward was in a different colour to help ensure that voters receive the correct ballot material. Ballot papers were produced using a security background print to ensure their integrity.

The printer responsible for the secure printing of the ballot paper/candidate statements was contracted by the VEC in 2009 as a result of a tender process. The company was experienced in the VEC’s requirements and worked closely with the VEC in the design and development of its current ballot material, which includes a ballot paper with a perforated edge attached to the candidate statements and indications of preferences.

### Production and mail-out of ballot material for postal election

Regulation 81 of the LGR requires that the ballot packs are randomly mailed, at least 15 days before the last day of voting, with no more than 35% being posted or delivered on any one day. Over the three-day period, Tuesday, 9 October to Thursday, 11 October 2012, the VEC mailed out 3,295,178 ballot packs for postal elections. A sample ballot pack can be found at Appendix 6.

The production of the ballot material for postal elections to meet legislative timelines places considerable pressure on print production and mailing. The VEC again utilised direct extraction of ballot paper/candidate statements data from the Election Management System using Extensible Markup Language (XML) into pre-prepared ballot paper/candidate statement templates. Each template was specifically coded to accept whatever number of candidates nominated for a particular election.

This process, introduced for the local government elections in 2008, gave the VEC a faster turnaround of ballot paper/candidate statement print-ready artwork

that included the ballot paper, candidate statements, photographs and indication of preferences.

Implementation of this process again in 2012 meant that all artwork for postal elections was with the printer by 7.00 pm on Friday, 28 September 2012. Printed materials, including the items listed above plus envelopes, are then collated at a mailhouse.

On Wednesday, 10 October 2012, the Returning Officer for the Greater Geelong City Council General Election was alerted that the ballot packs sent to all voters in that municipality included the standard declaration envelope, which instructed voters to only insert one ballot paper, rather than the product specifically designed for the City of Greater Geelong, where each voter had two ballot papers to complete due to the separate elections for the mayor and councillors. To correct any confusion, all voters were sent a letter on Wednesday, 10 October 2012 advising them that the instructions on the declaration envelope should be read as referring to two ballot papers. The VEC also issued a media release, and placed correction notices in local papers. The Returning Officer, in conjunction with VEC head office, prepared a protocol for dealing with returned ballot papers to ensure that no voter was disenfranchised as a result of following the instruction on the standard envelope.

Due to the large volumes of mail to be lodged with Australia Post on each of the three legislated dates, the VEC made arrangements with Australia Post to store prepared ballot material at their postal facility in Laverton. The ballot material was held at Laverton until the day of lodgement. It was then transported to the Dandenong Mail Centre, where it was released for lodgement.

Regional mail was then forwarded to one of five mail-sorting centres before delivery to local post offices and postal delivery agents. While this is standard Australia Post practice for mail lodged through the Dandenong Mail Centre, this process adds one day to the mail delivery times in rural areas. The delay may be compounded in some areas, where voters collect their mail from the town centre. Such delays are not generally experienced in metropolitan areas.

It should be noted however, that people in regional areas are usually accustomed to local mail delivery patterns, and the return rates of ballot material in these areas are generally higher than in metropolitan areas.

The VEC observed a large number of calls from voters who received ballot material well into the voting period and also a large number of voters attending election offices on the last day of voting who claimed to have received ballot material too late for return posting or not at all. The VEC has raised these observations with Australia Post who responded that their agreed delivery targets were met.

Recommendation 9: Timeline for postal elections The VEC recommends that the Government notes that mail delivery patterns have changed affecting the dispatch and return of standard mail services.

### Late return of ballot material

The VEC received 107,611 returned ballot packs during the first three business days following election day (Monday, 29 October to Wednesday, 31 October 2012). Some of this material would have been posted on or after election day.

Ballot material received after the closing time must be excluded from the count.

|  | 2008 | 2012 |
| --- | --- | --- |
| Metropolitan councils | 2.43% | 2.61% |
| Rural/Regional councils | 1.73% | 2.89% |

Figure 2: Ballot material returned in the three working days after election day as a proportion of enrolment, by council type

## Fraud prevention initiative

In the past, there have been isolated and unsubstantiated allegations that postal elections in Victoria are open to postal voting fraud. The VEC is committed to implementing legislative and administrative measures that could further protect the integrity of postal voting. With 70 of the State’s 78 councils conducting their elections using the postal method of voting, the VEC once again implemented a variety of fraud detection and prevention measures including:

- postal ballot material specifically designed to fit a standard household letterbox with no protrusion;

- random checks by VEC staff at high density residential blocks during the mailout period;

- a radio and print advertisement campaign coincided with the mailout of ballot packs, and security personnel were hired to conduct a total of 1,160 hours of observation around particular housing estates with bulk letterboxes in a common area in Melbourne’s inner city. No concerns were raised in relation to postal election fraud by the observations of security personnel;

- a partnership with Crime Stoppers Victoria, including sponsored print and radio advertising campaigns aimed at encouraging members of the public to call Crime Stoppers if they observed suspicious activity in relation to the suspected theft of ballot packs or suspicious activity near letterboxes;

- a ‘signature check’ against source documents. Although there is no legislative requirement to do so, spot checks were conducted to compare signatures on declaration envelopes with original signatures on enrolment forms or other source documents

Two calls were received by Crime Stoppers and were forwarded to Victoria Police for investigation. The VEC has no information in relation to these reports.

While respecting the anonymity attached to the Crime Stoppers program, the VEC has requested information from Victoria Police in relation to whether these allegations were investigated, and whether the matter was dismissed or prosecuted. At the time of this report, Victoria Police had not granted this request.

Two further matters identified during the checking process have been referred to the LGICI for their evaluation and possible investigation.

## Voting centres for attendance elections

Regulation 50 of the LGR requires that the Returning Officer [in an election being conducted using the attendance method of voting] must appoint as many voting centres as the Returning Officer considers necessary.

The VEC established 173 election day voting centres for the eight attendance elections. In addition, the VEC established at least one early voting centre in each municipality to operate between 9.00 am and 5.00 pm each weekday from Wednesday, 26 September 2012. Additional early voting facilities and hours were provided at councils’ request.

A list of venues proposed as voting centres for each attendance election was provided to councils by the VEC. In selecting venues, the VEC considered venues that had previously been used as voting centres at State, Federal or local government elections and ensured that, where possible, they were well located within each ward. Voting centres that were too close to ward boundaries were avoided. The VEC recommended venues that provided maximum access for voters and tried to ensure that there was at least one fully accessible voting centre in each ward. The VEC provided the list of recommended voting centres to councils for feedback, and, in keeping with the requirements of the legislation, the Returning Officer made the final decision regarding the appointment of voting centres.

### Accessibility of voting centres

The VEC reviewed the accessibility audit tool used at previous elections and made some updates to the document based on new accessibility requirements. All attendance election Returning Officers were provided with instruction and support in the use of the audit tool – to ensure a clear understanding of the considerations necessary when choosing venues suitable for use as a voting centre.

The VEC made efforts to locate at least one venue with full wheelchair access in each ward. However, the absence of suitable venues severely limited those opportunities. The VEC was able to provide at least one fully wheelchair-accessible venue in each municipality, and there was a total of 30 (17%) fully wheelchair-accessible venues across the eight attendance elections. Of the remaining venues, 107 (62%) were classified as ‘wheelchair access with assistance’ and 36 (21%) had no wheelchair access, a reduction on the proportion with no wheelchair access in 2008 (25%).

The VEC is working with relevant State Government departments under the auspices of the 2013-2016 Victorian State Disability Plan to address areas with the least number of fully wheelchair accessible voting centres.

## Postal voting and early voting at attendance elections

The eight attendance elections had an early voting centre established at the election office, and early votes were able to be issued for each ward in the municipality from Wednesday, 26 September until Friday, 26 October 2012. At least one additional early voting centre per council was established to issue early votes in the period leading up to election day. Greater Dandenong City Council had three additional early voting centres operating away from the election office that only operated in the last three days of early voting.

Early voting centres were open week days from 9.00 am to 5.00 pm until Thursday, 25 October 2012 when centres operated from 9.00 am to 8.00 pm. All centres were open until 6.00 pm on Friday, 27 October 2012. In addition, the election office early voting centre for the Banyule City Council General Elections was open on the four Saturdays prior to election day from 9.00 am to 12 noon. On application, postal voting was available for each of the eight attendance elections.

10,563 postal ballot packs were dispatched to voters registered as General Postal Voters (GPVs) for attendance elections. The GPV ballot material was dispatched to voters on Friday, 28 September 2012. Applications from voters who were not registered as GPVs were received until 12 noon on Thursday, 25 October 2012.

Postal votes made up 6.82% of all votes, and early voters comprised 20.57%, making a total of 27.38% of the total votes counted. This represents an increase of 4.39% in the number of postal and early votes counted compared to the previous round of elections.

|  | Votes | Postal votes (inc. general postal votes) | Early votes |
| --- | --- | --- | --- |
| 2012 | 393,146 | 26,794 (6.82%) | 80.864 (20.57%) |
| 2008 | 558,557 | 29,781 (5.33%) | 98,643 (17.66%) |

Figure 3: Number of postal and early votes at attendance elections

The VEC notes that Regulation 44(4) of the LGR specifies that postal vote applications can only be sent by post or fax, and does not provide for applications to be lodged by email. During the early voting period, the VEC received a number of requests from voters in councils using the attendance method of voting who were interstate or overseas and wanted to participate in the election but did not have access to a fax and there was insufficient time for the Returning Officer to receive their postal voting application by post, dispatch a postal vote to the voter, and for that postal vote to be completed and returned by the voter.

The VEC notes that legislation for Commonwealth and New South Wales elections provides for postal vote applications to be lodged electronically. The requirement to sign the application has been replaced by alternative voter authentication processes (e.g. Secret question).

Recommendation 10: Postal voting applications The VEC recommends that the Government amends Regulation 44(4) of the Local Government (Electoral) Regulations 2005 to allow voters to electronically lodge a postal voting application in relation to voting at an attendance election.

## Electronic Roll marking

For the local government elections in 2012, the VEC opted to use electronic roll marking (eRoll).

Voters at attendance elections were marked off the roll electronically with the vast majority recorded on Toshiba netbooks wirelessly connected to the VEC on the Next-G network. The remainder of voters, and all of those voting in postal elections, were directly marked off the roll using the VEC’s Election Management System.

On election day, 849 netbooks were deployed across the 173 voting centres and by close of voting 178,580 votes had been issued to voters who were marked off the roll using netbooks.

Training in the use of netbooks was provided for early voting staff, voting centre managers and election officials using a mixture of face-to-face, paper documents, DVD and video distributed over YouTube. The aim was to familiarise all users on the operation of the netbooks in advance of election day and to alert them to the fact that voters were to be marked off electronically.

The eRoll system and Next-G network performed well during the early voting period. Despite a network disruption that affected some netbooks early on election day, voting proceeded smoothly and scannable rolls were available as a back-up. Netbooks were brought back online as quickly as possible, however, some voting centres continued with back-up procedures until the close of voting.

When an issue was encountered, the VEC help desk was able to initiate troubleshooting routines so problems were identified and rectified.

The recording of a timestamp with each roll mark enabled a comprehensive track of voting behaviour during an election day, as well as an immediate indication of individual user and voting centre activity. The use of the eRoll also eliminates the risk of a person voting more than once.

## Services for the people who are blind or with low vision

To assist blind and low vision voters read election publicity or promotional material they received, the VEC liaised with Vision Australia so that a closed-circuit television monitor (CCTV) to magnify printed material was available at each of the election offices for those councils having attendance elections. A CCTV was also made available for the Melbourne City Council election office.

For the local government elections in 2012, the VEC again offered an ‘opt in’ service for the provision of large print and Braille ballot products to voters registered as blind or with low vision. The VEC liaised with Vision Australia and Blind Citizens Australia to provide information via three major communication pieces (email, Braille and CD formats) about the elections and the VEC’s ‘opt-in’ program for Braille or large print ballot papers for the 2012 council elections. To complement the provision of information to those registered on databases, a radio advertising campaign ran on 3AW and Vision Australia Radio during August and print advertisements were run in The Age, Herald Sun and Geelong Advertiser on Saturday, 11 August 2012.

A total of 182 people registered for the program – 36 for a Braille ballot pack, and 146 for a large print ballot pack. Feedback received by the VEC was very positive. Continued evaluation and modification of the program will enable the VEC to consider providing a similar service at future elections.

The special ballot packs included the required ballot paper, a declaration envelope, the candidate statements (for postal elections) and voting instructions in Braille or large print. A pre-paid pre-addressed Australia Post satchel was also included.

All Braille products were produced by Vision Australia, which ensured that the instructions were written in a style appropriate for the formats. Voters from 23 councils registered to receive a Braille ballot pack.

At the close of nominations there were four uncontested elections for which registrations had been received for large print ballot material. The VEC sent these voters an uncontested leaflet in large print and telephoned to inform them they would not be required to vote.

As detailed above, the VEC provided voters who are blind or who had low vision with the opportunity to request a Braille or large print ballot paper. There is currently no provision in the legislation to provide for this. The VEC treated these requests from voters at a postal election, as requests for replacement ballot material. Requests from voters at an attendance election were treated as applications for postal votes and the VEC assisted the voters to complete a postal vote application as required by the current provisions. The production of a Braille application could not be achieved in the available time and, as such, was difficult to administer.

Recommendation 11: Provision of ballot papers in Braille The VEC recommends that the Government considers a legislative provision that exempts voters who request a Braille ballot paper at an attendance election and who are not already registered as a General Postal Voter from the requirement to complete a written application.

## Services for people experiencing homelessness

For the local government elections in 2012, in the two months prior to the close of rolls, 15 organisations providing services to those experiencing homelessness in Metropolitan Melbourne, Geelong and Bendigo were visited to raise awareness of the upcoming election in staff meetings. Of these, nine organisations were visited to conduct enrolment sessions which were later followed by voting sessions. Overall, these sessions resulted in 130 new enrolments and 120 votes. More than 200 additional clients were provided with information relevant to their enrolment status and participation needs.

Information about enrolment and voting provisions for people experiencing homelessness, as well as the offer of regional enrolment and/or voting sessions, was distributed regionally via the Council to Homeless Persons (CHP) regional homelessness network. Other activities included:

- a ‘Homeless not Voteless’ resource kit which was sent to over 142 homelessness agencies across Victoria with information regarding the ‘Homeless not Voteless’ program and services available. This kit included information for those experiencing homelessness and the staff supporting them, along with posters and fliers to advertise the upcoming election;

- directly contacting agencies in metropolitan regions in Melbourne, Geelong and Bendigo to gauge interest and schedule sessions; and

- information on the VEC website detailing initiatives for people experiencing homelessness.

Information about enrolment and voting provisions for people experiencing homelessness was also distributed regionally via the CHP regional homeless network.

## Close of voting

Voting in elections being conducted using the postal method of voting closed at 6.00 pm on Friday, 26 October 2012. Voting for those elections using the attendance method of voting closed at 6.00 pm on Saturday, 27 October 2012. A number of activities take place between the close of voting and the final declaration of the result.

For postal elections these activities include:

- final processing of returned postal vote declaration envelopes;

- checking of voter entitlement for any unenrolled votes;

- identification and resolution of duplicate ballot paper envelopes;

- removal of identification flaps from ballot paper envelopes;

- opening and extraction of ballot papers from ballot paper envelopes;

- for manual counts, counting of ballot papers according to first preferences and where necessary the conduct of preference distributions;

- conducting computerised preference distributions; and

- the declaration of the result at a time that allows candidates and scrutineers reasonable time to review the result reports.

For attendance elections these activities include:

- counting first preference votes in voting centres on Saturday night;

- counting postal, early and absent votes in election offices on Saturday night and Sunday morning;

- receiving and sorting materials from voting centres;

- checking voter entitlement for any unenrolled votes;

- where manual preference distributions were required, conducting a full re-check of all ballot papers;

- conducting preference distributions where necessary, either manually or by computer; and

- the declaration of the result at a time that allows candidates and scrutineers reasonable time to review the result reports.

In the past, the VEC has noted that pushing to achieve a pre-determined declaration time resulted in less than ideal situations including processes beginning before the total number of ballot papers to be accounted for was finalised, staff fatigue and some candidates claiming they did not have a reasonable time to review the results prior to the declaration taking place. The only avenue available to candidates to request a recount after the declaration of the result is through a Municipal Electoral Tribunal.

The VEC’s timetable for counting was altered at the local government elections in 2008 to ensure that reconciliations were completed before the commencement of each stage of the process. The proposed timetable specified that extraction of ballot papers for all postal elections would commence on the Saturday morning after the close of voting. In discussions with councils, the VEC explained that the time and date of the declaration would be negotiated after the close of nominations when the size of the task was clearer. An undertaking was given that, except for any unforeseen circumstances, declarations would be completed by Friday, 2 November 2012 (five working days after election day).

For postal elections involving computer counts, some extraction of ballot papers was prioritised to ensure that data entry was completed before the end of the weekend when access to some counting venues ceased. These venues were generally at schools or TAFE colleges that needed the venues for classes on Monday, 29 October 2012.

Feedback from Returning Officers regarding the counting arrangements was positive. A number of election offices for postal elections still had a number of staff working late on Friday night due to large volumes of mail being received on Friday, 26 October 2012 and the large number of last minute voters attending election offices to vote in person. However, the arrangement allowed all mail processing to be completed and the total number of ballot paper envelopes to be determined before ballot paper extraction commenced on the following morning. Through its debriefing program the VEC has identified further administrative efficiencies that could be implemented for computer counts.

The VEC will continue to work with councils prior to the local government elections in 2016 to ensure that counts and declarations can be completed as efficiently as possible without compromising accuracy, transparency and staff wellbeing.

## Counting arrangements

Various counting arrangements were used across each of the 78 local government elections. Most proportional representation counts were conducted by computer, with one manual proportional count. Most preferential counts were conducted manually, except for the Melbourne City Council Leadership Team and Greater Geelong City Council Mayoral elections, which were conducted by computer.

Proportional representation counting alone took place in 50 municipalities. In 11 municipalities, counting was by the preferential method alone, and a combination of preferential and proportional representation counts took place for 16 municipalities. No counting took place for Ararat Rural City as the election for the unsubdivided municipality was uncontested.

See Appendix 12 for details of counting arrangements for each council.

### Manual counts

Full manual counts were conducted for three of the eight councils that used the attendance method of voting and in seven councils that used the postal method of voting. All manual counts were conducted within the municipality in which the election was held.

Where space was restricted, the extraction of ballot papers at postal elections occurred at a separate location to the count.

The proportional representation count for Yarran Ward in Gannawarra Shire Council was conducted manually due to the low numbers of voters and candidates.

### Computer count

Computer counts were conducted for elections in unsubdivided municipalities and wards with multi-councillor vacancies (where a proportional representation count is required). Computer counts were conducted at 65 venues for five attendance elections and 62 postal elections. For the Melbourne City Council General election, a computer count was conducted for the Leadership Team (preferential count) and for the election of councillors (proportional representation count). The Greater Geelong City Council Mayoral election (preferential count) was also counted by computer due to the large number of ballot papers involved.

The computerised counts involved preferences from ballot papers being entered into the computer count application, by trained data operators, in the presence of scrutineers.

The VEC prefers to use venues such as TAFE colleges and universities for the conduct of computer counts by data entry as the infrastructure and hardware required for the count is in place along with appropriate security measures and controlled access for scrutineers and staff.

The VEC encountered difficulty sourcing computer counting venues for the local government elections in 2012 due to some venues having experienced problems with other clients, which made them unwilling to lease their venues to the VEC. This restricted the types of venue available to the VEC in some areas.

Due to the growing trend for students to provide their own laptop or tablet, or for schools to use mobile laptop banks, it is becoming more difficult to source venues with established computer laboratories. It is anticipated that by the next local government elections in 2016 this issue will impact on the VEC’s ability to source computer counting venues in each municipality where computerised counting is to be conducted.

The establishment of computerised counts was simplified for the local government elections in 2012 with the introduction of an updated computerised counting application that reduced the information technology infrastructure and support required. Counting staff were provided with a unique log-on and password for each election and accessed the application via a web browser.

Computerised counts took place on Saturday, 27 October 2012 for 23 regional councils and one ward of Hobsons Bay City Council. The remaining computerised counts took place on Sunday, 28 October 2012, except for Moreland City Council where counting began on Monday, 29 October 2012. All computer counts were completed by Tuesday, 30 October 2012.

The introduction of the updated computerised counting application meant that, unlike 2008 where smaller regional counts were conducted manually, all proportional representation counts were counted by computer (with the exception of Yarran Ward in Gannawarra Shire Council).

The requirement to vacate a number of computer count venues located in colleges or universities by Monday morning to allow classes to resume put additional pressure on some counts to work shifts that were longer than desirable over election weekend and meant that some recounts were required to be conducted outside of the relevant municipality.

The VEC recognises it will need to consider its computer counting strategy for future elections. Lifting the legislative requirement for Council to pass a resolution agreeing to conduct computer counts outside the municipality would provide greater flexibility in this regard. This would also assist with countback requirements during the term of a council.

Recommendation 12: Counting outside the municipality The VEC recommends that the Government considers removing the requirement for a Council to pass a resolution in accordance with Regulation 93(2) of the Local Government (Electoral) Regulations 2005 thereby providing for circumstances where a Returning Officer (or election service provider) cannot secure a suitable counting venue within the municipal district.

## Recounts

Clause 13 of Schedule 3 of the LG Act states that the Returning Officer may, if he or she thinks fit, or at the written request of a candidate, conduct a recount of votes at any time before a candidate has been declared elected.

Recounts were conducted in six municipalities. In all cases, there was no change in the successful and unsuccessful candidates.

Where the original count was conducted manually, the recount was conducted manually. If the original count was conducted by computer, the recount was conducted using the same method. A recount involves a full review of all ballot material.

If the recount is conducted by computer, the recount includes the following steps:

- A recheck of all informal ballot papers. At the completion of the recheck, the Returning Officer may decide that it is unnecessary to proceed to a full recount. The Returning Officer adds any ballot papers now identified as formal to the original count database as a further batch and recalculates the result. The VEC refers to this as a partial recount.

- If proceeding to a full recount, the preferences on every ballot paper are re-entered into the computer application, which saves the information and checks that the re-entered preferences are the same as they were for the corresponding ballot paper at the original count. If they are the same, the original record is maintained on the database. If they are not the same, the operator is alerted to check the data entry, and if confirmed, the original preferences for that ballot paper are overwritten with the confirmed preferences.

| Council | Ward | Recount type | Recount type | Original critical margin | Final critical margin | Total ballot papers | Change in the critical margin |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Alpine | Unsubdivided | Computer | Full | 3 | 4 | 8,717 | +1 |
| Golden Plains | Unsubdivided | Computer | Full | 4 | 1 | 12,237 | -3 |
| Knox | Baird | Manual | Full | 28 | 28 | 8,301 | 0 |
| Moreland | North-East | Computer | Partial then full | 1 | 4 | 27,405 | +3 |
| Swan Hill | Robinvale | Manual | Full | 19 | 20 | 1,442 | +1 |
| Macedon Ranges | South | Computer | Full | 10 | 7 | 8,639 | -3 |

Figure 4: Recounts conducted during the local government elections in 2012.

After the results for all wards of Hume City Council had been declared, the Returning Officer became aware of a discrepancy in the count of ballot papers for Aitken Ward. Investigation found that 1,100 ballot papers had not been data entered at the computer count and remained uncounted. Despite the declaration having been made, the VEC determined it was necessary to data enter the uncounted ballot papers and recalculate the count to reinstate confidence in the results of the election and remove uncertainty about the effect of the discrepancy. After notifying all candidates and the Council, the uncounted ballot papers were data entered, and the result for Aitken Ward recalculated. The successful and unsuccessful candidates were unchanged.

## Declaration of results

All results for 77 of the 78 councils were declared on or by Wednesday, 31 October 2012, with the final ward declared on Friday, 2 November 2012.  A table showing the dates for declarations of results can be found at Appendix 13.

## Reports to Councils

Pursuant to clause 14 of Schedule 3 of the LG Act, the Returning Officer at a local government election is required to prepare a report to the Chief Executive Officer of the relevant council on the conduct of the election within three months of election day.

Final reports on each election were sent to Chief Executive Officers on Thursday, 24 January 2013. The reports included a certified record of ballot papers and declarations printed, issued, used, spoiled and returned as required by the legislation. Comprehensive details and statistics regarding election arrangements and outcomes were also included in the reports.

## Successful candidates

Appendix 14 contains a list of successful candidates. A list of all candidates is provided on the CD that accompanies this report.

## Voter turnout

Voter turnout is measured as the number of formal and informal votes received by the close of voting, as a percentage of voters on the roll.

At the local government elections in 2012, voter turnout for all those entitled to vote (excluding elections for Melbourne City Council’s Leadership Team and Geelong City Council’s Mayor) was 70.96%. The rate for postal elections (72.53%) was higher than that for attendance elections (63.62%). Turnout rates decreased across all categories compared with 2008 rates, which is of concern to the VEC and countering this decline will be a focus of evaluation and future planning. See Figure 5 and Appendices 14 and 15 for further detail.

Regulation 116 of the LGR details the provisions for the enforcement of compulsory voting in local government elections. There are several categories of entitlement for which voting is not compulsory, and a number of reasons for which a person may be excused for failing to vote.

## Informal voting rates

The incidence of informal voting at the local government elections in 2012 was 5.51%, an increase on the rate seen in 2008. The rate of informal voting remained significantly higher for attendance elections, at 10.09% compared to postal elections, with a rate of 4.65%.

A vote is declared informal when a voter does not complete their ballot paper according to the instructions or their voting intention is not clear. For a ballot paper to be considered formal in a local government election, the voter must complete an unbroken sequence of preferences filling every box on the ballot paper commencing with the number 1 (full preferential voting). Ballot papers that do not comply with the formality rules are not admitted to the count.

|  | Turnout % | Informality % |
| --- | --- | --- |
|  | 2004 2005 | 2008 | 2012 | 2004 2005 | 2008 | 2012 |
| All Councils (ex Melbourne Leadership Team and Geelong Mayor) | 73.89 | 74.68 | 70.96 | 4.60 | 4.99 | 5.51 |
| All Councils (inc Melbourne Leadership Team and Geelong Mayor) |  | 74.36 | 70.89 |  | 4.98 | 5.39 |
| Attendance | 67.59 | 70.03 | 63.62 | 9.84 | 9.90 | 10.09 |
| Postal (ex Melbourne Leadership Team and Geelong Mayor) | 75.51 | 75.96 | 72.53 | 3.50 | 3.75 | 4.66 |
| Postal (inc Melbourne Leadership Team and Geelong Mayor) |  | 75.51 | 72.32 |  | 3.77 | 4.58 |

Figure 5: Turnout and informal voting rates over time (% of all votes cast)

An analysis of informal voting showed that informal voting at the local government elections in 2012 increased as the number of candidates increased. In general, there were higher numbers of candidates for multi-councillor wards than for single-councillor wards. The average rate of informal voting in multi-councillor wards was 4.51 %, compared with 3.44% in single-councillor wards.

| Candidates | % informal votes 2012 (average) |
| --- | --- |
| 2 – 5 | 3.06 |
| 6 – 10 | 4.14 |
| 11 – 15 | 5.87 |
| >15 | 8.13 |
| 16-20 | 7.67 |
| 21-25 | 11.33 |
| >25 | 8.09 |

Figure 6: Average informality rates compared to numbers of candidates for all elections, 2012 local government elections

| Candidates | % informal votes 2005 (average) | % informal votes 2008 (average) | % informal votes 2012 (average) |
| --- | --- | --- | --- |
| 2 – 5 | 6.89 | 6.07 | 6.59 |
| 6 – 10 | 9.78 | 8.26 | 8.64 |
| 11 – 15 | 15.23 | 12.59 | 11.62 |
| >15 | 21.09 | 18.24 | 18.33 |
| 16-20 | 21.09 | 16.68 | 15.42 |
| 21-25 | - | 21.37 | 21.23 |
| >25 | - | - | - |

Figure 7: Average informality rates compared to number of candidates for attendance elections

| Candidates | % informal votes 2005 | % informal votes 2008 | % informal votes 2012 |
| --- | --- | --- | --- |
| 2-5 | 2.59 | 2.05 | 2.48 |
| 6-10 | 3.38 | 2.72 | 3.11 |
| 11-15 | 4.67 | 4.05 | 4.81 |
| >15 | 7.76 | 6.28 | 7.63 |

Figure 8: Informality rates compared to numbers of candidates for postal elections

The disparity between attendance and postal elections in relation to the rate of voter turnout and the incidence of informal voting has been a consistent feature over time (see Figure 9).

| Local government elections | 2004 | 2005 | 2004 & 2005 | 2008 | 2012 |
| --- | --- | --- | --- | --- | --- |
| Postal elections (a) | 75.07 | 75.66 | 75.51 | 75.96 | 76.48 |
| Attendance elections | 55.65 | 72.80 | 67.59 | 70.03 | 63.62 |

Figure 9: Voter turnout rates over time (% of enrolled voters who cast a vote)

(a) 2008 and 2012 figure exclude Melbourne City Council leadership team.

## Communication campaigns

The VEC provided each council with a comprehensive communication campaign developed to meet legislative requirements and increase voter awareness and participation in the elections. The VEC’s Communication Team coordinated the development and placement of advertising, development and distribution of media releases and preparation of election information for the VEC’s website. Each council’s advertising and communication campaign comprised the following basic components:

- council-specific statutory press advertisements;

- State-wide advertising;

- direct mail pieces;

- council-specific election information on the VEC website;

- council-specific media releases;

- communication services for voters with special needs; and

- a range of optional communication products.

### Statutory advertising

The Returning Officer is required to place four statutory notices during the conduct of a local government election:

- notice of entitlement date;

- notice of election;

- voting details; and

- declaration of results.

The content of the advertisements is guided by legislation. This has resulted in the VEC adopting an information-based rather than a motivational approach to press advertising. The large amount of content required poses a challenge to effective communication so, to increase reader attention and recall, each press advertisement was themed. Press advertisements for the Melbourne City Council General Elections were themed ‘Your Melbourne. Your Vote.’ For all other elections, the VEC used the theme ‘Your Community. Your Opportunity.’

Each statutory press advertisement (except the declaration of results advertisement) was branded with both the council logo and the VEC’s trademark ‘ribbon’, with the council logo the more prominent. In addition, notices included either the VEC’s enrolment hotline or an election specific contact phone number as well as the VEC’s web address, and (if requested by council) telephone numbers for a multi-language information and interpreting service operated through VITS Language Link.

As an optional extra, each council was offered the option of including a ‘voting reminder’ advertisement which ran in the week prior to election day. This advertisement followed the design and content of the statutory campaign.

67 councils requested that reminder advertising be included in their campaign and this resulted in 204 advertisements being placed.

This is discussed further in section 6.26.11.

As a smaller advertisement that ran after many of the election offices had closed, the declaration of results included the VEC’s web address only.

See Appendix 9 for samples of the voting details postal and attendance election advertisements.

### Advertisement placement

More than 1,110 statutory advertisements (including reminder advertising) were placed for the 78 local government elections. Councils nominated which newspapers largely circulating in their area they wanted to carry their advertising. The majority were booked in the ‘early general news’ (EGN) section of suburban newspapers as display ads, however, some councils also requested line advertisements in the public notices sections of other newspapers (often The Age or Herald Sun). Stonnington City Council requested options that included full display advertisements in The Age, Herald Sun, The Australian, the local press and in eight CALD publications, resulting in the largest campaign of any council.

It is important to note that neither the VEC, nor the Victorian Government’s Master Agency Media Services (MAMS) provider, is able to dictate or determine placement on any given page within the EGN section.

Another key factor affecting the rollout of statutory advertisements was the fact that the Victorian Government’s MAMS contract for functional advertising was won by Zenith Optimedia in early September 2012. Prior to this the contract had been held by Mitchell and Partners.

Although the booking schedule and associated core staff were transferred to the new provider, the booking process changed. This change was implemented as smoothly as possible and the new supplier was extremely sensitive to the VEC’s needs during such a critical period. However, the change in the booking process meant that several advertisements required resizing much later than under the original procedure and a number of deadlines became extremely short. No advertisement publication was affected as a result of these changes.

### Monitoring of advertisements

Statutory press advertisements must appear within nominated periods as defined in the LG Act. In a number of municipalities it was necessary to use smaller regional and rural publications with the consequence that in some cases it was difficult for the VEC to confirm within the available timeframe that publication of advertisements had occurred.

To help ensure advertisements appeared in accordance with the statutory timelines, the VEC undertook a number of measures including:

- booking advertisements to appear within a timeframe that allowed for publication still within legislated timelines if rebooking was required;

- briefing the Victorian Government’s MAMS provider on the necessity of meeting timelines, and of supplying a work plan reflecting these timelines well in advance of publication dates;

- requiring Returning Officers to make regular checks of publications; and

- requesting that councils track the publication of statutory advertisements and advise the VEC immediately of any errors with placement or non-appearance of advertisements.

It should be noted that, despite the above measures, the VEC was not in a position to guarantee placement of statutory advertisements as booked. Nevertheless, despite the very high volume of advertisements over the election period, there was only one instance of non-placement of a statutory advertisement, and one incorrect placement of a non-statutory advertisement. In the first case a replacement notice was published within the legislated time frame, and in the second case, a corrected notice was published.

The VEC’s monitoring systems also detected three instances where one (non-critical) error in detail was published. In each instance a correction notice was run in the following week.

### State-wide advertising

The conduct of 78 local government elections simultaneously provided an opportunity to promote the elections as a single, major electoral event.

The State-wide campaign was structured around the two major electoral phases of enrolment (from early to mid August 2012) and voting (throughout October 2012). The campaign involved advertising in the local, regional and major daily press, culturally and linguistically diverse (CALD) press, on metropolitan, regional and CALD radio and online through search engine marketing and targeted Facebook ads.

Total expenditure for the State-wide campaign was $311,937.90 ex. GST (less than 8 cents per voter) which was $91,164.79 under what the VEC had quoted to councils. This compares with $327,737.67 (around 8.2 cents per voter) at the 2008 local government elections and $2,793,083 State-wide advertising expenditure for the 2010 State Election. The VEC aimed to reduce the costs passed on to each council without compromising on the breadth of the campaign. Wherever possible, fewer, more prominent ads were placed. For example, radio advertising was booked only for breakfast and drive timeslots, the times which ratings demonstrate have the highest audiences.

Councils were invoiced on a cost per elector basis with invoicing differences being based on municipality type (metropolitan or regional) and the associated needs. Metropolitan councils paid for updates to the 20 Victorian Interpreting & Translating Service (VITS) Language Link telephone recordings on a cost per elector basis (see section 6.26.9). However, the VEC funded the CALD media release campaign and the production and distribution of commercial radio audio grabs and translated copy on the VEC website.

All State-wide press advertising included a telephone enquiry number (enrolment hotline, election office direct line or other specific service line) that was relevant to the particular phase of the election. The VEC’s web address, Facebook address and Twitter handle were also included in these advertisements. Telephone numbers for the multi-language information and interpreting service operated through VITS Language Link were included on advertisements where appropriate.

See Appendix 8 for samples of the State-wide campaign press advertisements.

### Direct mail pieces

#### Voter notice - EasyVote letters

Returning Officers are required to provide all eligible voters with a voter notice for attendance local government elections. To meet the requirements of Regulation 43 of the LGR, the VEC developed a voter notice, or EasyVote letter.

Each voter (except General Postal Voters) received a personally addressed EasyVote letter that contained their entitlement address, a map of their ward, details of where to vote, postal and early voting arrangements, election enquiry telephone numbers, telephone numbers for the VITS Language Link service and a one sentence translation in up to six languages selected by each council.

In 2008, the EasyVote letter was produced as a black and white direct mail piece and this cost-effective method was repeated in 2012. Over 691,647 EasyVote letters were mailed for the 2012 local government elections at a cost per elector of approximately $0.55 cents (including postage).

See Appendix 7 for a sample EasyVote letter.

Uncontested election leaflets

The VEC presented the uncontested election leaflet as a necessary product to all subdivided councils for the local government elections in 2012, where one or more ward was uncontested.

Nearly 94,873 uncontested election leaflets were mailed for 27 uncontested elections at a cost per voter of approximately $0.70 (including postage).

See Appendix 10 for a sample uncontested leaflet.

### Social media campaign

Using paid promotion on Facebook, the VEC targeted voters by geographic area and topics of interest. This Facebook promotion targeted searchers in areas with a history of lower participation, and was also triggered by topic searches that it is believed may be of interest to people whose details, may not be up to date on the roll or who may be less likely to participate. For example, searches related to renting, landlords and university may suggest that users have moved address and might not have updated their enrolment details.

This paid advertising was supported by a defined timeline of social media posts on Facebook and Twitter designed to cover each of the key messages of the communication campaign, and to seed conversation about the democratic process.

By November 2012, the VEC’s Facebook following had reached more than 2,900 and the Twitter feed was followed by more than 1,100. In addition, a total of 2,053 posters used the VEC’s seeded “#...votes” tags 5,004 times during the election period.

A review of the user data available for this period through Facebook’s analysis systems indicated increases in follower numbers from the target demographics such as young people (particularly young males) and spikes were evident in the target geographic areas.

### VEC website

The internet is a major information source for voters, candidates and media during major elections. During the council election period, the VEC’s website is a combination of municipality-specific pages and pages with information of a general nature relating to all councils.

For each council, the municipality-specific pages provided information including:

- the electoral structure of the municipality;

- how to enrol or update your details;

- how to vote;

- how to nominate;

- information on who had registered a how-to-vote card (attendance elections);

- candidates’ details, including the candidates’ statements (for postal elections) and indications of preferences; and

- election results.

The pages with general information included those providing:

- information about services available for people with disabilities, including audio files for those who are blind or have low vision and a video in Auslan for people who are deaf or hearing-impaired;

- translated audio files for those voters who were not literate in their own language;

- a translated enrolment form for non-English speakers;

- information for candidates;

- a facility for people to check their enrolment details on the State electoral roll;

- an online candidate helper which candidates could use to fill out their nomination form and provide other information relating to their candidacy;

- a facility for people wishing to work in election offices to register their interest;

- election information in 20 languages other than English and in Easy English;

- media releases, media advisories and a media information kit;

- a list of all candidates across all municipalities; and

- advice for people who were interstate or overseas.

During the period of the communication campaign (1 August to 31 October 2012) the VEC’s website had 544,384 visits, with 328,787 unique visitors and required more than 719 updates. A total of 73.18% of users used a computer to access the website and, interestingly, 25.91% used a mobile platform such as a smartphone or tablet over that period.

Eight of the 25 most frequently accessed pages from 1 August to 31 October 2012 were results pages, with Moreland, Glen Eira, Melbourne and Geelong City councils’ results pages being those with the highest number of discrete visitors.

The single most-viewed page between 1 August and 31 October 2012 was the general information page on council elections (58,312 unique visitors). This page was specially created for the elections and most viewers perused it for around one minute.

In 2012, the VEC’s website also provided an application that directed the user to the relevant council election page when an address was provided.

It is difficult to extrapolate the number of downloads of forms from the number of pageviews. However, during the campaign period, the AEC enrolment form was the most frequently viewed item (12,438 unique pageviews). The overseas notification form (in PDF and Word format) was the second most frequently viewed item (4,376 unique pageviews) followed by the General Postal Vote form (1,936), which many people appeared to have confused with the postal vote application form for attendance elections, nomination forms (1,525) and the Candidate Handbook Postal (1,064).

A total of 3,582 emails were received via info@vec website between 6 August and 9 November 2012, with 2,921 of these received between 11 October and 9 November 2012. This compares to 1,265 for the 2008 local government elections and 1,913 for the 2010 State Election. The turnaround time on responses for the majority of emails was within 24 hours, with most responses to emails being made within 12 hours of receipt.

### Media relations

Media releases formed an important part of the communication campaign, assisting journalists by providing factual information for election reporting.

To help nurture a good working relationship with key media representatives, the VEC conducted two media briefing sessions — one for major metropolitan media outlets about the Melbourne City Council Elections and the other for both metropolitan and regional media outlets about local government elections in general. Journalists from The Age, Herald Sun, Fairfax Community Newspapers, Leader Newspapers and ABC Radio attended along with communication staff from a number of councils. A detailed Media Information Kit was supplied and was emailed to journalists who were unable to attend the briefing.

The communications campaign also involved the production of six council-specific media releases for each of the 78 councils holding elections in 2012, and the distribution of these releases to a council-specific media contacts list. In addition, corresponding State-wide media releases (six media releases and five media advisories) containing general information, were distributed to the major metropolitan daily newspapers, commercial radio and television broadcasters. Over 1,500 elections-related newspaper articles were published across the State from late August to early November 2012.

MP3 radio audio grabs, featuring either the Acting Electoral Commissioner or the VEC’s Manager of Election Services were recorded and distributed with a corresponding media release in the immediate lead up to important deadlines. The radio media campaign generated more than 150 news items between late August and the last week of elections (late October) in 2012.

Returning Officers and communication staff at the VEC responded to media enquiries and interview requests throughout the election period. Media interest peaked during the nomination period and over the election weekend, with enquiries seeking clarification about candidate nomination, election timelines and election results.

See Appendix 8 for examples of State-wide coverage. All non-council-specific media releases were published on the VEC website at vec.vic.gov.au/about/VEC-media-council.html.

### Communication services for voters with special needs

Along with providing ballot packs in large print and Braille, the VEC worked with Vision Australia to provide information about the local government elections for blind and low vision voters. Two specific communication pieces went to those on the Vision Australia and Blind Citizens Australia mailing lists. Downloadable large-print and MP3 audio files were available on the VEC website, there was onsite access to assisted reading equipment at Vision Australia centres, and the promotion of the elections on Vision Australia Radio throughout Victoria.

The VITS Language Link telephone interpreting and multi-language information service operated throughout the election period. All State-wide press advertising included interpreting service telephone numbers, as did the statutory and reminder press advertisements for those councils that had requested them. For the period 19 September to Friday, 26 October 2012, a total of 4,695 calls were made to the VITS Language Link service. Of these, 2,847 callers obtained the information required from the pre-recorded message in their language while 1,848 required the assistance of an interpreter.

| Election year | August | September VITS calls | October VITS calls | November VITS calls | Total |
| --- | --- | --- | --- | --- | --- |
| 2012 – local government elections | 117 | 65 | 4,692 | N/A* | 4,874 |
| 2008 - local government elections | N/A* | 191 | 191 | 7,859 | 8,241 |
| 2005 - local government elections (54 councils) | N/A* | 96 | 67 | 5,549 | 5,712 |

Figure 10: Number of calls to VITS during election period in 2005-2012

*Election moved forward by one month due to change in legislation.

The VEC engaged ethnic media specialists to translate two media releases for distribution to 69 ethnic publications in 17 languages (Amharic, Arabic, Bosnian, Cambodian, Chinese, Croatian, Dari, Greek, Italian, Korean, Macedonian, Persian, Russian, Serbian, Spanish, Turkish and Vietnamese).

The languages selected were those recommended by LEBA Ethnic Media and the Victorian Multicultural Commission on the basis of 2006 Census data, the growth trends of new and emerging communities, and the availability, distribution and suitability of ethnic media publications.

The releases were distributed to almost 100 ethnic publications. More than 170 articles were published in response to the media releases, with more than $75,000 worth media space secured.

Information on enrolment and voting at the local government elections in 2012 was also available to download in 20 languages on the VEC website (Amharic, Arabic, Bosnian, Cambodian, Cantonese, Croatian, Dari, Dinka, Greek, Italian, Korean, Macedonian, Mandarin, Persian, Russian, Serbian, Somali, Spanish, Turkish and Vietnamese).

| Media release | Publication period | Advertising value (inc GST) |
| --- | --- | --- |
| Enrol to Vote Phase | 8–31 August 2012 | $36,014.86 |
| Voting Phase | 26 September –27 October 2012 | $40,354.35 |

Figure 11: Coverage of media releases in CALD publications

### Telephone enquiry services

Each Returning Officer provided a telephone enquiry service at their election office from Wednesday, 19 September 2012 to the close of voting. Typically calls related to voting entitlement and compulsory voting, roll queries, ballot pack despatch and non-receipt of ballot packs, overseas or interstate voters, requests for a postal vote, and inquiries about where to vote (both early and on election day). Overflow calls were answered by the VEC’s overflow call centre (located at head office) between the hours of 9.00 am and 5.00 pm. Just over 150,500 calls were received altogether with 132,253 received at election offices around the State.

The election office telephone enquiry services were linked to the VEC’s overflow call centre, which also answered calls to the VEC’s 131 832 telephone number. Over 43,800 calls were answered at the VEC’s overflow call centre between Wednesday, 19 September and Friday, 3 November 2012. Over 18,000 of these calls were directly related to a specific council.

Appendix 11 contains a table of the number of enquiry calls received during the election period at election offices and by the overflow centre. Over 20% of calls related to attendance elections and, even though these comprised only 10% of elections, this represents 18.6% of the total number of electors across all elections (see Figure 12: Enquiry calls received, 2012 local government elections).

Figure 12: Enquiry calls received, 2012 local government elections

### Optional communication products

To complement communication campaigns, the VEC offered councils the following two optional communication products.

#### Multi-language voting instructions

The VEC provided an option to councils to make multi-language voting instructions available to their voters. Due to the high volume and tight production timelines involved, a ‘one-size-fits-all’ product was developed for the local government elections in 2012.

To meet council community language requirements as effectively as possible, the VEC selected languages on the basis of the results of surveys of council requirements, cross-referenced with ABS data and recommendations made by the Victorian Multicultural Commission.

For postal elections, the VEC produced step-by-step leaflet containing voting instructions in 24 languages (Amharic, Arabic, Bosnian, Cambodian, Chinese traditional script, Chinese simplified script, Croatian, Dari, Dinka, Greek, Italian, Korean, Macedonian, Persian, Russian, Serbian, Somali, Spanish, Turkish and Vietnamese). One sentence translations, directing people to the VITS Language Link telephone number, were included for languages that could not be accommodated in the leaflet (Filipino, Hindi, Hungarian, Indonesian, Nuer, Portuguese, Romanian, Sinhalese and Tamil).

The leaflet also contained step-by-step illustrations and VITS Language Link telephone numbers to enable non-English speaking voters to speak with a member of the VEC staff via an interpreter.

28 councils (excluding Melbourne City Council) selected this product in 2012, reaching over 2.06 million voters via ballot packs, at a cost of 4.7 cents per elector. Melbourne City Council’s multi-language voting instructions were published in the Councillor and Leadership Team booklets in the six languages requested by the Council (Arabic, Mandarin, Cantonese, Hindi, Italian and Korean).

For attendance elections, the VEC produced two-step ‘how to vote’ instructions in 20 languages (Albanian, Arabic, Bosnian, Chinese traditional script, Chinese simplified script, Croatian, Dari, Dinka, Greek, Italian, Khmer, Macedonian, Maltese, Polish, Russian, Serbian, Somali, Spanish, Turkish and Vietnamese).

The attendance election voting instructions were printed on the inner facing panel of each voting compartment.

#### Non-statutory advertising

On request by individual councils, the VEC placed (additional) non-statutory advertisements during the election period.

A total of 67 councils requested that a voting reminder advertisement be published during the final two weeks before election day (204 placements). Two councils also requested that their voting reminder notices be published twice and one council requested additional radio advertising to coincide with the voting reminder press advertising.

### Additional products and services

Along with the information booklet series detailed in section 6.26.13, the VEC provided a number of additional products and services to complement the communication campaigns, which were not costed back to councils.

#### Information DVD: Auslan

The VEC produced an updated Auslan DVD for the local government elections in 2012. Signed by an Auslan interpreter and with optional subtitles, the DVD contained information explaining voting and enrolling entitlements, nomination procedures and voting procedures. This resource was promoted primarily through VicDeaf (2,100 copies) and via online and print newsletters, word-of-mouth and disability networks.

Available free of charge by contacting the Victorian Electoral Commission or Vic Deaf, the DVD could also be viewed on the VEC website.

#### Information DVD: Proportional Representation

Changes to a number of council structures following the conduct of Electoral Representation Reviews meant that some councils would experience the proportional representation counting system for the first time at these elections.

In order to assist candidates, council staff and other interested parties to understand the principles and application of proportional representation, the VEC developed a 10 minute DVD illustrating how this vote-counting system works.  The DVD was made available to all candidates and disks were mailed to interested parties on request. The content of the DVD was also available on the VEC website.

#### Braille and large print ballot packs

The VEC ran an opt-in service for blind and low vision voters wishing to receive Braille or large-print ballot papers. This service was promoted through direct mail (via email, Braille and CD) via the Vision Australia and Blind Citizens Australia client databases, and on radio 3AW and Vision Australia Radio.

#### Easy English information booklets

Election information was produced in Easy English with assistance from Scope Victoria for people with low English literacy, and learning and cognitive disabilities. The VEC distributed around 3,000 community information kits, which contained either the postal or attendance booklets with other collateral to community information centres and migrant resource centres.

#### Election information packs

Election specific information packs were sent to more than 800 community and government organisations across Victoria, including Indigenous groups, migrant resource centres, CALD community groups, aged care providers, community legal centres, community information centres, youth organisations and disability groups. Election specific resource packs were also sent to all 128 Victorian Members of Parliament and all councils.

#### The Age Education Supplement

The VEC sponsored the production of The Age Education Supplement ‘Make a Difference in Your Community’, which was distributed with The Age on Monday, 20 August 2012 to an overall readership of 670,000. The supplement specifically aimed to engage young people in the local government elections, reached 95% of all Victorian schools with 25,000 teachers sent copies directly. In addition, a teacher’s guide ‘Make a Difference in Your Community’ was made available to download for teachers to use within the classroom.

#### Information, enrolment and voting sessions

In the three-months prior to election day, enrolment information and voter education sessions were delivered to groups traditionally under-represented in voter turnout, including CALD community members, young people and people experiencing homelessness. Six sessions were provided to disability groups and five sessions to CALD groups.

### Election information booklet series

The VEC updated its series of information booklets to provide candidates, media and other interested parties with easily accessible election information from the VEC website or in hard copy. Copies of these booklets are included on the CD that accompanies this report.

The booklets in the series were:

- Structural Overview and Key Dates

Provides information on all of Victoria’s 79 councils, their structure, the number of councillors to be elected and if the election was scheduled to be conducted by postal or attendance voting. The booklet also included a summary of changes to legislation and election timelines and notes the status of the re-scheduled Brimbank City Council General Election.

- Municipal Voters Roll – Information for Councils

Includes an overview of voting entitlements and procedures for the production of the municipal voters’ roll.

- Municipal Electoral Tribunals and Case Studies

Explains the Municipal Electoral Tribunal process and provides case studies from inquiries conducted by the Municipal Electoral Tribunal following the local government elections in 2008.

- Electoral Advertising and Campaign Material

Covers legal responsibilities for candidates in relation to the preparation and publication of electoral advertising and campaign material.

- Counting Arrangements

Includes a description of the processes between the close of voting and the declaration of the election and estimated timetables for attendance, postal and Melbourne City Council counts.

- Costing Local Government Elections

Explains the VEC’s method of costing for local government elections and the procurement process followed by the VEC and councils.

- Ballot Paper Tracking – Postal Elections

Explains and illustrates the ballot paper reconciliation processes implemented by Returning Officers at postal elections.

- Ballot Paper Tracking – Attendance Elections

Explains and illustrates the ballot paper reconciliation processes implemented by Returning Officers at attendance elections.

The VEC expects to publish further booklets in this series to provide some analysis and evaluation of aspects of the local government elections in 2012. Any additional publications will be available from the VEC’s website or by contacting the VEC.

## Compulsory voting enforcement

Councils are obliged to enforce the compulsory voting provisions of the LG Act. Councils may choose to contract the enforcement of compulsory voting to the VEC. After the local government elections in 2012, 73 councils contracted the VEC to conduct compulsory voting enforcement on their behalf.

### Appointment of Prosecution Officer

Prior to the commencement of compulsory voting enforcement by the VEC the Chief Executive Officer under section 40(2)(a) of the LG Act is required to appoint a VEC staff member as a Prosecution Officer for the purpose of section 40 of the LG Act. All councils fulfilled this requirement prior to the commencement of the enforcement process.

### Provision of list of non-voters

The VEC prepared for all councils, regardless of whether the VEC was appointed to conduct compulsory voting enforcement, a list of persons who were required to vote at the elections but who appeared not to have voted. The list was forwarded to those councils that had not appointed the VEC for compulsory voting enforcement. For all other councils the list was provided to the prosecution officer.

### Enforcement Process

Compulsory voting enforcement is conducted in three stages. Where the VEC has been contracted to do this work on the council’s behalf, all three stages of non-voter follow up will be undertaken. The VEC believes that, in fairness to all apparent non-voters, it is important to complete the entire process. A standardised non-voter follow-up service has been provided to all councils. The Prosecution Officer has established a list of reasons for failing to vote that will be deemed to be acceptable excuses across all councils in addition to the excuses prescribed in Regulation 116(2) of the LGR.

Stage one of the non-voter process is a requirement of the LG Act and the remaining stages are pursuant to the provisions of the Infringements Act 2006.

Stage one is a mandatory requirement. An Apparent Failure to Vote Notice is sent to each voter who appeared to have failed to vote. No penalties are collected against this notice.

Preparations for the mail-out of the Apparent Failure to Vote notices commenced in late November 2012 and involved scanning 1,677 marked rolls for eight attendance elections to capture voters who voted at an early or election day voting centre. Six staff members were responsible for the scanning and reconciliation of the marked rolls over a two week period.

Additionally, up to 50 staff were appointed to process ballot material returned after close of voting, return to sender ballot material and voter information reports containing details of voters unable to vote at an election and excuses recorded by telephone overflow service. A total of 8,039 staff hours were required to undertake this task.

Due to the large number of Apparent Failure to Vote Notices to be despatched (505,582), the mail out was staggered over eight dates commencing Tuesday, 15 January 2013, with the last mail out occurring on Friday, 8 February 2013.

The VEC appointed approximately 115 staff to process responses to Apparent Failure to Vote Notices with a maximum of 102 staff working on any one day. All responses to the notice were sorted to the relevant council prior to processing through the Election Management System. A total of 21,072 staff hours were required to undertake this task.

Stage two of the process, the despatch of 333,143 Infringement Notices commenced on Tuesday, 5 March with the first of seven mail outs. The final despatch took place on Wednesday, 3 April. The penalty amount against this notice is currently set at $70 and to date $4,246,640 has been collected in penalties across all councils. The Infringement Notice stage is due to be completed by early May.

The Penalty Reminder Notice stage of the process for all councils will take place during May. The Penalty Reminder stage of enforcement incurs the original penalty amount plus costs. The completion date for this notice is anticipated to be early July. At the conclusion of the compulsory voting process, all councils will be provided with a final list of non-voters. Councils proposing to lodge outstanding infringements with the Infringement Court must do so within six months of the issuing of the Infringement Notice.

All materials relating to compulsory voting enforcement will be returned to councils for storage in accordance with Regulation 114 of the LGR.

### Issue in Greater Bendigo City Council

Following the mail out of Apparent Failure to Vote Notices to apparent non-voters for Greater Bendigo City Council, the VEC identified an omission in the process of marking voters off the roll at the election office. The omission meant that some voters had returned their ballot material but were not marked off the roll and, as a consequence, these voters were issued with an Apparent Failure to Vote Notice in error.

The VEC retrieved the election records and was able to review the declaration flaps that had been set aside from the ballot paper envelope during the extraction and counting operations. The declarations were checked against the list of non-voters and any voter who had returned their ballot material was removed from the non-voter list and any further enforcement action. Following these checks, the Prosecution Officer also wrote to the affected voters to confirm that their ballot material had been received and included in the counting process and that no further action was necessary in relation to the Apparent Failure to Vote Notice.

## Complaints

Complaints in relation to local government elections generally fall into two categories. The first category consists of complaints relating to the LG Act that are more appropriately dealt with by the LGICI. Neither the Returning Officer nor the Electoral Commissioner has authority to investigate these matters.

The second category is comprised of complaints relating to the administration of the election, to which it is appropriate that the VEC respond on behalf of the Returning Officer.

Prior to the local government elections in 2012, the VEC met with LGICI to develop a complaints procedure. The agreed procedure aimed at ensuring that all complaints were handled by the organisation best suited to respond, minimising double handling, reducing response times and providing LGICI with the opportunity to directly review all relevant complaints so that legislative or other solutions could be developed and recommended if appropriate.

The VEC reviewed its complaints handling and related procedures to ensure that complaints were handled as efficiently as possible. Complaint receipt, filing protocols and document templates individualised responses and cover letters prepared within the target acknowledgement time of 24 hours. For a complaint to be considered formal, it had to be received in writing. The 24 hour acknowledgement time target was met for the vast majority of the complaints received by the VEC.

### Details of complaints

A total of 325 complaints were received in relation to the local government elections in 2012, the majority between 1 October 2012 and 10 December 2012. This is an increase on the 223 complaints received in relation to the 2008 local government elections.

Just over 77% of the complaints received by the VEC were related to the application of the LG Act and were forwarded to the LGICI, with the VEC acknowledging these complaints and advising the complainant that their correspondence had been forwarded. The VEC also advised the person complained about that a complaint had been received, the nature of the complaint and where applicable, that the complaint had been referred to the LGICI.

|  | 2005* | 2008 | 2012 |
| --- | --- | --- | --- |
| Complaints referred to Local Government Victoria |  | 137 | 252 |
| Complaints concerning the administration of the election |  | 86 | 73 |
| Total complaints | 215 | 223 | 325 |

Figure 13: Number of complaints received by VEC, local government elections, 2005-2012
* 2005 – 54 councils

The majority of complaints contained allegations that a breach of the LG Act had occurred. These complaints contained allegations of lack of authorisation of electoral material (61), false or defamatory information (22), misleading or deceptive material (43) and eligibility or fitness of the candidate to stand (9).

A large number related to allegations about candidate conduct (70) whether in breach of the LG Act and/or of a criminal or civil nature. This is a significant increase on the 12 complaints received about candidate conduct at the previous local government elections in 2008.

Other complaints related to the removal or distribution of campaign material by persons unknown, the content of newspaper editorials or articles, the placement of campaign material in public places, the use of the voters list for campaigning and the security of ballot material.

Of the complaints relating to administrative aspects of the elections, the main issues raised related to the enforcement of legislated deadlines, candidate eligibility rulings, candidate statement content, how-to-vote card content, the conduct of election staff and a perceived lack of security relating to the handling of ballot material.

The division of responsibilities between the Returning Officer, the Electoral Commissioner and the LGICI in responding to complaints caused a degree of confusion for complainants. However, an explanation by phone was generally sufficient to clarify understanding.

A significant number of the complaints alleging misleading or deceptive electoral matter and false and defamatory statements were lodged by first-time candidates.

| Complaint category | 2008 | 2012 |
| --- | --- | --- |
| Eligibility or fitness to be candidate | 10 | 9 |
| Conduct of candidate | 12 | 70 |
| Improper [or lack of] authorisation of electoral material | 32 | 62 |
| False or defamatory information | 61* | 22 |
| Misleading or deceptive material | * | 43 |
| Conduct of Returning Officer or Voting Centre Manager | 6 | 1 |
| Election administration | ** | 28 |

Figure 14: Main categories of complaints received 2008, 2012 local government elections

*These categories were combined in 2008 data
** This category not used in 2008

## Applications to the Municipal Electoral Tribunal

Section 45 of the LG Act provides for a candidate or a group of at least 10 voters who dispute the validity of the election, to apply for an inquiry into the election by a Municipal Electoral Tribunal. Applications must be lodged within 14 days of the declaration of the result of an election.

Following the local government elections in 2012, five applications were lodged with the Municipal Electoral Tribunal. This is a significant reduction on the twelve applications lodged after the 2008 elections. The details of the five applications are shown in Figure 15.

| Council | Ward | Summary of grounds as provided by applicant |
| --- | --- | --- |
| Macedon Ranges Shire Council | South | Alleged errors in data entry during the original computer count Alleged lack of access for scrutineers to the counting venue and review of informal ballot papers Alleged inclusion of formal ballot papers that should have been ruled as informal Alleged mishandling of returned ballot packs by a candidate during hand-delivery to the election office |
| Manningham City Council | Mullum Mullum | Allegedly disqualified candidate remained on the ballot paper for the election and, although not elected, influenced the outcome of the election |
| Moreland City Council | North-East | Alleged fraud in the handling of postal voting applications by a candidate and their supporters Alleged bribery by a candidate to illicit votes |
| Port Phillip City Council | Albert Park | Alleged offences caused by a candidate’s how-to-vote card, including in its content and distribution |
| Swan Hill Rural City Council | Robinvale | Alleged offences against the LG Act by a candidate Alleged irregularities in the preparation of the municipal voters’ roll Alleged lack of access to the election office in Swan Hill for Robinvale voters |

Figure 15: Details of applications to the Municipal Elections Tribunal

At the time of preparing this report, the Municipal Electoral Tribunal had released decisions on three of the five inquiries:

- The applications were dismissed in the enquiries relating to Macedon Ranges Shire Council and Swan Hill Rural City Council; and

- The Municipal Electoral Tribunal found the Manningham City Council election was valid despite an allegedly disqualified candidate.

The remaining matters, regarding elections in Moreland City Council and Port Phillip City Council, were still before the Municipal Electoral Tribunal.

Following the completion of each inquiry, affected persons have a period of seven days in which to apply to VCAT for a review of a decision by the Municipal Electoral Tribunal (see section 48(2) of the LG Act).

### Referring a matter to a Municipal Electoral Tribunal

The VEC has noted that the LG Act does not currently contain a provision for the Returning Officer (or electoral service provider) to refer a matter to the Municipal Electoral Tribunal. Without the capacity to apply for a Municipal Electoral Tribunal, those responsible for conducting a local government election must rely on a candidate or a group of at least 10 voters in the election to make an application.

Recommendation 13: Applying to a Municipal Electoral Tribunal The VEC recommends that the Government considers a mechanism for a Returning Officer (or election service provider) at a local government election to refer a matter of concern in relation to that election to the Municipal Electoral Tribunal.

## Election Costs

The VEC operates a marginal cost recovery program and does not pass on costs for using resources existing from its general operations. Only costs that directly relate to delivery of a council election are considered for invoicing back to councils. This is different from other jurisdictions where local government elections are conducted by the election services provider on a full cost recovery basis. The VEC reviews its prices and rates regularly to capture inflation in its products and services and to ensure costs are maintained in line with the election service plan and each council’s service requirements.

The VEC plans to invoice councils in up to two stages:

1.	 Following the completion of election and post-election activities, except for compulsory voting enforcement (where applicable); and

2.	 As soon as possible after all costs involved with compulsory voting enforcement have been confirmed for those councils who are using this service.

Revenue from penalties paid to the VEC during the compulsory voting enforcement program are entirely remitted to the respective council. The VEC does not use the revenue to off-set invoices. A net cost is useful, however, to consider the underlying cost of conducting local government elections.

| Year | No. of councils using the VEC for the election | Total cost invoiced to councils (ex. GST) ($’000) | Number of councils using the VEC for compulsory voting enforcement | Non-voter payments ($’000) | Total net cost for Councils ($’000) |
| --- | --- | --- | --- | --- | --- |
| 2008 | 79 | 16,458 | 70 | 6,019 | 10,439 |
| 2012 | 78 | 19,192 | 73 | 2,996 | 16,169 |

Figure 16: Summary of costs invoiced to councils and compulsory voting revenue remitted to councils following the 2008 and 2012 elections

The total marginal costs incurred by the VEC for the conduct of the local government elections in 2012 was $19,192,380.38 (ex. GST), including an estimated amount to conclude compulsory voting. Marginal costs included all direct labour and associated on-costs, materials, equipment, mail processing, postage, advertising, printing, rent, utilities, insurance, computer equipment, software licences and software maintenance. Final costs will be reported in the VEC’s local government activity report for 2013/14.

From time to time the cost of elections to councils is raised in policy discussions and, in determining future local government election arrangements, the Government may wish to consider, in consultation with the sector, an appropriate costing methodology to apply in Victoria. The VEC has outlined the benefits of adopting a single service provider option earlier in this report (see Recommendation 4 in section 6.2 of this report).

# DEBRIEFING AND EVALUATION

## Debriefing

The VEC conducted a comprehensive internal and external debriefing program following the conduct of the local government elections in 2012.

Returning Officers and their staff submitted a written report including comments for consideration at future elections. Returning Officers were also invited to attend a one-day debriefing session in mid-December 2012. Five sessions were conducted, including one session specifically addressing the Melbourne City Council elections. Of the VEC’s 78 Returning Officers, 76 attended a debriefing session. One Returning Officer provided written feedback only.

VEC managers and team leaders conducted debriefing sessions with VEC project staff who had worked on the elections and individual debriefing sessions were conducted with the VEC’s service providers. Councils were also invited to provide written feedback to the VEC, and 56 councils did so.

A consolidated report listing all the matters raised through the debriefing activities has been prepared to assist and inform the VEC when planning for future local government elections.

## Evaluation surveys

In November 2012, the VEC invited feedback on aspects of the conduct of the local government elections in 2012 directly from voters, candidates, and election officials using an online survey tool.

The feedback provided by election officials will be used to improve arrangements for the VEC’s future election activity, including State and local government elections. The information obtained from voters and candidates through the online surveys is summarised in this report.

### Voters

The voter survey comprised 34 predominantly non-compulsory questions. It was advertised in the major daily newspapers and on the VEC website and there were 592 respondents. There was almost an even split of gender with 48% female and 52% male respondents, and 97% of respondents reported speaking mainly English at home. Of the 81% who provided age data, 80% were aged 40 years or over. See Figure 17 for the breakdown by age group of these respondents.

Figure 17: Voter survey, proportion of respondents by age range

A total of 93.6% of survey respondents stated that they had voted in the council elections, and only one of these declined to comment on why they voted. Almost 320 said it was important to vote and that they cared about the services in their local community. Not wanting to get a fine motivated 137 respondents to vote. Of those who selected ‘other’ reasons for voting, there was a mix of people complaining about compulsory voting and an equal number who commented about the removal of existing councillors. The importance of democracy and the civic right and responsibility to vote were also noted.

Figure 18: Voter survey, reasons for voting (multiple selections allowed)

Of the 35 respondents who expanded on why they didn’t vote, 34% said they didn’t receive a ballot pack, with other reasons including incorrectly assuming that voting in person (attendance voting) was available, not enough information about candidates and living in an uncontested ward.

Most of the survey respondents came from metropolitan councils, with the largest individual numbers of respondents being from attendance election councils.

Of the total of metropolitan 498 voters who responded, 36% were from attendance election councils. Of those who responded to the question about voting entitlements in other municipalities, 82% had none, 11% had other entitlements and voted in those elections, and 7% had them but didn’t vote in any other election.

Respondents who voted in an attendance election were asked to indicate what method they had used to vote. Some 38% voted at an early voting centre, 13% voted by post and 48% voted at a voting centre on election day. This accords with the increasing trend towards early or pre-poll voting that has been observed at many Victorian, Australian and interstate elections.

Figure 19: Voter survey, voting method of those who voted in attendance elections

Over 95% of respondents expressed awareness of the 2012 council elections. Of those, awareness primarily came from suburban newspapers (54.1%) and major daily (32%) newspapers and direct mail from the VEC 34.4% and candidates (48.1%). Just over 9% of respondents registered social media as a source of awareness of the elections (see Figure 20). Nearly 18% of respondents chose ‘other’ with the majority of these stating that they became aware of the elections because they worked in local government or were politically active (e.g. member of a party, candidate).

Figure 20: Voter survey, sources of awareness about elections

Almost 63% of respondents who had been aware of the elections reported seeing or hearing VEC advertising. Suburban newspaper advertising and the VEC’s direct mail were rated as the most helpful advertising people saw, followed by the metropolitan newspaper advertisements (see Figure 21).

Figure 21: Voter survey, helpfulness of advertising methods

Commentary stated overwhelmingly that there was not enough information provided about candidates for both postal and attendance elections. Respondents reported that candidate statements provided in ballot packs for postal elections were too short and rudimentary to be helpful. There was also a strong call to include political affiliations with the candidate statements. Only 56% of survey participants responded to the question about overall satisfaction with advertising. Of these, 51% were satisfied or extremely satisfied, 17% were neutral and 27% were either dissatisfied or extremely dissatisfied.

In relation to attendance voting experience, the overall level of satisfaction of the 165 respondents with the experience had an average score of 3.26 out of 5. The experience components with the highest degree of satisfaction related to the helpfulness and efficiency of staff, and the lowest level of voter satisfaction expressed was with the accessibility of the voting centre (see Figure 22).

Figure 22: Voter survey, overall satisfaction with attendance voting experience

The 24 respondents who voted in attendance areas and applied for a postal vote were most satisfied with the clarity of the instructions on the ballot pack and least satisfied with the time taken for the ballot pack to arrive. Almost 46% of respondents received the pack within 1-3 days, 33% received it within 4-7 days, 17% reported that it was more than 7 days before the pack arrived, and one respondent reported that they did not receive a ballot pack.

Figure 23: Voter survey, time taken for postal ballot pack to arrive (attendance elections)

Almost 90% of respondents who voted in postal elections, provided a response relating to the delivery of their ballot pack. Almost 73% of these respondents received their ballot pack at least two weeks before the close of voting. A further 19% said they received it a week prior to the close of voting, almost 6% said it arrived less than a week prior to the close of voting and almost 3% said that they had to go and vote at the election office as their ballot pack hadn’t arrived by 26 October.

In terms of satisfaction with the content of the ballot pack, respondents were most satisfied with the voting instructions and least satisfied with the candidate statements – reflecting the narrative responses in which respondents expressed great dissatisfaction with the general lack of information about candidates.

Almost 20% (99) of respondents contacted the VEC by telephone over the election period and average rating for pleasantness of staff of 5.4 out of 7 and rated the staff member’s knowledge of the subject at 4.85 out of 7. The overall rating of the telephone experience was 4.63 out of 7. Some 77% of callers waited 1-3 minutes to have their call answered, 13% waited 4-6 minutes, 2% waited 7-10 minutes, 5% waited more than 10 minutes and 3 respondents said they couldn’t get through at all.

Just over 6% (33) of respondents contacted the VEC by email during the election period. People who contacted the VEC by email were most satisfied with the quick response to their enquiry and the staff member’s level of knowledge and least satisfied with the helpfulness of the response. Over 36% received a response within the same working day, 15% said they received it the next working day and 27% said it took 2-3 working days and 6 respondents said that they received no response. The VEC’s system indicates that all emails were answered and the longest would have been 2-3 days including weekend days.

Over 50% of survey respondents visited the VEC’s website during the election period. Web visitors were most satisfied with the council election finder application and the council election results finder. The overall weighted average satisfaction with the website was 4.43 out of 7.

Figure 24: Voter satisfaction with information on VEC website

Almost 80% of 514 respondents didn’t know that the VEC had a Facebook page. Of those who were aware, just fewer than 7% (35) visited it. This could possibly be attributed to the age demographic of the respondents. The average satisfaction level with the information provided on the VEC facebook page was 4.91 out of 7.

Almost 78% of respondents were not Twitter users – a further 15% use Twitter but were not aware of the VEC’s Twitter handle (name). Some 8% (40) of respondents either followed the VEC’s Twitter feed or saw the VEC’s posts. There was positive feedback on the quality of the VEC’s Twitter feed from those who followed it.

Only 46 survey participants responded when asked for suggestions about how elections could be communicated in future. The majority suggested that email would be superior to direct mail. TV and radio advertising was also suggested.

### Candidates

The VEC invited candidates who stood in the 2012 council elections, and who provided an email address to rate their satisfaction with a range of elements of the 2012 council elections using an online survey. A total of 353 candidates responded to the survey with 92% completing the questionnaire. This figure comprises 17.6% of the total number of candidates who nominated. Just over 86% of respondents stood for election in postal elections and 14% stood in attendance elections.

Summary

There was a reasonable spread of responses from both metropolitan and regional/rural councils, although the higher individual numbers tended to be from metropolitan councils with those represented averaging around 2-3% of respondents. Casey City Council was the most well represented council with 16 respondents.

Almost all respondents (98%) said that they obtained a copy of the Candidate Handbook, which provided information on all aspects of nominating, candidate statements, HTVCs, authorisation and complaints processes, scrutineers and vote counting timelines (see Figure 25) Almost half of the respondents (45%) obtained the Handbook when they nominated, 35% collected it from a candidate information session, 30% downloaded it from the VEC’s website and 7% collected it from the VEC. Some 96% of respondents considered that the Handbook was available at the appropriate time. The remainder indicated it would be better much earlier – say six months prior to the election.

Respondents were most satisfied with the information on nomination procedures – with the average satisfaction rating of 4.2 out of a possible 5, followed closely by information on how-to-vote card registrations (4.1) and candidate statements (4.0). They were least satisfied with information on the counting of votes (3.87) – however, this may still be viewed as a very healthy average satisfaction rating.

Figure 25: Candidate survey, satisfaction with the information provided in the Candidate Handbook

If the respondents required further information about the election, 96% sought it from the Returning Officer, 8% from the VEC head office and 5% from council. Some 91% felt that they received this information within an acceptable timeframe.

In terms of the candidate information sessions, 58% (191) of respondents indicated that they had attended a candidate information session conducted by a Returning Officer, 26% attended a council run session, 25% attended a computer count information session, 19% attended an MAV information session and 11% attended a VLG Act session. A total of 29% said that they did not attend any information session.

Figure 26: Candidate survey, information sessions attended (multiple selections allowed)

Of those who had attended an information session with a Returning Officer, the highest average satisfaction levels (out of a possible 5) recorded related to the venue (4.19), followed by the time of day (4.15), opportunities to seek clarification or further information (4.14), the relevance and usefulness of the session (4.03), length of the session (4.01), handouts and slides (3.96) and presentation style (3.90).

When asked for suggestions for improvement of the Returning Officer’s information session, almost half of the respondents indicated the sessions were good and did not require any change. The remainder included suggestions relating to advertising of sessions, presentation style and knowledge of the presenter and venue.

The reasons for not attending an information session predominantly included having enough information in the candidate handbook or having previously been a councillor and knowing what to do already. Other than that, workloads and timing prevented some candidates from being able to attend. Several indicated that they either didn’t know there were information sessions or that the information sessions had concluded by the time they decided to run.

When asked what other information could be provided to candidates, the majority of responses indicated that the information currently provided was adequate and of high quality. The key themes of those who felt further information could be provided related to more information on preferences – how they work, and a significant number of respondents felt that more information on the expectations and time commitments of councillors once elected would be useful. This last suggestion is probably one for the MAV or councils to consider.

The VEC provided an online Candidate Helper, through which candidates could nominate and provide statements and an indication of preferences. Some 73% of the 335 respondents who addressed this question used the Candidate Helper. When asked about their satisfaction with the three key elements, respondents gave an average rating of 4.32 out of a possible 5 for the nomination procedure, 4.24 for the candidate statements and 4.09 for the indication of preferences. When queried as to how the Candidate Helper might be improved, suggestions included removing the need to visit the election office to complete the nomination, the ability to upload a photo online, making it easier to find and available earlier on the VEC website, and reviewing the candidate statement section so that more detail can be provided, checked and word count notified.

Figure 27: Candidate survey, satisfaction with online candidate helper

Candidate bulletins were provided to candidates, with 92% of respondents reporting having received these by email, 3% by mail and 2% in person. Some 4% of respondents said they did not receive any candidate bulletins. When asked to rate their satisfaction with the candidate bulletins, the highest average rating related to the ease of receiving the bulletin with 77.6% of respondents rating their satisfaction as 4 or 5 out of 5, followed by the usefulness of the information (63.4%), the content (61.4%) and the number of bulletins received (60.7%). Around half of those who commented (53) thought the bulletins were ‘good’ and ‘helpful’. Suggestions for improvements included having more of them and providing more regular updates on the number of votes received (cumulative total).

When asked to rate their satisfaction with their interaction with election officials, the highest satisfaction level was with the helpfulness of election officials – with 86.7% of respondents rating it 4 or 5 out of 5, followed by impartiality (86.1%), promptness (86%), professionalism (85.5%), attention to detail (82.6%), and knowledge (79.3%). The overwhelming majority of the 60 comments about election officials were that they were extremely competent and of an excellent standard. There were several comments calling the impartiality of staff or the Returning Officer into question, several suggesting the knowledge and computer literacy of staff could have been better and a couple of comments related to inconsistencies in the application of rules and processes.

Figure 28: Candidate survey, satisfaction with interactions with election staff

When asked how quickly the respondent received a response from election staff upon contact, almost 76% of those who contacted the staff in person got an immediate response, 55% who made contact by phone had an immediate response and a further 20% of those who made contact this way had a response within half a day, those who emailed a query generally had a response within half a day (36%) or within 1-2 days (14%). Several respondents said they didn’t receive any response.

Some 75% of respondents felt that they received enough information about the counting process and 55% stated that they had appointed a scrutineer.

Only 38% of respondents or their scrutineers attended a computer count information session. Of those who attended a session, participants were most satisfied with the ability to seek further information or clarification with an average weighted rating of 4.0 out of 5. Next they were most satisfied with the time of day (3.94), venue (3.93), relevance and usefulness of the information (3.91), length of the session (3.88), followed by presentation style and handouts that both received ratings of 3.83. Of the 18 who commented on why they did not attend, almost half said that a scrutineer attended on their behalf or that they did not have time to attend.

When rating their satisfaction with the count process and declaration of results, respondents rated their satisfaction with the scrutineer management process most highly (3.59) followed by the results declaration process (3.43) and then the count process (3.37).

Almost 1 in 3 respondents made comment on the count process and declaration of results. The major complaints were that the process was slow and tedious and there were far too many delays (or changes to times and dates of counts) and computer glitches. Many also complained about miscommunication or a complete lack of communication around the reasons for the delays. A number of respondents suggested that all candidates should be formally advised of the results – ideally by email. In some instances where they couldn’t attend they were advised that they would be notified of the result but this did not occur.

Of the respondents who saw or heard advertising for the council elections, 89% read about them in the local papers, followed by the Age (21%) and Herald Sun (14%). Radio (14%), direct mail (13%) and Facebook (9%) were other communication channels identified. Of the 50 respondents who selected ‘other’ for where they heard about the elections, many were previously councillors or heard about it via council. The overall impression of the communication campaign for the election had a weighted average score of 3.14 out of 5.

Some 75% of respondents had no involvement in the complaints handling process, whilst 19% lodged one or more complaints. Just over 7% of respondents said that they had been notified of one or more complaints being lodged about them or their activity. When asked to disregard whether the respondents was happy with the outcome of the complaint - but to instead just rate their satisfaction with the complaints handling process – those who had a complaint lodged against them were most satisfied with a weighted average score of 2.97 out of 5. Next came satisfaction with the information provided about the complaints handling process in the candidate information booklet (2.77), then acknowledgement time after lodging a complaint (2.73), interaction with complaints handling staff (2.72) and the overall impression of the complaints handling process (2.28).

A total of 44 respondents provided comments about the complaints handling process. A significant number complained that the VEC was powerless and either ignored or did nothing about the complaint. A similar proportion was unhappy with the performance or outcome of the complaint forwarded to the LGICI. Several respondents say they have still not received any response to their complaint.

When asked to rate their overall satisfaction with the conduct of the council elections, the weighted average score was 3.58 out of a possible score of 5.

Respondents were invited to provide feedback about their election experience. There was an overwhelming majority of complaints about dummy candidates running and calls for optional preferential voting to address this issue. There were also significant numbers of comments about the VEC not having the power to address issues and concerns about postal voting generally (lack of awareness, missing ballots, ballot packs not received). There were also calls to shorten the early voting period, force candidates to declare political affiliations and to decry the practice of dirty tricks tactics employed by other candidates. A small number of candidates complained that the publication of their email address on the VEC’s website resulted in them being inundated with spam emails and some candidates also suggested better communication of the elections and voting methods.

# APPENDICES

Appendix 1: Local government election timelines

POSTAL ELECTION TIMELINE

Appendix 2: Municipal voter count by ward

|  |  | State Roll data | Council Data | Certification | Amendments | Revised Total |
| --- | --- | --- | --- | --- | --- | --- |
| Municipality | Ward | EC List | N | A | P | O | T | Council List | Total | Additions | Deletions |  |
| Alpine Shire Council | Un-Subdivided | 9,089 | 2,390 |  | 19 | 26 |  | 2,435 | 11,524 |  | 2 | 11,522 |
| Ararat Rural City Council | Un-Subdivided | 8,011 | 1,068 | 2 |  |  |  | 1,070 | 9,081 |  |  | 9,081 |
| Ballarat City Council | Central | 20,237 | 2,575 |  |  | 7 |  | 2,582 | 22,819 |  | 1 | 22,818 |
|  | North | 23,123 | 1,677 | 2 |  | 2 |  | 1,681 | 24,804 |  | 1 | 24,803 |
|  | South | 22,879 | 2,222 |  |  | 2 |  | 2,224 | 25,103 | 1 |  | 25,104 |
|  | Total | 66,239 | 6,474 | 2 | 0 | 11 | 0 | 6,487 | 72,726 |  |  | 72,725 |
| Banyule City Council | Bakewell | 11,228 | 1,020 | 4 |  | 2 |  | 1,026 | 12,254 |  |  | 12,254 |
|  | Beale | 12,732 | 601 | 2 |  | 1 |  | 604 | 13,336 |  |  | 13,336 |
|  | Griffin | 12,337 | 1,218 | 3 |  | 9 |  | 1,230 | 13,567 |  |  | 13,567 |
|  | Grimshaw | 12,089 | 1,081 | 6 |  | 6 |  | 1,093 | 13,182 |  |  | 13,182 |
|  | Hawdon | 12,817 | 850 | 5 |  | 6 |  | 861 | 13,678 |  |  | 13,678 |
|  | Ibbott | 13,060 | 1,033 | 9 |  | 2 |  | 1,044 | 14,104 |  |  | 14,104 |
|  | Olympia | 11,413 | 1,732 | 5 |  | 5 |  | 1,742 | 13,155 |  |  | 13,155 |
|  | Total | 85,676 | 7,535 | 34 | 0 | 31 | 0 | 7,600 | 93,276 |  |  | 93,276 |
| Bass Coast Shire Council | Anderson | 4,537 | 1,349 | 3 |  |  |  | 1,352 | 5,889 |  |  | 5,889 |
|  | Churchill | 1,821 | 3,470 | 4 |  | 1 |  | 3,475 | 5,296 |  |  | 5,296 |
|  | Hovell | 3,825 | 1,611 | 4 |  | 1 |  | 1,616 | 5,441 |  |  | 5,441 |
|  | Leadbeater | 3,494 | 2,032 | 1 |  |  |  | 2,033 | 5,527 |  |  | 5,527 |
|  | McHaffie | 2,139 | 3,647 | 2 |  | 1 |  | 3,650 | 5,789 |  |  | 5,789 |
|  | Thompson | 2,665 | 3,860 | 1 |  |  |  | 3,861 | 6,526 |  |  | 6,526 |
|  | Townsend | 3,290 | 3,127 | 1 |  | 1 |  | 3,129 | 6,419 |  |  | 6,419 |
|  | Total | 21,771 | 19,096 | 16 | 0 | 4 | 0 | 19,116 | 40,887 |  |  | 40,887 |

| Baw Baw Shire Council | Drouin | 6,977 | 1,024 | 5 |  |  |  | 1,029 | 8,006 |  |  | 8,006 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Mount Worth | 7,284 | 616 |  |  | 1 |  | 617 | 7,901 |  |  | 7,901 |
|  | North | 6,700 | 1,159 |  |  | 2 |  | 1,161 | 7,861 |  |  | 7,861 |
|  | Warragul | 10,372 | 713 |  |  |  |  | 713 | 11,085 |  |  | 11,085 |
|  | Total | 31,333 | 3,512 | 5 | 0 | 3 | 0 | 3,520 | 34,853 |  |  | 34,853 |
| Bayside City Council | Central | 27,426 | 2,039 | 3 |  |  |  | 2,042 | 29,468 | 1 | 1 | 29,468 |
|  | Northern | 19,527 | 1,481 | 4 | 1 |  | 1 | 1,487 | 21,014 |  | 7 | 21,007 |
|  | Southern | 19,521 | 1,179 | 3 |  |  |  | 1,182 | 20,703 |  | 2 | 20,701 |
|  | Total | 66,474 | 4,699 | 10 | 1 | 0 | 1 | 4,711 | 71,185 |  |  | 71,176 |
| Benalla Rural City Council | Un-Subdivided | 10,419 | 910 | 1 |  | 5 |  | 916 | 11,335 |  |  | 11,335 |
| Boroondara City Council | Bellevue | 11,114 | 678 |  |  |  |  | 678 | 11,792 |  | 1 | 11,791 |
|  | Cotham | 11,545 | 699 |  |  |  |  | 699 | 12,244 | 1 | 1 | 12,244 |
|  | Gardiner | 10,962 | 1,182 | 1 |  |  |  | 1,183 | 12,145 |  |  | 12,145 |
|  | Glenferrie | 10,290 | 2,839 |  | 1 |  |  | 2,840 | 13,130 | 1 | 2 | 13,129 |
|  | Junction | 10,850 | 1,714 |  |  |  |  | 1,714 | 12,564 |  |  | 12,564 |
|  | Lynden | 11,395 | 821 |  |  |  |  | 821 | 12,216 |  |  | 12,216 |
|  | Maling | 11,441 | 784 | 2 |  |  |  | 786 | 12,227 |  | 1 | 12,226 |
|  | Maranoa | 11,089 | 761 | 1 |  |  |  | 762 | 11,851 |  |  | 11,851 |
|  | Solway | 11,647 | 753 | 1 |  |  |  | 754 | 12,401 |  | 1 | 12,400 |
|  | Studley | 10,925 | 1,330 |  |  |  |  | 1,330 | 12,255 |  |  | 12,255 |
|  | Total | 111,258 | 11,561 | 5 | 1 | 0 | 0 | 11,567 | 122,825 |  |  | 122,821 |
| Brimbank City Council |  |  | No Election |  |  |  |  |  |  |  |  |
| Buloke Shire Council | Lower Avoca | 1,564 | 287 |  |  |  |  | 287 | 1,851 |  |  | 1,851 |
|  | Mallee | 1,300 | 339 |  |  | 1 |  | 340 | 1,640 |  |  | 1,640 |
|  | Mount Jeffcott | 2,142 | 329 |  |  | 4 |  | 333 | 2,475 |  |  | 2,475 |
|  | Total | 5,006 | 955 | 0 | 0 | 5 | 0 | 960 | 5,966 |  |  | 5,966 |
| Campaspe Shire Council | Echuca | 9,478 | 713 | 3 |  |  |  | 716 | 10,194 |  |  | 10,194 |
|  | Kyabram-Deakin | 8,716 | 314 |  |  |  |  | 314 | 9,030 |  |  | 9,030 |
|  | Rochester | 2,990 | 252 |  |  |  |  | 252 | 3,242 |  |  | 3,242 |
|  | Waranga | 2,524 | 544 |  |  |  |  | 544 | 3,068 |  |  | 3,068 |
|  | Western | 2,980 | 306 |  |  |  |  | 306 | 3,286 |  |  | 3,286 |
|  | Total | 26,688 | 2,129 | 3 | 0 | 0 | 0 | 2,132 | 28,820 |  |  | 28,820 |
| Cardinia Shire Council | Central | 19,713 | 5,429 |  |  | 2 |  | 5,431 | 25,144 | 1 |  | 25,145 |
|  | Port | 10,474 | 846 |  |  | 5 |  | 851 | 11,325 |  |  | 11,325 |
|  | Ranges | 18,099 | 1,809 |  |  |  |  | 1,809 | 19,908 | 1 |  | 19,909 |
|  | Total | 48,286 | 8,084 | 0 | 0 | 7 | 0 | 8,091 | 56,377 |  |  | 56,379 |
| Casey City Council | Balla Balla | 13,020 | 1,451 | 2 |  |  |  | 1,453 | 14,473 | 123 |  | 14,596 |
|  | Edrington | 28,606 | 2,215 |  |  |  |  | 2,215 | 30,821 | 2 |  | 30,823 |
|  | Four Oaks | 31,275 | 1,448 | 3 |  |  |  | 1,451 | 32,726 | 1 | 1 | 32,726 |
|  | Mayfield | 27,278 | 3,155 |  |  |  |  | 3,155 | 30,433 | 1 | 122 | 30,312 |
|  | River Gum | 29,433 | 3,016 | 12 |  |  |  | 3,028 | 32,461 | 1 |  | 32,462 |
|  | Springfield | 26,520 | 2,076 | 3 |  |  |  | 2,079 | 28,599 | 2 | 1 | 28,600 |
|  | Total | 156,132 | 13,361 | 20 | 0 | 0 | 0 | 13,381 | 169,513 |  |  | 169,519 |
| Central Goldfields Shire Council | Flynn | 1,242 | 399 |  | 1 |  |  | 400 | 1,642 |  |  | 1,642 |
|  | Maryborough | 5,695 | 332 |  | 7 |  | 2 | 341 | 6,036 |  |  | 6,036 |
|  | Paddys Ranges | 1,337 | 292 |  |  |  |  | 292 | 1,629 |  | 2 | 1,627 |
|  | Tullaroop | 1,327 | 225 |  | 1 |  |  | 226 | 1,553 |  |  | 1,553 |
|  | Total | 9,601 | 1,248 | 0 | 9 | 0 | 2 | 1,259 | 10,860 |  |  | 10,858 |
| Colac Otway Shire Council | Un-Subdivided | 15,295 | 4,491 | 3 |  | 10 |  | 4,504 | 19,799 |  |  | 19,799 |
| Corangamite Shire Council | Central | 5,458 | 412 |  |  |  |  | 412 | 5,870 |  |  | 5,870 |
|  | Coastal | 1,466 | 305 |  |  |  |  | 305 | 1,771 |  |  | 1,771 |
|  | North | 1,488 | 382 |  |  |  |  | 382 | 1,870 |  |  | 1,870 |
|  | South-Central | 1,850 | 113 |  |  |  |  | 113 | 1,963 |  |  | 1,963 |
|  | South-West | 1,715 | 143 |  |  |  |  | 143 | 1,858 |  |  | 1,858 |
|  | Total | 11,977 | 1,355 | 0 | 0 | 0 | 0 | 1,355 | 13,332 |  |  | 13,332 |
| Darebin City Council | Cazaly | 30,828 | 3,842 | 10 |  | 5 |  | 3,857 | 34,685 | 3 |  | 34,688 |
|  | La Trobe | 28,182 | 3,187 | 8 |  | 1 |  | 3,196 | 31,378 |  |  | 31,378 |
|  | Rucker | 31,394 | 4,626 | 8 |  | 5 |  | 4,639 | 36,033 | 1 |  | 36,034 |
|  | Total | 90,404 | 11,655 | 26 | 0 | 11 | 0 | 11,692 | 102,096 |  |  | 102,100 |
| East Gippsland Shire Council | Un-Subdivided | 31,730 | 7,914 |  |  | 1 |  | 7,915 | 39,645 |  | 3 | 39,642 |
| Frankston City Council | North-East | 29,544 | 3,680 |  |  |  |  | 3,680 | 33,224 |  | 1 | 33,223 |
|  | North-West | 25,642 | 5,201 |  |  |  |  | 5,201 | 30,843 |  |  | 30,843 |
|  | South | 29,626 | 3,498 |  | 1 |  |  | 3,499 | 33,125 |  |  | 33,125 |
|  | Total | 84,812 | 12,379 | 0 | 1 | 0 | 0 | 12,380 | 97,192 |  |  | 97,191 |
| Gannawarra Shire Council | Avoca | 1,038 | 228 |  |  |  |  | 228 | 1,266 |  |  | 1,266 |
|  | Murray | 1,126 | 229 |  |  |  |  | 229 | 1,355 |  |  | 1,355 |
|  | Patchell | 3,206 | 327 |  |  | 3 |  | 330 | 3,536 |  |  | 3,536 |
|  | Yarran | 2,577 | 177 |  |  | 1 |  | 178 | 2,755 |  |  | 2,755 |
|  | Total | 7,947 | 961 | 0 | 0 | 4 | 0 | 965 | 8,912 |  |  | 8,912 |
| Glen Eira City Council | Camden | 28,356 | 2,960 |  |  | 4 |  | 2,964 | 31,320 |  |  | 31,320 |
|  | Rosstown | 29,076 | 4,400 |  |  | 6 |  | 4,406 | 33,482 |  |  | 33,482 |
|  | Tucker | 30,894 | 2,408 |  |  | 5 |  | 2,413 | 33,307 |  |  | 33,307 |
|  | Total | 88,326 | 9,768 | 0 | 0 | 15 | 0 | 9,783 | 98,109 |  |  | 98,109 |
| Glenelg Shire Council | Un-Subdivided | 14,470 | 2,336 | 3 | 1 | 1 |  | 2,341 | 16,811 |  |  | 16,811 |
| Golden Plains Shire Council | Un-Subdivided | 13,379 | 2,708 |  |  | 11 |  | 2,719 | 16,098 | 1 | 19 | 16,080 |
| Greater Bendigo City Council | Eppalock | 22,350 | 2,987 | 2 |  | 1 |  | 2,990 | 25,340 |  |  | 25,340 |
|  | Lockwood | 25,274 | 1,672 | 2 |  |  |  | 1,674 | 26,948 |  | 1 | 26,947 |
|  | Whipstick | 25,172 | 2,270 | 2 |  | 6 |  | 2,278 | 27,450 |  | 1 | 27,449 |
|  | Total | 72,796 | 6,929 | 6 | 0 | 7 | 0 | 6,942 | 79,738 |  |  | 79,736 |
| Greater Dandenong City Council | Lightwood | 22,972 | 2,844 |  |  | 6 |  | 2,850 | 25,822 | 1 |  | 25,823 |
|  | Paperbark | 23,671 | 2,718 |  |  | 6 |  | 2,724 | 26,395 |  | 1 | 26,394 |
|  | Red Gum | 19,565 | 5,677 |  |  | 33 |  | 5,710 | 25,275 | 2 |  | 25,277 |
|  | Silverleaf | 16,577 | 1,428 | 2 |  | 2 |  | 1,432 | 18,009 |  |  | 18,009 |
|  | Total | 82,785 | 12,667 | 2 | 0 | 47 | 0 | 12,716 | 95,501 |  |  | 95,503 |
| Greater Geelong City Council | Austin | 13,094 | 730 |  |  |  |  | 730 | 13,824 |  |  | 13,824 |
|  | Beangala | 10,500 | 2,990 | 2 |  | 1 |  | 2,993 | 13,493 |  | 1 | 13,492 |
|  | Brownbill | 12,041 | 1,246 | 1 |  |  |  | 1,247 | 13,288 |  |  | 13,288 |
|  | Buckley | 13,582 | 1,736 | 2 |  |  |  | 1,738 | 15,320 |  |  | 15,320 |
|  | Cheetham | 14,219 | 919 | 1 |  |  |  | 920 | 15,139 |  |  | 15,139 |
|  | Corio | 12,693 | 1,095 | 3 |  |  |  | 1,098 | 13,791 |  |  | 13,791 |
|  | Coryule | 8,490 | 5,737 | 1 |  |  |  | 5,738 | 14,228 | 1 | 1 | 14,228 |
|  | Cowie | 13,191 | 593 |  |  | 1 |  | 594 | 13,785 |  |  | 13,785 |
|  | Deakin | 14,086 | 631 | 6 |  |  |  | 637 | 14,723 | 1 |  | 14,724 |
|  | Kardinia | 13,540 | 907 | 2 |  |  |  | 909 | 14,449 |  |  | 14,449 |
|  | Kildare | 12,055 | 649 | 1 |  |  |  | 650 | 12,705 |  |  | 12,705 |
|  | Windermere | 14,596 | 1,067 |  |  |  |  | 1,067 | 15,663 |  |  | 15,663 |
|  | Total | 152,087 | 18,300 | 19 | 0 | 2 | 0 | 18,321 | 170,408 |  |  | 170,408 |
| Greater Shepparton City Council | Un-Subdivided | 40,944 | 2,424 | 4 |  |  |  | 2,428 | 43,372 |  |  | 43,372 |
| Hepburn Shire Council | Birch | 3,005 | 1,291 | 1 |  | 12 |  | 1,304 | 4,309 |  |  | 4,309 |
|  | Cameron | 1,490 | 529 | 2 |  | 3 |  | 534 | 2,024 |  |  | 2,024 |
|  | Coliban | 1,449 | 575 |  |  | 3 |  | 578 | 2,027 |  |  | 2,027 |
|  | Creswick | 3,691 | 557 |  |  | 3 |  | 560 | 4,251 | 2 |  | 4,253 |
|  | Holcombe | 1,318 | 746 | 1 |  | 4 |  | 751 | 2,069 |  |  | 2,069 |
|  | Total | 10,953 | 3,698 | 4 | 0 | 25 | 0 | 3,727 | 14,680 |  |  | 14,682 |

| Hindmarsh Shire Council | East | 1,449 | 216 |  |  |  |  | 216 | 1,665 |  |  | 1,665 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | North | 1,371 | 284 |  |  |  |  | 284 | 1,655 |  |  | 1,655 |
|  | West | 1,587 | 143 | 1 |  |  |  | 144 | 1,731 |  |  | 1,731 |
|  | Total | 4,407 | 643 | 1 | 0 | 0 | 0 | 644 | 5,051 |  |  | 5,051 |
| Hobsons Bay City Council | Cherry Lake | 16,099 | 1,938 | 8 |  | 4 |  | 1,950 | 18,049 |  | 2 | 18,047 |
|  | Strand | 23,198 | 2,741 | 9 |  |  |  | 2,750 | 25,948 |  | 2 | 25,946 |
|  | Wetlands | 17,757 | 2,113 | 3 |  |  |  | 2,116 | 19,873 |  | 4 | 19,869 |
|  | Total | 57,054 | 6,792 | 20 | 0 | 4 | 0 | 6,816 | 63,870 |  |  | 63,862 |
| Horsham Rural City Council | Un-Subdivided | 14,067 | 1,371 |  |  | 7 |  | 1,378 | 15,445 |  |  | 15,445 |
| Hume City Council | Aitken | 33,612 | 4,827 | 210 |  |  |  | 5,037 | 38,649 | 1 | 2 | 38,648 |
|  | Jacksons Creek | 29,364 | 3,028 | 3 |  |  |  | 3,031 | 32,395 |  |  | 32,395 |
|  | Meadow Valley | 41,862 | 2,126 | 4 |  |  |  | 2,130 | 43,992 | 3 |  | 43,995 |
|  | Total | 104,838 | 9,981 | 217 | 0 | 0 | 0 | 10,198 | 115,036 |  |  | 115,038 |
| Indigo Shire Council | Un-Subdivided | 11,486 | 1,377 |  | 1 | 3 |  | 1,381 | 12,867 |  | 2 | 12,865 |
| Kingston City Council | Central | 33,375 | 3,986 | 5 |  |  |  | 3,991 | 37,366 |  |  | 37,366 |
|  | North | 32,126 | 3,699 | 5 | 1 | 1 |  | 3,706 | 35,832 | 1 | 1 | 35,832 |
|  | South | 35,501 | 3,431 | 7 |  |  |  | 3,438 | 38,939 | 1 | 1 | 38,939 |
|  | Total | 101,002 | 11,116 | 17 | 1 | 1 | 0 | 11,135 | 112,137 |  |  | 112,137 |
| Knox City Council | Baird | 10,952 | 1,476 | 4 |  |  |  | 1,480 | 12,432 |  |  | 12,432 |
|  | Chandler | 11,030 | 800 | 4 |  |  |  | 804 | 11,834 | 2 |  | 11,836 |
|  | Collier | 10,895 | 613 | 5 |  |  |  | 618 | 11,513 |  | 1 | 11,512 |
|  | Dinsdale | 10,392 | 1,118 | 3 |  |  |  | 1,121 | 11,513 | 2 |  | 11,515 |
|  | Dobson | 12,714 | 677 | 2 |  |  |  | 679 | 13,393 |  |  | 13,393 |
|  | Friberg | 12,677 | 739 | 3 |  |  |  | 742 | 13,419 |  |  | 13,419 |
|  | Scott | 12,555 | 529 | 3 |  |  |  | 532 | 13,087 |  |  | 13,087 |
|  | Taylor | 13,147 | 485 |  |  |  |  | 485 | 13,632 |  |  | 13,632 |
|  | Tirhatuan | 12,169 | 782 | 5 |  |  |  | 787 | 12,956 | 1 |  | 12,957 |
|  | Total | 106,531 | 7,219 | 29 | 0 | 0 | 0 | 7,248 | 113,779 |  |  | 113,783 |
| Latrobe City Council | Central | 11,212 | 1,026 | 1 |  |  |  | 1,027 | 12,239 |  |  | 12,239 |
|  | East | 21,767 | 1,212 | 4 |  |  |  | 1,216 | 22,983 |  |  | 22,983 |
|  | South | 5,806 | 526 | 1 |  |  |  | 527 | 6,333 |  |  | 6,333 |
|  | West | 11,980 | 847 | 3 |  |  |  | 850 | 12,830 |  |  | 12,830 |
|  | Total | 50,765 | 3,611 | 9 | 0 | 0 | 0 | 3,620 | 54,385 |  |  | 54,385 |
| Loddon Shire Council | Boort | 1,325 | 251 |  |  | 4 |  | 255 | 1,580 |  |  | 1,580 |
|  | Inglewood | 1,250 | 278 |  | 2 | 1 |  | 281 | 1,531 |  |  | 1,531 |
|  | Tarnagulla | 908 | 564 | 2 |  | 4 |  | 570 | 1,478 |  |  | 1,478 |
|  | Terrick | 1,258 | 240 |  |  | 4 |  | 244 | 1,502 |  | 1 | 1,501 |
|  | Wedderburn | 1,025 | 462 |  | 1 | 2 |  | 465 | 1,490 |  |  | 1,490 |
|  | Total | 5,766 | 1,795 | 2 | 3 | 15 | 0 | 1,815 | 7,581 |  |  | 7,580 |
| Macedon Ranges Shire Council | East | 9,726 | 1,159 | 2 |  |  |  | 1,161 | 10,887 |  |  | 10,887 |
|  | South | 10,706 | 783 | 1 |  |  |  | 784 | 11,490 |  |  | 11,490 |
|  | West | 10,072 | 1,263 |  |  |  |  | 1,263 | 11,335 | 2 | 2 | 11,335 |
|  | Total | 30,504 | 3,205 | 3 | 0 | 0 | 0 | 3,208 | 33,712 |  |  | 33,712 |
| Manningham City Council | Heide | 28,108 | 1,192 | 10 |  |  |  | 1,202 | 29,310 |  |  | 29,310 |
|  | Koonung | 26,989 | 1,850 | 3 |  |  |  | 1,853 | 28,842 |  |  | 28,842 |
|  | Mullum Mullum | 28,102 | 1,067 | 10 |  |  |  | 1,077 | 29,179 |  |  | 29,179 |
|  | Total | 83,199 | 4,109 | 23 | 0 | 0 | 0 | 4,132 | 87,331 |  |  | 87,331 |
| Mansfield Shire Council | Bonnie Doon | 807 | 1,141 |  |  |  |  | 1,141 | 1,948 |  | 6 | 1,942 |
|  | Jamieson | 683 | 1,419 |  |  |  |  | 1,419 | 2,102 |  | 3 | 2,099 |
|  | Mansfield | 3,248 | 686 |  |  |  |  | 686 | 3,934 | 1 | 10 | 3,925 |
|  | Tolmie | 1,114 | 969 |  |  |  |  | 969 | 2,083 |  | 6 | 2,077 |
|  | Total | 5,852 | 4,215 | 0 | 0 | 0 | 0 | 4,215 | 10,067 |  |  | 10,043 |

| Maribyrnong City Council | River | 12,227 | 3,436 |  |  |  |  | 3,436 | 15,663 |  | 1 | 15,662 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Stony Creek | 13,377 | 2,524 | 1 |  | 1 |  | 2,526 | 15,903 |  | 1 | 15,902 |
|  | Yarraville | 18,414 | 3,836 | 6 |  |  |  | 3,842 | 22,256 | 1 | 5 | 22,252 |
|  | Total | 44,018 | 9,796 | 7 | 0 | 1 | 0 | 9,804 | 53,822 |  |  | 53,816 |
| Maroondah City Council | Arrabri | 24,886 | 2,411 |  |  |  |  | 2,411 | 27,297 |  |  | 27,297 |
|  | Mullum | 23,507 | 2,859 | 3 |  | 1 |  | 2,863 | 26,370 |  |  | 26,370 |
|  | Wyreena | 24,698 | 2,052 |  |  |  |  | 2,052 | 26,750 |  |  | 26,750 |
|  | Total | 73,091 | 7,322 | 3 | 0 | 1 | 0 | 7,326 | 80,417 |  |  | 80,417 |
| Melbourne City Council | Un-Subdivided | 43,691 | 64,823 |  |  |  |  | 64,823 | 108,514 | 26 | 106 | 108,434 |
| Melton City Council | Cambridge | 19,445 | 3,592 | 4 | 1 |  |  | 3,597 | 23,042 | 2 | 1 | 23,043 |
|  | Coburn | 28,165 | 5,418 |  | 5 |  |  | 5,423 | 33,588 |  | 1 | 33,587 |
|  | Watts | 17,233 | 2,160 |  | 3 |  |  | 2,163 | 19,396 |  |  | 19,396 |
|  | Total | 64,843 | 11,170 | 4 | 9 | 0 | 0 | 11,183 | 76,026 |  |  | 76,026 |
| Mildura Rural City Council | Un-Subdivided | 34,743 | 3,319 | 1 |  |  |  | 3,320 | 38,063 | 1 | 1 | 38,063 |
| Mitchell Shire Council | Central | 8,587 | 840 | 1 |  |  |  | 841 | 9,428 |  |  | 9,428 |
|  | North | 7,480 | 1,118 |  |  |  |  | 1,118 | 8,598 |  |  | 8,598 |
|  | South | 7,398 | 1,533 |  |  | 6 |  | 1,539 | 8,937 |  | 1 | 8,936 |
|  | Total | 23,465 | 3,491 | 1 | 0 | 6 | 0 | 3,498 | 26,963 |  |  | 26,962 |
| Moira Shire Council | Un-Subdivided | 20,467 | 2,956 |  | 2 | 3 |  | 2,961 | 23,428 |  | 1 | 23,427 |
| Monash City Council | Glen Waverley | 19,269 | 1,475 | 2 | 1 |  |  | 1,478 | 20,747 |  |  | 20,747 |
|  | Mount Waverley | 32,505 | 2,885 | 6 |  |  |  | 2,891 | 35,396 | 1 | 1 | 35,396 |
|  | Mulgrave | 29,258 | 1,285 | 5 |  |  |  | 1,290 | 30,548 | 1 |  | 30,549 |
|  | Oakleigh | 28,965 | 5,420 |  |  | 4 |  | 5,424 | 34,389 | 1 |  | 34,390 |
|  | Total | 109,997 | 11,065 | 13 | 1 | 4 | 0 | 11,083 | 121,080 |  |  | 121,082 |
| Moonee Valley City Council | Buckley | 27,488 | 2,782 | 12 |  | 12 | 1 | 2,807 | 30,295 |  |  | 30,295 |
|  | Myrnong | 24,725 | 4,002 | 12 |  | 23 |  | 4,037 | 28,762 |  |  | 28,762 |
|  | Rose Hill | 24,218 | 1,416 | 33 |  | 14 | 1 | 1,464 | 25,682 | 1 |  | 25,683 |
|  | Total | 76,431 | 8,200 | 57 | 0 | 49 | 2 | 8,308 | 84,739 |  |  | 84,740 |
| Moorabool Shire Council | Central Moorabool | 2,874 | 407 |  | 2 | 2 |  | 411 | 3,285 |  |  | 3,285 |
|  | East Moorabool | 11,942 | 1,662 | 9 | 2 | 6 |  | 1,679 | 13,621 |  |  | 13,621 |
|  | West Moorabool | 2,663 | 715 | 1 | 4 | 1 |  | 721 | 3,384 |  |  | 3,384 |
|  | Woodlands | 2,500 | 759 | 2 | 2 |  |  | 763 | 3,263 |  | 2 | 3,261 |
|  | Total | 19,979 | 3,543 | 12 | 10 | 9 | 0 | 3,574 | 23,553 |  |  | 23,551 |
| Moreland City Council | North-East | 36,578 | 4,641 |  |  |  |  | 4,641 | 41,219 | 2 | 1 | 41,220 |
|  | North-West | 37,233 | 3,881 |  |  |  |  | 3,881 | 41,114 | 4 |  | 41,118 |
|  | South | 23,579 | 6,067 |  |  |  |  | 6,067 | 29,646 | 3 | 1 | 29,648 |
|  | Total | 97,390 | 14,589 | 0 | 0 | 0 | 0 | 14,589 | 111,979 |  |  | 111,986 |
| Mornington Peninsula Shire Council | Briars | 39,439 | 3,727 | 5 |  | 7 |  | 3,739 | 43,178 | 1 |  | 43,179 |
|  | Cerberus | 11,273 | 1,116 |  |  | 1 |  | 1,117 | 12,390 | 1 |  | 12,391 |
|  | Nepean | 9,995 | 14,558 |  |  | 5 |  | 14,563 | 24,558 | 2 |  | 24,560 |
|  | Red Hill | 8,541 | 3,805 | 1 |  | 4 |  | 3,810 | 12,351 |  | 2 | 12,349 |
|  | Seawinds | 25,037 | 15,217 | 1 |  | 5 |  | 15,223 | 40,260 | 3 |  | 40,263 |
|  | Watson | 12,035 | 600 |  |  | 1 |  | 601 | 12,636 |  |  | 12,636 |
|  | Total | 106,320 | 39,023 | 7 | 0 | 23 | 0 | 39,053 | 145,373 |  |  | 145,378 |
| Mount Alexander Shire Council | Calder | 1,749 | 306 |  |  |  |  | 306 | 2,055 |  |  | 2,055 |
|  | Castlemaine | 6,521 | 492 |  |  |  |  | 492 | 7,013 |  |  | 7,013 |
|  | Coliban | 1,647 | 519 |  |  |  |  | 519 | 2,166 |  |  | 2,166 |
|  | Loddon River | 1,723 | 462 |  |  |  |  | 462 | 2,185 |  |  | 2,185 |
|  | Tarrengower | 1,619 | 437 |  |  |  |  | 437 | 2,056 |  |  | 2,056 |
|  | Total | 13,259 | 2,216 | 0 | 0 | 0 | 0 | 2,216 | 15,475 |  |  | 15,475 |
| Moyne Shire Council | Un-Subdivided | 11,736 | 2,368 | 4 |  |  |  | 2,372 | 14,108 | 16 |  | 14,124 |
| Murrindindi Shire Council | Cathedral | 1,010 | 779 | 1 |  | 2 |  | 782 | 1,792 |  | 1 | 1,791 |
|  | Cheviot | 1,511 | 382 |  |  |  |  | 382 | 1,893 |  |  | 1,893 |
|  | Eildon | 1,098 | 802 |  |  | 3 | 2 | 807 | 1,905 | 1 |  | 1,906 |
|  | King Parrot | 1,462 | 514 |  |  |  | 1 | 515 | 1,977 |  |  | 1,977 |
|  | Kinglake | 1,548 | 427 |  |  |  |  | 427 | 1,975 |  |  | 1,975 |
|  | Koriella | 1,250 | 625 | 2 |  | 1 | 2 | 630 | 1,880 |  |  | 1,880 |
|  | Red Gate | 1,960 | 244 |  |  |  | 3 | 247 | 2,207 |  |  | 2,207 |
|  | Total | 9,839 | 3,773 | 3 | 0 | 6 | 8 | 3,790 | 13,629 |  |  | 13,629 |
| Nillumbik Shire Council | Blue Lake | 6,674 | 271 | 2 |  |  |  | 273 | 6,947 |  |  | 6,947 |
|  | Bunjil | 6,176 | 167 |  |  |  |  | 167 | 6,343 |  |  | 6,343 |
|  | Edendale | 6,781 | 202 |  |  |  |  | 202 | 6,983 |  |  | 6,983 |
|  | Ellis | 5,996 | 189 |  |  | 2 |  | 191 | 6,187 |  |  | 6,187 |
|  | Sugarloaf | 6,647 | 261 |  |  |  |  | 261 | 6,908 |  | 1 | 6,907 |
|  | Swipers Gully | 6,394 | 208 | 2 |  |  |  | 210 | 6,604 | 1 |  | 6,605 |
|  | Wingrove | 6,109 | 292 |  |  |  |  | 292 | 6,401 |  |  | 6,401 |
|  | Total | 44,777 | 1,590 | 4 | 0 | 2 | 0 | 1,596 | 46,373 |  |  | 46,373 |
| Northern Grampians Shire Council | Central | 1,149 | 367 |  |  | 3 | 1 | 371 | 1,520 |  |  | 1,520 |
|  | Kara Kara | 2,415 | 690 | 2 |  | 5 | 1 | 698 | 3,113 |  |  | 3,113 |
|  | South West | 1,029 | 579 |  |  | 3 |  | 582 | 1,611 |  |  | 1,611 |
|  | Stawell | 4,250 | 368 |  |  | 2 |  | 370 | 4,620 |  |  | 4,620 |
|  | Total | 8,843 | 2,004 | 2 | 0 | 13 | 2 | 2,021 | 10,864 |  |  | 10,864 |
| Port Phillip City Council | Albert Park | 9,430 | 1,956 | 2 |  |  |  | 1,958 | 11,388 |  | 1 | 11,387 |
|  | Carlisle | 9,366 | 2,974 | 1 |  |  |  | 2,975 | 12,341 |  | 1 | 12,340 |
|  | Catani | 7,926 | 3,009 | 7 |  | 1 |  | 3,017 | 10,943 |  |  | 10,943 |
|  | Emerald Hill | 7,361 | 2,845 | 1 |  |  |  | 2,846 | 10,207 |  |  | 10,207 |
|  | Junction | 7,680 | 4,357 | 6 |  |  |  | 4,363 | 12,043 | 1 |  | 12,044 |
|  | Point Ormond | 9,364 | 2,726 | 2 |  |  |  | 2,728 | 12,092 |  | 1 | 12,091 |
|  | Sandridge | 8,477 | 2,125 | 4 |  | 1 |  | 2,130 | 10,607 | 1 | 2 | 10,606 |
|  | Total | 59,604 | 19,992 | 23 | 0 | 2 | 0 | 20,017 | 79,621 |  |  | 79,618 |
| Pyrenees Shire Council | Avoca | 1,118 | 309 |  |  | 7 |  | 316 | 1,434 |  |  | 1,434 |
|  | Beaufort | 1,150 | 278 |  |  | 1 |  | 279 | 1,429 |  |  | 1,429 |
|  | De Cameron | 673 | 746 |  |  | 2 |  | 748 | 1,421 |  |  | 1,421 |
|  | Ercildoune | 973 | 447 |  |  | 6 |  | 453 | 1,426 |  |  | 1,426 |
|  | Mount Emu | 1,060 | 330 |  |  | 3 |  | 333 | 1,393 |  |  | 1,393 |
|  | Total | 4,974 | 2,110 | 0 | 0 | 19 | 0 | 2,129 | 7,103 |  |  | 7,103 |
| Queenscliffe Borough Council | Un-Subdivided | 2,594 | 1,620 | 1 | 2 | 50 | 1 | 1,674 | 4,268 |  |  | 4,268 |
| South Gippsland Shire Council | Coastal-Promontory | 4,031 | 5,244 | 2 |  | 3 |  | 5,249 | 9,280 |  |  | 9,280 |
|  | Strzelecki | 8,294 | 1,071 | 2 |  |  |  | 1,073 | 9,367 |  |  | 9,367 |
|  | Tarwin Valley | 8,169 | 995 | 1 |  |  |  | 996 | 9,165 |  |  | 9,165 |
|  | Total | 20,494 | 7,310 | 5 | 0 | 3 | 0 | 7,318 | 27,812 |  |  | 27,812 |
| Southern Grampians Shire Council | Un-Subdivided | 12,282 | 1,120 | 2 |  | 2 |  | 1,124 | 13,406 |  | 1 | 13,405 |
| Stonnington City Council | East | 23,367 | 3,612 | 2 |  | 2 | 22 | 3,638 | 27,005 | 23 | 23 | 27,005 |
|  | North | 21,382 | 6,933 | 3 | 3 |  | 24 | 6,963 | 28,345 | 25 | 25 | 28,345 |
|  | South | 19,908 | 5,379 |  |  |  | 39 | 5,418 | 25,326 | 37 | 39 | 25,324 |
|  | Total | 64,657 | 15,924 | 5 | 3 | 2 | 85 | 16,019 | 80,676 |  |  | 80,674 |
| Strathbogie Shire Council | Honeysuckle Creek | 1,095 | 222 |  |  | 6 |  | 228 | 1,323 |  |  | 1,323 |
|  | Hughes Creek | 1,038 | 205 |  |  | 9 |  | 214 | 1,252 |  |  | 1,252 |
|  | Lake Nagambie | 1,915 | 706 |  |  | 27 |  | 733 | 2,648 | 1 |  | 2,649 |
|  | Mount Wombat | 987 | 369 | 1 |  | 18 |  | 388 | 1,375 |  |  | 1,375 |
|  | Seven Creeks | 2,438 | 261 | 2 |  | 3 |  | 266 | 2,704 |  |  | 2,704 |
|  | Total | 7,473 | 1,763 | 3 | 0 | 63 | 0 | 1,829 | 9,302 |  |  | 9,303 |
| Surf Coast Shire Council | Anglesea | 2,841 | 3,978 |  |  | 45 |  | 4,023 | 6,864 |  |  | 6,864 |
|  | Lorne | 1,313 | 2,080 |  |  | 52 |  | 2,132 | 3,445 |  |  | 3,445 |
|  | Torquay | 9,164 | 3,987 |  |  | 17 |  | 4,004 | 13,168 |  |  | 13,168 |
|  | Winchelsea | 5,774 | 689 |  |  | 7 |  | 696 | 6,470 |  |  | 6,470 |
|  | Total | 19,092 | 10,734 | 0 | 0 | 121 | 0 | 10,855 | 29,947 |  |  | 29,947 |
| Swan Hill Rural City Council | Central | 8,020 | 365 |  |  |  | 1 | 366 | 8,386 |  |  | 8,386 |
|  | Lakes | 1,751 | 265 |  |  |  |  | 265 | 2,016 |  |  | 2,016 |
|  | Murray-Mallee | 1,845 | 170 |  |  |  |  | 170 | 2,015 | 2 |  | 2,017 |
|  | Robinvale | 1,946 | 104 |  |  |  |  | 104 | 2,050 |  |  | 2,050 |
|  | Total | 13,562 | 904 | 0 | 0 | 0 | 1 | 905 | 14,467 |  |  | 14,469 |
| Towong Shire Council | Un-Subdivided | 4,634 | 851 | 1 |  |  |  | 852 | 5,486 |  |  | 5,486 |
| Wangaratta Rural City Council | Un-Subdivided | 20,495 | 1,231 | 1 |  | 11 |  | 1,243 | 21,738 |  |  | 21,738 |
| Warrnambool City Council | Un-Subdivided | 23,019 | 2,111 | 1 |  | 2 |  | 2,114 | 25,133 | 1 |  | 25,134 |
| Wellington Shire Council | Un-Subdivided | 29,854 | 12,326 | 1 |  |  |  | 12,327 | 42,181 | 12 |  | 42,193 |
| West Wimmera Shire Council | Un-Subdivided | 3,234 | 784 |  |  |  |  | 784 | 4,018 |  |  | 4,018 |
| Whitehorse City Council | Central | 20,630 | 1,512 | 2 |  |  |  | 1,514 | 22,144 |  |  | 22,144 |
|  | Elgar | 20,202 | 3,259 | 1 |  | 4 | 3 | 3,267 | 23,469 |  |  | 23,469 |
|  | Morack | 20,850 | 1,154 | 1 | 1 | 2 |  | 1,158 | 22,008 |  |  | 22,008 |
|  | Riversdale | 19,409 | 2,326 | 3 |  |  |  | 2,329 | 21,738 | 1 |  | 21,739 |
|  | Springfield | 20,993 | 2,135 | 3 |  |  |  | 2,138 | 23,131 |  | 1 | 23,130 |
|  | Total | 102,084 | 10,386 | 10 | 1 | 6 | 3 | 10,406 | 112,490 |  |  | 112,490 |
| Whittlesea City Council | North | 25,382 | 4,927 | 6 | 2 | 7 |  | 4,942 | 30,324 | 1 | 7 | 30,318 |
|  | South East | 41,376 | 3,618 | 3 |  | 16 |  | 3,637 | 45,013 |  | 26 | 44,987 |
|  | South West | 36,781 | 4,458 | 3 |  | 21 |  | 4,482 | 41,263 |  | 20 | 41,243 |
|  | Total | 103,539 | 13,003 | 12 | 2 | 44 | 0 | 13,061 | 116,600 |  |  | 116,548 |
| Wodonga City Council | Un-Subdivided | 24,120 | 2,957 | 1 |  |  |  | 2,958 | 27,078 | 1 | 3 | 27,076 |
| Wyndham City Council | Chaffey | 35,944 | 6,579 | 1 |  |  |  | 6,580 | 42,524 |  |  | 42,524 |
|  | Harrison | 29,526 | 10,547 | 3 |  | 3 |  | 10,553 | 40,079 |  |  | 40,079 |
|  | Iramoo | 27,401 | 4,366 | 4 |  | 3 |  | 4,373 | 31,774 |  | 1 | 31,773 |
|  | Total | 92,871 | 21,492 | 8 | 0 | 6 | 0 | 21,506 | 114,377 |  |  | 114,376 |
| Yarra City Council | Langridge | 16,933 | 4,048 |  |  |  |  | 4,048 | 20,981 |  |  | 20,981 |
|  | Melba | 17,552 | 5,378 | 1 | 2 | 3 |  | 5,384 | 22,936 |  | 2 | 22,934 |
|  | Nicholls | 17,936 | 4,662 | 2 | 2 |  |  | 4,666 | 22,602 | 1 |  | 22,603 |
|  | Total | 52,421 | 14,088 | 3 | 4 | 3 | 0 | 14,098 | 66,519 |  |  | 66,518 |
| Yarra Ranges Shire Council | Billanook | 12,255 | 301 | 3 |  |  |  | 304 | 12,559 |  |  | 12,559 |
|  | Chandler | 11,008 | 350 | 4 |  |  |  | 354 | 11,362 |  |  | 11,362 |
|  | Chirnside | 11,794 | 501 | 5 |  |  |  | 506 | 12,300 |  |  | 12,300 |
|  | Lyster | 10,949 | 464 | 7 |  |  |  | 471 | 11,420 |  |  | 11,420 |
|  | Melba | 11,735 | 770 | 4 |  |  | 1 | 775 | 12,510 |  |  | 12,510 |
|  | O'Shannassy | 10,993 | 1,308 | 4 |  |  |  | 1,312 | 12,305 |  |  | 12,305 |
|  | Ryrie | 11,474 | 720 | 3 |  | 1 |  | 724 | 12,198 |  | 2 | 12,196 |
|  | Streeton | 10,968 | 459 | 6 | 1 |  |  | 466 | 11,434 | 1 |  | 11,435 |
|  | Walling | 12,164 | 688 | 3 |  |  |  | 691 | 12,855 |  |  | 12,855 |
|  | Total | 103,340 | 5,561 | 39 | 1 | 1 | 1 | 5,603 | 108,943 |  |  | 108,942 |
| Yarriambiack Shire Council | Dunmunkle | 1,613 | 293 |  |  |  |  | 293 | 1,906 |  |  | 1,906 |
|  | Hopetoun | 1,418 | 238 |  |  |  |  | 238 | 1,656 |  |  | 1,656 |
|  | Warracknabeal | 2,349 | 343 |  |  |  |  | 343 | 2,692 |  |  | 2,692 |
|  | Total | 5,380 | 874 | 0 | 0 | 0 | 0 | 874 | 6,254 |  |  | 6,254 |
| State Totals |  | 3,521,971 | 574,430 | 720 | 72 | 708 | 106 | 576,036 | 4,098,007 | 338 | 499 | 4,097,846 |

(a) Council electors -property sold 		(b) Council electors omitted	(c) State roll coding errors

N – Non-resident owner

A – Resident owner (not on EC list)

P - Occupier ratepayer

O – Corporation (owner)

T – Corporation (occupier)

Appendix 3: Details of Returning Officers and election offices

| Council | Returning Officer | Election office address |
| --- | --- | --- |
| Alpine Shire Council | Andrew Robertson | Alpine Shire Council Election, 52 Norton Street, Wangaratta |
| Ararat Rural City Council | Kevin Waterhouse | Ararat Rural City Council Offices, Cnr Vincent and High Streets, Ararat |
| Ballarat City Council | Colin Nicholson | Lvl 2 Central Square Shopping Centre, 18 Armstrong Street South, Ballarat |
| Banyule City Council | Bob Oldfield | 9-13 Flintoff Street, Greensborough |
| Bass Coast Shire Council | Janine Taylor | Bass Coast Civic Centre, 76 McBride Avenue (access via Baillieu Street), Wonthaggi |
| Baw Baw Shire Council | Phillip Robinson | 75A Queen Street, Warragul |
| Bayside City Council | Elaine Milne | 16/354 Reserve Road, Cheltenham |
| Benalla Rural City Council | Jim Shanahan | 33 Sydney Road, Benalla |
| Boroondara City Council | Graeme Cobb | 25 Inglesby Road, Camberwell |
| Buloke Shire Council | Julie Nix | Donald District Office, 31 McCulloch Street, Donald |
| Campaspe Shire Council | Wayne Park | 11 Murray Valley Highway, Echuca |
| Cardinia Shire Council | Rob Rutter | Gallery Room, Cardinia Cultural Centre, Lakeside Boulevard, Pakenham |
| Casey City Council | Ian Herron | Old Shire Offices, 160 Sladen Street, Cranbourne |
| Central Goldfields Shire Council | Robyn Walker | Community Hub, Shire Offices, 12-22 Nolan Street, Maryborough |
| Colac Otway Shire Council | Elizabeth Reeves | 139 Wilson Street, Colac |
| Corangamite Shire Council | John Angel | Corangamite Civic Centre, 181 Manifold Street, Camperdown |
| Darebin City Council | Mike King | 1A/99 Bell Street, Preston |
| East Gippsland Shire Council | Sandra Wood | 54 Service Street, Bairnsdale |
| Frankston City Council | Ian Smyth | 62 Playne Street, Frankston |
| Gannawarra Shire Council | Mardi Messer | Gannawarra Shire Council, 47 Victoria Street, Kerang |
| Glen Eira City Council | Jill Esplan | East Caulfield Reserve Social Room, Dudley Street, Caulfield East |
| Glenelg Shire Council | Jan Lineker | Drill Hall, 26 Bentinck Street, Portland |
| Golden Plains Shire Council | Colin Riley | Golden Plains Shire Council Offices, 2 Pope Street, Bannockburn |
| Greater Bendigo City Council | Tony McDowell | First Floor Shop 3 The Beehive Plaza, 18 Pall Mall, Bendigo |
| Greater Dandenong City Council | Bill Irvine | 279 Lonsdale Street, Dandenong |
| Greater Geelong City Council | Eeon Macaulay | Lvl 2/10 Moorabool Street, Geelong |
| Greater Shepparton City Council | Mick Bastian | 2/164 Welsford Street, Shepparton |
| Hepburn Shire Council | Jeff Stewart | 2 Duke Street, Daylesford |
| Hindmarsh Shire Council | Lynne Sargent | 85 Nelson Street, Nhill |
| Hobsons Bay City Council | Rose McVicar | Meeting Rooms 1 & 2, Civic Centre, 115 Civic Parade, Altona |
| Horsham Rural City Council | Graeme Sargent | 24 Darlot Street, Horsham |
| Hume City Council | Peter Murray | Broadmeadows Town Hall, 1079 Pascoe Vale Road, Broadmeadows |
| Indigo Shire Council | Trevor Deacon | Chiltern Community Centre, 52 Main Street, Chiltern |
| Kingston City Council | Peter Cole | Level 5, 1230 Nepean Highway, Cheltenham |
| Knox City Council | Leonie Taylor | Unit 3/794 Burwood Highway, Ferntree Gully |
| Latrobe City Council | Alan Bright | 126-130 George Street, Morwell |
| Loddon Shire Council | Andrew Howlett | 37 Peppercorn Way, (parallel to Loddon Valley Highway), Serpentine |
| Macedon Ranges Shire Council | Kate Daniel | Mechanics Institute, 71 Mollison Street, Kyneton |
| Manningham City Council | Helen Halliday | 2 Hummell Way, Doncaster |
| Mansfield Shire Council | Jo Wise | Stringybark Room, Council Offices, 33 Highett Street, Mansfield |
| Maribyrnong City Council | Heather Oke | 92 Nicholson Street, Nicholson Street Mall (next to Commonwealth Bank), Footscray |
| Maroondah City Council | Greg Irvine | Ringwood Square Shopping Centre, Shop 24A 59 Maroondah Hwy, Ringwood |
| Melbourne City Council | Bill Lang | Grnd Flr, Melbourne Town Hall, Administration Building, 120 Swanston Street, |
| Melton City Council | Peter Long | Community Hall, 232 High Street, Melton |
| Mildura Rural City Council | Trevor Leighton | 2/118 Eighth Street, Mildura |
| Mitchell Shire Council | Alison Ridley | Mitchell Shire Council Offices, 113 High Street, Broadford |
| Moira Shire Council | Tim Gerrish | 59 Broadway Street, Cobram |
| Monash City Council | Jeff Gazzard | Monash Seminar and Training Centre, 1A Atherton Road, Oakleigh |
| Moonee Valley City Council | Kathryn Freeman | 67L Matthews Avenue Cnr Hawker Street, Airport West |
| Moorabool Shire Council | Doug Lindsay | Lerderderg Library, 215 Main Street, Bacchus Marsh |
| Moreland City Council | Bob Guest | Moreland Civic Centre, 90 Bell Street, Coburg |
| Mornington Peninsula Shire Council | Julie Allan | Shop 2, 1391-1395 Point Nepean Road, Rosebud |
| Mount Alexander Shire Council | Bob Twyford | 155 Barker Street, Castlemaine |
| Moyne Shire Council | Lynda Beekhof | Blackwood Centre, Commercial Road, Koroit |
| Murrindindi Shire Council | Peter Williams | Murrindindi Shire Council Service Centre, Semi Circle, Yea |
| Nillumbik Shire Council | Tony Buttler | Nillumbik Shire Council, Civic Drive, Greensborough |
| Northern Grampians Shire Council | Andy McCann | Media Centre, Grandstand, Central Park, 10-12 Main Street, Stawell |
| Port Phillip City Council | Trevor Sutherland | 1st Floor, 19-25 Raglan Street, South Melbourne |
| Pyrenees Shire Council | Peter Reid | Beaufort Community Development Centre, 1 Lawrence Street, Beaufort |
| Queenscliffe Borough Council | Helen Friee | Municipal Offices, 50 Learmonth Street, Queenscliff |
| South Gippsland Shire Council | Sheryl Bruce | 52A Bair Street, Leongatha |
| Southern Grampians Shire Council | Leanne Huf | Martin J. Hynes Auditorium, 5 Market Place, Hamilton |
| Stonnington City Council | Ed Stewart | Banquet Hall, Malvern Town Hall, Cnr Glenferrie Road and High Street, Malvern |
| Strathbogie Shire Council | Ian Wise | Council Offices, 109A Binney Street, Euroa |
| Surf Coast Shire Council | John Manley | 1/28A Baines Crescent, Torquay |
| Swan Hill Rural City Council | Tamara Matthews | Town Hall, 53-57 McCallum Street, Swan Hill |
| Towong Shire Council | Harold Cover | Towong Shire Council Offices, 32 Towong Street, Tallangatta |
| Wangaratta Rural City Council | Elaine Broadway | 52 Norton Street, Wangaratta |
| Warrnambool City Council | Russell Isaac | Bayside City Plaza, 24-36 Fairy Street, Warrnambool |
| Wellington Shire Council | Julie Duffy | Port of Sale Civic Centre, 70 Foster Street, Sale |
| West Wimmera Shire Council | Iain McNee | Edenhope Business Centre, 45 Elizabeth Street, Edenhope |
| Whitehorse City Council | Keith Crothers | 183-185 Springvale Road, Nunawading |
| Whittlesea City Council | Chris Montgomery | Council Offices, 25 Ferres Boulevard, South Morang |
| Wodonga City Council | Alan Cuman | 5/155 Melbourne Road, Wodonga |
| Wyndham City Council | Mary Noonan | 3-5 Werribee Street, Werribee |
| Yarra City Council | Henry Gaughan | Fitzroy Town Hall, Reading Room Entrance, 201 Napier Street, Fitzroy |
| Yarra Ranges Shire Council | Les Johnson | 5 Moores Road, Monbulk |
| Yarriambiack Shire Council | Fiona Werner | Yarriambiack Shire Council Offices, 34 Lyle Street, Warracknabeal |

Appendix 4: Details of information sessions for candidates

| Municipality | Address | Date | Time |
| --- | --- | --- | --- |
| Alpine Shire Council | Council Chambers, Alpine Shire Council Offices, Great Alpine Road, Bright | Wednesday, 19 September 2012 | 7.00 pm |
| Ararat Rural City Council | Council Chambers, Corner of Vincent and High Streets, Ararat | Monday, 17 September 2012 | 6.00 pm |
| Ballarat City Council | Trench Room, Town Hall, Sturt Street, Ballarat | Tuesday, 18 September 2012 | 6.30 pm |
| Banyule City Council | Council Chambers, 275 Upper Heidelberg Road, Ivanhoe | Wednesday, 19 September 2012 | 7.00 pm |
| Bass Coast Shire Council | Council Chambers, Bass Coast Shire Council Civic Centre, Wonthaggi | Monday, 17 September 2012 | 7.00 pm |
|  | Cowes Cultural Centre, Meeting Room 1, Thompson Avenue, Cowes | Tuesday, 18 September 2012 | 7.00 pm |
| Baw Baw Shire Council | Council Chambers, Civic Place, Warragul | Thursday, 13 September 2012 | 6.00 pm |
| Bayside City Council | Bayside Corporate Centre, 76 Royal Avenue, Sandringham | Wednesday, 19 September 2012 | 3.00 pm |
|  | Bayside Corporate Centre, 76 Royal Avenue, Sandringham | Wednesday, 19 September 2012 | 6.00 pm |
| Benalla Rural City Council | Benalla Performing Arts and Convention Centre, Samaria Road, Benalla | Monday, 17 September 2012 | 7.00 pm |
| Boroondara City Council | Boroondara Room, Council Offices, 8 Inglesby Road, Camberwell | Wednesday, 19 September 2012 | 7.00 pm |
| Borough of Queenscliffe Council | Town Hall, 50 Learmonth Street, Queenscliff | Tuesday, 18 September 2012 | 6.00 pm |
| Buloke Shire Council | District Office, 65 Horace Street, Sea Lake | Tuesday, 18 September 2012 | 6.30 pm |
|  | District Office, 367 Broadway, Wycheproof | Wednesday, 19 September 2012 | 6.30 pm |
| Campaspe Shire Council | Function Room, 35 Heygarth Street, Echuca | Wednesday, 19 September 2012 | 7.00 pm |
| Cardinia Shire Council | Council Chambers, Shire Offices, Henty Way, Pakenham | Wednesday, 19 September 2012 | 7.00 pm |
| Casey City Council | Council Chambers, Magid Drive, Narre Warren | Wednesday, 19 September 2012 | 2.30 pm |
|  | Council Chambers, Magid Drive, Narre Warren | Wednesday, 19 September 2012 | 7.30 pm |
| Central Goldfields Shire Council | Community Hub, Shire Offices, 12-22 Nolan Street, Maryborough | Tuesday, 18 September 2012 | 7.30 pm |
| Colac Otway Shire Council | Colac Otway Performing Arts and Cultural Centre, Gellibrand Street, Colac | Wednesday, 19 September 2012 | 7.00 pm |
| Corangamite Shire Council | Old Council Chambers, Corangamite Civic Centre, 181 Manifold Street, Camperdown | Monday, 17 September 2012 | 7.00 pm |
| Darebin City Council | Council Chambers, 350 High Street, Preston | Wednesday, 19 September 2012 | 7.00 pm |
| East Gippsland Shire Council | Bairnsdale Corporate Centre, 273 Main Street, Bairnsdale | Wednesday, 19 September 2012 | 7.00 pm |
| Frankston City Council | Acacia Room, Frankston Civic Centre, Corner of Young and Davey Streets, Frankston | Tuesday, 18 September 2012 | 6.30 pm |
| Gannawarra Shire Council | Council offices, 47 Victoria Street, Kerang | Monday, 17 September 2012 | 7.00 pm |
| Glen Eira City Council | Yarra Yarra Room, Glen Eira Town Hall, Corner of Glen Eira and Hawthorn Roads, Caulfield | Wednesday, 12 September 2012 | 6.30 pm |
| Glenelg Shire Council | Reception Room, Glenelg Shire Council, 71 Cliff Street, Portland | Tuesday, 18 September 2012 | 7.00 pm |
| Golden Plains Shire Council | Rokewood Memorial Hall, Ferrars Road, Rokewood | Wednesday, 19 September 2012 | 7.30 pm |
| Greater Bendigo City Council | Reception Room, Town Hall, Lyttleton Terrace, Bendigo | Tuesday, 21 August 2012 | 7.30 pm |
| Greater Dandenong City Council | Springvale Customer Service Centre, 397-405 Springvale Road, Springvale | Wednesday, 19 September 2012 | 7.00 pm |
| Greater Geelong City Council | Geelong City Hall, 30 Gheringhap Street, Geelong | Monday, 3 September 2012 | 6.30 pm |
|  | Geelong City Hall, 30 Gheringhap Street, Geelong | Monday, 10 September 2012 | 6.30 pm |
| Greater Shepparton City Council | Council Board Room, 90 Welsford Street, Shepparton | Monday, 17 September 2012 | 6.30 pm |
| Hepburn Shire Council | Town Hall, 76 Vincent Street, Daylesford | Wednesday, 19 September 2012 | 7.00 pm |
| Hindmarsh Shire Council | Council Chamber, 92 Nelson Street, Nhill | Wednesday, 19 September 2012 | 7.00 pm |
| Hobsons Bay City Council | Meeting Room 3, Hobsons Bay Civic Centre, 115 Civic Drive, Altona | Wednesday, 19 September 2012 | 7.00 pm |
| Horsham Rural City Council | Reception Room, Civic Centre, Roberts Avenue, Horsham | Wednesday, 19 September 2012 | 6.00 pm |
| Hume City Council | Council Chamber, 1079 Pascoe Vale Road, Broadmeadows | Tuesday, 18 September 2012 | 7.00 pm |
| Indigo Shire Council | Chiltern Memorial Hall, 90 Conness Street, Chiltern | Monday, 17 September 2012 | 6.00 pm |
| Kingston City Council | Council Offices, 1230 Nepean Highway, Cheltenham | Tuesday, 18 September 2012 | 7.00 pm |
| Knox City Council | Knox City Council, Civic Centre, 511 Burwood Highway, Wantirna South | Tuesday, 18 September 2012 | 7.00 pm |
| Latrobe City Council | Nambur Wariga, Corporate Headquarters, 141 Commercial Road, Morwell | Wednesday, 19 September 2012 | 6.00 pm |
| Loddon Shire Council | 37 Peppercorn Way (parallel to Loddon Valley Highway), Serpentine | Tuesday, 18 September 2012 | 7.30 pm |
| Macedon Ranges Shire Council | Mechanics Institute, 71 Mollison Street, Kyneton | Tuesday, 18 September 2012 | 7.00 pm |
| Manningham City Council | Council Chambers, Council Offices, 699 Doncaster Road, Doncaster | Thursday, 13 September 2012 | 7.00 pm |
|  | Council Chambers, Council Offices, 699 Doncaster Road, Doncaster | Monday, 17 September 2012 | 7.00 pm |
| Mansfield Shire Council | Council Chambers, 33 Highett Street, Mansfield | Wednesday, 19 September 2012 | 6.30 pm |
| Maribyrnong City Council | Reception Room, Maribyrnong Council Offices, Corner of Hyde and Napier Streets, Footscray | Monday, 17 September 2012 | 7.00 pm |
| Maroondah City Council | Council Chambers, City Offices, Braeside Avenue, Ringwood | Tuesday, 18 September 212 | 7.00 pm |
| Melbourne City Council | Melbourne Town Hall, Administration Building, 120 Swanston Street, Melbourne | Monday, 17 September 2012 | 7.00 pm |
|  | Melbourne Town Hall, Administration Building, 120 Swanston Street, Melbourne | Wednesday, 19 September 2012 | 12.30 pm |
| Melton City Council | Melton Community Hall, Meeting Room 4, 232 High Street, Melton | Tuesday, 18 September 2012 | 7.00 pm |
| Mildura Rural City Council | Council Committee Room, Deakin Avenue, Mildura | Tuesday, 18 September 2012 | 7.00 pm |
| Mitchell Shire Council | Council Chambers, 113 High Street, Broadford | Wednesday, 19 September 2012 | 7.00 pm |
| Moira Shire Council | Cobram Civic Centre, Punt Road, Cobram | Tuesday, 18 September 2012 | 6.30 pm |
| Monash City Council | Council Chambers, Monash Civic Centre, 293 Springvale Road, Glen Waverley | Wednesday, 19 September 2012 | 7.00 pm |
| Moonee Valley City Council | Moonee Valley Civic Centre, 9 Kellaway Avenue, Moonee Ponds | Wednesday, 19 September 2012 | 7.00 pm |
| Moorabool Shire Council | Moorabool Shire Offices, 15 Stead Street, Ballan | Tuesday, 18 September 2012 | 7.00 pm |
| Moreland City Council | Council Chambers, Municipal Offices, 90 Bell Street, Coburg | Tuesday, 18 September 2012 | 7.00 pm |
| Mornington Peninsula Shire Council | Shire Offices, 90 Besgrove Street, Rosebud | Tuesday, 18 September 2012 | 4.00 pm |
|  | Shire Offices, 2 Queen Street, Mornington | Tuesday, 18 September 2012 | 7.00 pm |
|  | Shire Offices, 21 Marine Parade, Hastings | Wednesday, 19 September 2012 | 5.00 pm |
| Mount Alexander Shire Council | Ray Bradfield Room, Victory Park, Castlemaine | Monday, 17 September 2012 | 7.00 pm |
| Moyne Shire Council | Blackwood Centre, Commercial Road, Koroit | Monday, 17 September 2012 | 7.00 pm |
| Murrindindi Shire Council | Murrindindi Shire Council Service Centre, Semi Circle, Yea | Monday, 17 September 2012 | 7.30 pm |
| Nillumbik Shire Council | Council Chambers, Civic Drive, Greensborough | Monday, 17 September 2012 | 6.30 pm |
| Northern Grampians Shire Council | Council Chamber, Western Highway Office, 50-52 Longfield Street, Stawell | Monday, 17 September 2012 | 7.30 pm |
|  | Committee Room, Town Hall, 40 Napier Street, St Arnaud | Tuesday, 18 September 2012 | 7.30 pm |
| Port Phillip City Council | 1st Floor, 19-25 Raglan Street, South Melbourne | Monday, 17 September 2012 | 7.30 pm |
| Pyrenees Shire Council | Lexton Community Centre, Corner of Williamson and Goldsmith Streets, Lexton | Monday, 17 September 2012 | 7.00 pm |
| South Gippsland Shire Council | Council Chamber, Michael Place, Leongatha | Tuesday, 18 September 2012 | 7.00 pm |
| Southern Grampians Shire Council | Martin J. Hynes Auditorium, 5 Market Place, Hamilton | Monday, 17 September 2012 | 7.30 pm |
| Stonnington City Council | Malvern Town Hall, Corner of Glenferrie Road and High Street, Malvern | Tuesday, 18 September 2012 | 7.00 pm |
| Strathbogie Shire Council | Council Offices, 109A Binney Street, Euroa | Monday, 17 September 2012 | 7.00 pm |
| Surf Coast Shire Council | Lorne Fig Tree Community House, 16 Mountjoy Parade, Lorne | Monday, 17 September 2012 | 7.00 pm |
|  | Anglesea Senior Citizens Centre, McMillan Street, Anglesea | Tuesday, 18 September 2012 | 5.30 pm |
|  | Surf Coast Shire Council Offices, 1 Merrijig Drive, Torquay | Wednesday, 19 September 2012 | 7.30 pm |
|  | Winchelsea Senior Citizens Centre, Harding Street, Winchelsea | Monday, 17 September 2012 | 7.00 pm |
| Swan Hill Rural City Council | Meeting Room 1, Town Hall, 53-57 McCallum Street, Swan Hill | Monday, 17 September 2012 | 7.00 pm |
| Towong Shire Council | Corryong Council Offices, 76 Hansen Street, Corryong | Tuesday, 18 September 2012 | 7.00 pm |
|  | Towong Shire Council Offices, 32 Towong Street, Tallangatta | Wednesday, 19 September 2012 | 7.00 pm |
| Wangaratta Rural City Council | Wangaratta Government Centre, Council Chamber, Corner of Ovens and Ford Streets, Wangaratta | Wednesday, 19 September 2012 | 6.00 pm |
| Warrnambool City Council | Reception Room, Warrnambool Civic Centre, 25 Liebig Street, Warrnambool | Wednesday, 19 September 2012 | 7.00 pm |
| Wellington Shire Council | Wellington Room, Port of Sale Civic Centre, 70 Foster Street, Sale | Wednesday, 19 September 2012 | 11.00 am |
| West Wimmera Shire Council | Civic Centre, 49 Elizabeth Street, Edenhope | Tuesday, 18 September 2012 | 7.30 pm |
|  | Shire Offices, Baker Street, Kaniva | Wednesday, 19 September 2012 | 7.30 pm |
| Whitehorse City Council | Whitehorse Civic Centre, Main Service Centre, 379 Whitehorse Road, Nunawading | Tuesday, 18 September 2012 | 7.00 pm |
| Whittlesea City Council | Fountain View Room, Council offices, Ferres Boulevard, South Morang | Monday, 17 September 2012 | 7.00 pm |
| Wodonga City Council | Wodonga City Council Offices, 104 Hovell Street, Wodonga | Tuesday, 18 September 2012 | 6.00 pm |
| Wyndham City Council | Civic Centre, 45 Princes Highway, Werribee | Wednesday, 19 September 2012 | 7.00 pm |
| Yarra City Council | Meeting Room 1, Richmond Town Hall, Bridge Road, Richmond | Wednesday, 19 September 2012 | 7.00 pm |
| Yarra Ranges Shire Council | Council Offices, 15 Anderson Street, Lilydale | Wednesday, 19 September 2012 | 7.00 pm |
| Yarriambiack Shire Council | Function Room, Shire Offices, 34 Lyle Street, Warracknabeal | Monday, 17 September 2012 | 7.00 pm |

Appendix 5: VEC discussion paper: Conformity with how-to-vote cards

Under the preferential system operating in Victorian local government elections, voters have to number every square on the ballot paper. In unsubdivided councils and multi-councillor wards, there are often large numbers of candidates on the ballot paper. The nature of the preferential system encourages candidates to negotiate preference arrangements with each other, so that they can benefit from preferences flowing from elected or excluded candidates. To maximise their chances of election, candidates issue directions to voters on how to allocate their preferences. In elections conducted by post, candidates may include their advised indications of preferences, to be printed with the candidate statements included in the ballot packs that the VEC posts to every voter. In attendance elections, candidates and their supporters distribute registered how-to-vote cards to voters outside voting centres.

The VEC can provide information on the degree to which voters conform with candidates’ how-to-vote instructions. For elections counted by computer, the VEC holds the preferences for each vote, which can be sorted by candidate and by conformity with how-to-vote instructions. After the 2008 local government elections, the VEC selected ten elections for study – all for multi-councillor electorates. To ensure a representative sample, the VEC selected attendance and postal elections, from inner suburban, outer suburban and regional areas, and covering a range of socio-economic variables. To achieve comparability, the VEC selected the same councils for the 2012 elections, though including all three wards in the cities of Ballarat and Whittlesea. The elections chosen were as follows:

| Council and Ward | Type of election | Geographic position | Percentage speaking a language other than English at home |
| --- | --- | --- | --- |
| Ballarat – Central, North and South Wards | Postal | Provincial | 5.7 |
| Casey – Mayfield Ward | Postal | Outer suburban | 32.6 |
| East Gippsland | Postal | Rural | 4.9 |
| Glen Eira – Camden Ward | Attendance | Middle suburban | 33.8 |
| Greater Dandenong – Red Gum Ward | Attendance | Middle/outer suburban | 62.2 |
| Macedon Ranges – West Ward | Postal | Peri-urban | 6.8 |
| Maroondah – Wyreena Ward | Postal | Outer suburban | 14.8 |
| Moreland – South Ward | Attendance | Inner suburban | 43.7 |
| Stonnington – North Ward | Attendance | Inner suburban | 25.7 |
| Whittlesea – North, South East and South West Wards | Postal | Outer suburban / peri-urban | 48.7 |

How-to-vote conformity in 2012

The following table shows the degree to which voters in the above elections complied with candidates’ how-to-vote instructions:

| Council | Total votes | Ballot papers following HTV instructions | Percentage |
| --- | --- | --- | --- |
| Ballarat - Central | 16,684 | 7,300 | 43.8% |
| Ballarat - North | 19,247 | 8,567 | 44.5% |
| Ballarat - South | 18,912 | 7,517 | 39.8% |
| Casey - Mayfield | 19,280 | 8,412 | 43.6% |
| East Gippsland | 27,679 | 11,916 | 43.1% |
| Glen Eira - Camden | 18,861 | 7,480 | 39.7% |
| Greater Dandenong – Red Gum | 13,482 | 3,489 | 25.9% |
| Macedon Ranges - West | 8,087 | 3,074 | 38.0% |
| Maroondah - Wyreena | 18,398 | 9,451 | 51.4% |
| Moreland - South | 13,728* | 5,466 | 39.8% |
| Stonnington - North | 12,068* | 4,617 | 38.3% |
| Whittlesea - North | 20,749 | 9,732 | 46.9% |
| Whittlesea - South East | 30,617* | 15,036 | 49.1% |
| Whittlesea - South West | 27,683* | 11,588 | 41.9% |
| TOTAL | 265,475 | 114,583 | 42.8% |

* Total votes for candidates indicating preferences

Somewhat fewer than half of the voters surveyed followed their first chosen candidates’ directions. Those directions clearly had a strong influence on the results of the elections, but over half the voters made up their own minds on the allocation of preferences. How-to-vote conformity ranged from 25.9% in Greater Dandenong to 51.4% in Maroondah, with eight of the 14 elections having a conformity rate in the 40s.

To what extent did factors such as the type of election and the nature of the area affect voters’ responses? The following table compares how-to-vote conformity in postal elections with that in attendance elections. Substantially more voters in postal elections followed how-to-vote instructions. The explanation probably relates to the nature of the elections. In postal elections, all voters receive candidates’ preference indications (where submitted), and have plenty of time to peruse them. By contrast, candidates in attendance elections are not necessarily able to distribute their how-to-cards to all voters.

| Election type | Total votes | Ballot papers following HTV instructions | Percentage |
| --- | --- | --- | --- |
| Attendance | 58,139 | 21,052 | 36.2% |
| Postal | 207,336 | 92,593 | 44.7% |

Nine of the elections examined were in the Melbourne metropolitan area, and five were in regional areas. Regional councils tend to have a lower informal voting rate than metropolitan ones, and it might be conjectured that regional voters would also show a greater tendency to follow how-to-vote instructions. However, the table below shows that there was no real difference between metropolitan and rural elections.

| Area | Total votes | Ballot papers following HTV instructions | Percentage |
| --- | --- | --- | --- |
| Metropolitan | 174,866 | 75,271 | 43.0% |
| Regional | 90,609 | 38,374 | 42.4% |

Councils with high proportions of residents speaking a language other than English (LOTE) tend to have higher informal voting rates than councils with low proportions of LOTE speakers. Does this also apply to how-to-vote conformity? The table below shows no real difference: voters in local government areas with few LOTE speakers were no more likely to follow how-to-vote directions than voters in areas where LOTE speakers were concentrated.

| LOTE speakers | Total votes | Ballot papers following HTV instructions | Percentage |
| --- | --- | --- | --- |
| > 40% of residents | 106,259 | 45,311 | 42.6% |
| < 10% of residents | 90,609 | 38,374 | 42.4% |

The elections examined mostly had large numbers of candidates. The informal voting rate tends to increase with the number of candidates, and it might be expected that voters’ ability to follow how-to-vote instructions would decline as the number of candidates increases. The following table shows the number of number of candidates for each election and the percentage compliance with how-to-vote instructions. When these two variables were compared, there was a fairly weak positive correlation coefficient of .4089 – which means that the more candidates there were, the more likely voters were to follow how-to-vote instructions. Possibly a large field of candidates is so intimidating to some voters that they turn to how-to-vote instructions as a guide.

| Council/Ward | Number of candidates | Percentage of ballot papers following HTV instructions |
| --- | --- | --- |
| Ballarat - Central | 8 | 43.8% |
| Ballarat - North | 6 | 44.55 |
| Ballarat - South | 8 | 39.7% |
| Casey - Mayfield | 14 | 43.6% |
| East Gippsland | 17 | 43.1% |
| Glen Eira - Camden | 11 | 39.7% |
| Greater Dandenong – Red Gum | 11 | 25.9% |
| Macedon Ranges - West | 6 | 38% |
| Maroondah - Wyreena | 14 | 51.4% |
| Moreland - South | 8 | 39.8% |
| Stonnington - North | 15 | 38.3% |
| Whittlesea - North | 11 | 46.9 |
| Whittlesea - South East | 22 | 49.1% |
| Whittlesea - South West | 15 | 43.2% |

It is also possible to examine how voters for individual candidates behaved. Compliance with candidates’ how-to-vote instructions ranged from none at all (for Peter Cooke in Stonnington, who probably did not distribute any how-to-vote cards) to 57% (for Les Willmott in Maroondah). In Stonnington, a non-candidate, Ms Annabel Clayton, registered a how-to-vote card giving a first preference to Jami Klisaris, but only 33 voters followed her advised order of preferences. Political parties were active in some of the elections, and members of parties stood as candidates, but as the LG Act does not recognise political parties, the VEC has no information to identify party candidates. However, it is possible to identify incumbent councillors, winning candidates and candidates who did not receive a refund of their deposit because they obtained less than 4% of the vote. A reasonable hypothesis is that incumbent councillors would have achieved some recognition during their term and that voters would be more likely to follow their how-to-vote instructions. The same could apply to winning candidates, who by definition had popular support. The following table shows how-to-vote conformity by council for different categories of candidate.

| Council | Percentage of ballot papers following HTV instructions |
| --- | --- |
|  | Incumbent councillors | Winning candidates | Non-deposit candidates | All candidates |
| Ballarat - Central | 43.8% | 47.1% | 34.8% | 43.8% |
| Ballarat - North | 45.5% | 46.5% |  | 44.5% |
| Ballarat - South | 42.5% | 42.3% | 28.3% | 39.7% |
| Casey - Mayfield | 51% | 48.8% | 32.2% | 43.6% |
| East Gippsland | 44.2% | 43.9% | 40.9% | 43.1% |
| Glen Eira - Camden | 38.8% | 44.1% | 20.5% | 39.7% |
| Greater Dandenong – Red Gum | 31.5% | 31.2% | 2.8% | 25.9% |
| Macedon Ranges - West | 37.5% | 39.3% |  | 38% |
| Maroondah - Wyreena | 54.5% | 53.9% | 45% | 51.4% |
| Moreland - South | 50.3% | 42.2% |  | 39.8% |
| Stonnington - North | 32% | 36.3% | 27.5% | 38.3% |
| Whittlesea - North | 55% | 52.2% | 34.6% | 46.9% |
| Whittlesea - South East | 57.7% | 57% | 38.8% | 49.1% |
| Whittlesea - South West | 49.4% | 46.5% | 34.7% | 41.9% |
| TOTAL | 46.9% | 46.2% | 36.5% | 42.8% |

The results confirm that voters for incumbent councillors and winning candidates were more inclined than average to follow how-to-vote instructions, and voters for minor candidates were much less inclined to follow instructions. These tendencies were particularly strong in the attendance elections, probably because councillors, winning candidates and their helpers were able to hand out how-to-vote cards to voters entering voting centres, while many of the minor candidates did not do so consistently.

Comparison with 2008

The table below shows the changes in how-to-vote conformity between the 2008 and 2012 elections.

| Council/Ward | Conforming votes 2008 (%) | Conforming votes 2012 (%) | Percentage point change |
| --- | --- | --- | --- |
| Ballarat - Central | 43 | 44 | +1 |
| Casey - Mayfield | 42 | 44 | +2 |
| East Gippsland | 45 | 43 | -2 |
| Glen Eira - Camden | 43 | 40 | -3 |
| Greater Dandenong – Red Gum | 35 | 26 | -9 |
| Macedon Ranges - West | 46 | 38 | -8 |
| Maroondah - Wyreena | 55 | 51 | -4 |
| Moreland - South | 42 | 40 | -2 |
| Stonnington - North | 50 | 38 | -12 |
| Whittlesea – East/South East | 49 | 49 | - |
| TOTAL | 45 | 43 | -2 |

Overall, and in most councils, there was very little change from 2008 to 2012. The rate of how-to-vote conformity declined more in attendance elections, at an average rate of 4.7 percentage points compare to 1.8 percentage points in postal elections. In Stonnington City Council, which switched from a postal election in 2008 to attendance in 2012, the rate of how-to-vote conformity declined by 12 percentage points, from 50% to 38%. It appears that how-to-vote cards in attendance elections are increasingly ineffective in directing voters, while there is little variation in the efficacy of the candidates’ directions in the ballot packs posted to all voters in postal elections.

Donkey votes

A donkey vote is a vote cast by a voter who numbers the squares down the ballot paper, without caring about the nature of the candidates on offer. Candidates are pleased if they get the top spot on the ballot paper when the draw for positions takes place, because they will have the advantage of the donkey vote. The size of the donkey vote has been a matter for discussion.

It is possible to measure the donkey vote for these elections. None of the lead candidates for each election advised a vote straight down the ballot paper. Although it is necessary to allow for random variation, its effects were very small in these elections. The number of possible combinations increases exponentially with the number of candidates; with six candidates, there are 720 possible orders of preferences; with eight candidates, there are 40,320 possible combinations; and with 11 candidates, there are 39,916,800 combinations. In the table below, the proportion of the donkey vote attributable to random variation has been subtracted for the election with six candidates (Ballarat’s North Ward).

| Council/Ward | Donkey votes | Percentage of total votes |
| --- | --- | --- |
| Ballarat - Central | 220 | 1.32% |
| Ballarat - North | 359 | 1.73%* |
| Ballarat - South | 279 | 1.48% |
| Casey - Mayfield | 415 | 2.15% |
| East Gippsland | 222 | 0.80% |
| Glen Eira - Camden | 185 | 0.98% |
| Greater Dandenong - Red Gum | 207 | 1.54% |
| Macedon Ranges - West | 134 | 1.66% |
| Maroondah - Wyreena | 252 | 1.37% |
| Moreland - South | 335 | 2.19% |
| Stonnington - North | 476 | 3.84% |
| Whittlesea - North | 239 | 1.15% |
| Whittlesea - South East | 400 | 1.28% |
| Whittlesea - South West | 411 | 1.44% |
| Total | 4,134 | 1.54% |

* Amount attributable to random variation (0.14%) subtracted

Across all the elections examined, donkey votes comprised 1.54% of all first preference votes, and the median rate for the elections was 1.46%. This is a remarkably low rate considering that political parties are not indicated on the ballot papers and that there were frequent complaints concerning lack of information about candidates.

There was no apparent relationship between the number of candidates and the donkey vote, with a correlation between them of -.0229. The rate of donkey voting was slightly higher in attendance elections (2% of the total) than in postal elections (1.4%). It was also higher than average (1.85%) in the six elections where the lead candidate was successful. In each case, the winning candidate’s margin over the next candidate was substantially greater than the number of donkey votes they received. It may be that, rather than donkey votes helping these candidates over the line, these candidates attracted some of the donkey votes to them. Some of the donkey voters may have recognised these candidates and voted for them, though without bothering to follow their preference directions.

It is also possible to measure “reverse donkey” votes, where voters numbered up the ballot paper instead of down it. As the following table shows, the number of reverse donkey votes was insignificant in every council except Moreland.

| Council/Ward | Reverse donkey votes | Percentage of total votes |
| --- | --- | --- |
| Ballarat - Central | 34 | 0.2% |
| Casey - Mayfield | 32 | 0.17% |
| East Gippsland | 34 | 0.12% |
| Glen Eira - Camden | 112 | 0.59% |
| Macedon Ranges - West | 27 | 0.33% |
| Moreland - South | 193 | 1.26% |
| Stonnington - North | 64 | 0.52% |
| Whittlesea - North | 40 | 0.19% |
| Whittlesea - South East | 99 | 0.32% |
| Whittlesea - South West | 83 | 0.29% |
| Total | 718 | 0.36% |

Appendix 6: Sample ballot pack

Appendix 7: Sample EasyVote letter

Appendix 8: Sample State-wide advertising

Enrol

Braille and large print ballot papers

Update your address

Look in the mail

Elections (regional papers)

Elections (regional papers)

Appendix 9: Sample Council-specific advertising

Notice of entitlement (statutory)

Notice of election (statutory)

Voting details – Postal elections (statutory)

Voting details – Attendance elections (statutory)

Voting reminder – Postal elections (non-statutory)

Voting reminder – Attendance elections (non-statutory)

Notice of results (statutory)

Appendix 10: Sample uncontested election leaflet

Appendix 11: Number of enquiry calls received at election offices during the election period

| Council | 3-14 Sept | 17-21 Sept | 24-28 Sept | 1-5 Oct | 8-12 Oct | 15-19 Oct | 22-26 Oct | Election day | 29 Oct-2 Nov | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Melbourne City Council | 13 | 49 | 74 | 92 | 421 | 1339 | 1372 | 0 | 0 | 3360 |
| Alpine Shire Council |  | 36 | 44 | 53 | 84 | 164 | 209 | 0 | 0 | 590 |
| Ararat Rural City Council |  | 21 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 30 |
| Ballarat City Council |  | 17 | 58 | 45 | 224 | 627 | 611 | 0 | 0 | 1582 |
| Banyule City Council |  | 102 | 244 | 283 | 363 | 1217 | 1203 | 77 | 0 | 3489 |
| Bass Coast Shire Council |  | 52 | 31 | 75 | 271 | 420 | 608 | 0 | 0 | 1457 |
| Baw Baw Shire Council |  | 41 | 17 | 40 | 146 | 271 | 283 | 0 | 0 | 798 |
| Bayside City Council |  | 34 | 45 | 72 | 416 | 903 | 1038 | 0 | 0 | 2508 |
| Benalla Rural City Council |  | 20 | 19 | 15 | 54 | 105 | 94 | 0 | 0 | 307 |
| Boroondara City Council |  | 69 | 140 | 124 | 607 | 1114 | 1565 | 0 | 0 | 3619 |
| Borough of Queenscliffe Council |  | 7 | 13 | 10 | 34 | 55 | 80 | 0 | 1 | 200 |
| Buloke Shire Council |  | 14 | 26 | 16 | 29 | 49 | 54 | 0 | 0 | 188 |
| Campaspe Shire Council |  | 26 | 33 | 33 | 82 | 154 | 164 | 0 | 0 | 492 |
| Cardinia Shire Council |  | 13 | 43 | 53 | 238 | 708 | 932 | 0 | 0 | 1987 |
| Casey City Council |  | 121 | 157 | 211 | 1483 | 2114 | 2260 | 0 | 0 | 6346 |
| Central Goldfields Shire Council |  | 51 | 43 | 22 | 74 | 172 | 131 | 0 | 0 | 493 |
| Colac Otway Shire Council |  | 16 | 15 | 28 | 50 | 112 | 152 | 0 | 0 | 373 |
| Corangamite Shire Council |  | 12 | 11 | 18 | 33 | 77 | 102 | 0 | 0 | 253 |
| Darebin City Council |  | 77 | 106 | 78 | 416 | 1327 | 1546 | 0 | 0 | 3550 |
| East Gippsland Shire Council |  | 31 | 56 | 58 | 174 | 346 | 428 | 0 | 0 | 1093 |
| Frankston City Council |  | 35 | 69 | 64 | 508 | 1067 | 1050 | 0 | 0 | 2793 |
| Gannawarra Shire Council |  | 21 | 45 | 26 | 46 | 73 | 81 | 0 | 0 | 292 |
| Glen Eira City Council |  | 82 | 264 | 254 | 405 | 2530 | 1235 | 104 | 151 | 5025 |
| Glenelg Shire Council |  | 27 | 54 | 52 | 70 | 166 | 187 | 0 | 0 | 556 |
| Golden Plains Shire Council |  | 33 | 54 | 41 | 127 | 205 | 300 | 0 | 3 | 763 |
| Greater Bendigo City Council |  | 38 | 67 | 82 | 430 | 712 | 933 | 0 | 0 | 2262 |
| Greater Dandenong City Council |  | 5 | 158 | 254 | 301 | 1388 | 1285 | 86 | 0 | 3477 |
| Greater Geelong City Council |  | 111 | 232 | 225 | 1065 | 2666 | 2143 | 0 | 177 | 6619 |
| Greater Shepparton City Council |  | 58 | 130 | 109 | 255 | 649 | 643 | 0 | 0 | 1844 |
| Hepburn Shire Council |  | 4 | 11 | 9 | 46 | 126 | 122 | 0 | 0 | 318 |
| Hindmarsh Shire Council |  | 14 | 30 | 22 | 33 | 64 | 100 | 0 | 0 | 263 |
| Hobsons Bay City Council |  | 29 | 78 | 95 | 555 | 929 | 920 | 0 | 36 | 2642 |
| Horsham Rural City Council |  | 45 | 94 | 66 | 101 | 197 | 303 | 0 | 0 | 806 |
| Hume City Council |  | 88 | 201 | 194 | 514 | 1050 | 986 | 0 | 0 | 3033 |
| Indigo Shire Council |  | 19 | 26 | 27 | 46 | 117 | 170 | 0 | 0 | 405 |
| Kingston City Council |  | 95 | 138 | 100 | 564 | 1559 | 1215 | 0 | 0 | 3671 |
| Knox City Council |  | 85 | 86 | 230 | 359 | 1536 | 0 | 0 | 0 | 2296 |
| Latrobe City Council |  | 26 | 41 | 81 | 198 | 405 | 0 | 0 | 0 | 751 |
| Loddon Shire Council |  | 3 | 6 | 7 | 41 | 67 | 88 | 0 | 0 | 212 |
| Macedon Ranges Shire Council |  | 58 | 44 | 44 | 172 | 360 | 491 | 0 | 0 | 1169 |
| Manningham City Council |  | 66 | 104 | 103 | 560 | 1087 | 1078 | 0 | 79 | 3077 |
| Mansfield Shire Council |  | 16 | 18 | 14 | 49 | 92 | 84 | 0 | 0 | 273 |
| Maribyrnong City Council |  | 67 | 109 | 95 | 260 | 548 | 747 | 0 | 0 | 1826 |
| Maroondah City Council |  | 51 | 68 | 63 | 450 | 828 | 1067 | 0 | 42 | 2569 |
| Melton City Council |  | 92 | 155 | 103 | 376 | 1014 | 1251 | 0 | 105 | 3096 |
| Mildura Rural City Council |  | 15 | 37 | 33 | 130 | 331 | 357 | 0 | 0 | 903 |
| Mitchell Shire Council |  | 32 | 48 | 20 | 139 | 260 | 233 | 0 | 0 | 732 |
| Moira Shire Council |  | 72 | 87 | 107 | 169 | 333 | 425 | 0 | 0 | 1193 |
| Monash City Council |  | 36 | 74 | 82 | 428 | 1182 | 1497 | 0 | 25 | 3324 |
| Moonee Valley City Council |  | 0 | 42 | 52 | 523 | 792 | 983 | 0 | 0 | 2392 |
| Moorabool Shire Council |  | 6 | 17 | 15 | 72 | 202 | 198 | 0 | 0 | 510 |
| Moreland City Council |  | 84 | 126 | 200 | 317 | 562 | 981 | 0 | 0 | 2270 |
| Mornington Peninsula Shire Council |  | 77 | 222 | 225 | 1055 | 1780 | 1858 | 0 | 97 | 5314 |
| Mount Alexander Shire Council |  | 73 | 62 | 33 | 105 | 245 | 187 | 0 | 0 | 705 |
| Moyne Shire Council |  | 10 | 26 | 20 | 54 | 87 | 98 | 0 | 0 | 295 |
| Murrindindi Shire Council |  | 16 | 23 | 10 | 70 | 133 | 117 | 0 | 0 | 369 |
| Nillumbik Shire Council |  | 25 | 59 | 30 | 189 | 422 | 175 | 0 | 0 | 900 |
| Northern Grampians Shire Council |  | 62 | 59 | 58 | 54 | 91 | 106 | 0 | 0 | 430 |
| Port Phillip City Council |  | 32 | 46 | 64 | 106 | 1634 | 1139 | 60 | 0 | 3081 |
| Pyrenees Shire Council |  | 1 | 6 | 4 | 20 | 61 | 59 | 0 | 0 | 151 |
| South Gippsland Shire Council |  | 36 | 20 | 50 | 183 | 287 | 414 | 0 | 0 | 990 |
| Southern Grampians Shire Council |  | 22 | 44 | 43 | 54 | 133 | 150 | 0 | 0 | 446 |
| Stonnington City Council |  | 32 | 81 | 185 | 248 | 1442 | 1260 | 0 | 0 | 3248 |
| Strathbogie Shire Council |  | 15 | 16 | 11 | 44 | 85 | 79 | 0 | 0 | 250 |
| Surf Coast Shire Council |  | 59 | 97 | 76 | 236 | 385 | 558 | 0 | 5 | 1416 |
| Swan Hill Rural City Council |  | 32 | 74 | 41 | 74 | 120 | 133 | 0 | 0 | 474 |
| Towong Shire Council |  | 7 | 10 | 9 | 19 | 50 | 72 | 0 | 0 | 167 |
| Wangaratta Rural City Council |  | 69 | 80 | 100 | 159 | 309 | 394 | 0 | 0 | 1111 |
| Warrnambool City Council |  | 18 | 44 | 34 | 96 | 157 | 174 | 0 | 0 | 523 |
| Wellington Shire Council |  | 34 | 61 | 59 | 185 | 368 | 456 | 0 | 0 | 1163 |
| West Wimmera Shire Council |  | 10 | 24 | 14 | 25 | 50 | 80 | 0 | 0 | 203 |
| Whitehorse City Council |  | 46 | 67 | 80 | 545 | 1140 | 1044 | 0 | 0 | 2922 |
| Whittlesea City Council |  | 60 | 80 | 75 | 682 | 1111 | 1159 | 0 | 35 | 3202 |
| Wodonga City Council |  | 39 | 51 | 54 | 94 | 245 | 356 | 0 | 0 | 839 |
| Wyndham City Council |  | 59 | 102 | 84 | 504 | 1243 | 1411 | 0 | 0 | 3403 |
| Yarra City Council |  | 67 | 215 | 351 | 143 | 1395 | 855 | 0 | 103 | 3129 |
| Yarra Ranges Shire Council |  | 81 | 77 | 68 | 456 | 1026 | 1414 | 0 | 0 | 3122 |
| Yarriambiack Shire Council |  | 18 | 36 | 27 | 41 | 78 | 123 | 0 | 0 | 323 |

Appendix 12: Details of counting arrangements

| Municipality | Number of councillors | Electoral structure | Count type | Election Type |
| --- | --- | --- | --- | --- |
| Alpine | 7 | Unsubdivided | Computer PR | Postal |
| Ararat | 7 | Unsubdivided | Count not required | Postal |
| Ballarat | 9 | 3 three-Cr wards | Computer PR | Postal |
| Banyule | 7 | 7 single-Cr wards | Manual PD | Attendance |
| Bass Coast | 7 | 7 single-Cr wards | Manual PD | Postal |
| Baw Baw | 9 | 1 three-Cr ward, 3 two-Cr wards | Computer PR | Postal |
| Bayside | 7 | 1 three-Cr ward, 2 two-Cr wards | Computer PR | Postal |
| Benalla | 7 | Unsubdivided | Computer PR | Postal |
| Boroondara | 10 | 10 Single-Cr wards | Manual PD | Postal |
| Brimbank | No election until March 2015 |
| Buloke | 7 | 1 three-Cr ward, 2 two-Cr wards | Computer PR | Postal |
| Campaspe | 9 | 2 three-Cr wards, 3 single-Cr wards | Computer PR and Manual PD | Postal |
| Cardinia | 9 | 1 two-Cr ward, 1 three-Cr ward, 1 four-Cr ward | Computer PR | Postal |
| Casey | 11 | 1 single-Cr ward, 5 two-Cr wards | Computer PR and Manual PD | Postal |
| Central Goldfields | 7 | 3 single-Cr wards, 1 four-Cr ward | Computer PR and Manual PD | Postal |
| Colac Otway | 7 | Unsubdivided | Computer PR | Postal |
| Corangamite | 7 | 4 single-Cr wards, 1 three-Cr ward | Computer PR and Manual PD | Postal |
| Darebin | 9 | 3 three-Cr wards | Computer PR | Postal |
| East Gippsland | 9 | Unsubdivided | Computer PR | Postal |
| Frankston | 9 | 3 three-Cr wards | Computer PR | Postal |
| Gannawarra | 7 | 2 single-Cr wards, 1 two-Cr ward, 1 three-Cr ward | Manual PR and Manual PD | Postal |
| Glen Eira | 9 | 3 three-Cr wards | Computer PR | Attendance |
| Glenelg | 7 | Unsubdivided | Computer PR | Postal |
| Golden Plains | 7 | Unsubdivided | Computer PR | Postal |
| Greater Bendigo | 9 | 3 three-Cr wards | Computer PR | Postal |
| Greater Dandenong | 11 | 3 three-Cr wards, 1 two-Cr ward | Computer PR | Attendance |
| Greater Geelong | 1 + 12 | 1 Mayor, 12 single-Cr wards | Computer PD and Manual PD | Postal |
| Greater Shepparton | 7 | Unsubdivided | Computer PR | Postal |
| Hepburn | 7 | 2 two-Cr wards, 3 single-Cr wards | Computer PR and Manual PD | Postal |
| Hindmarsh | 6 | 3 two-Cr wards | Computer PR | Postal |
| Hobsons Bay | 7 | 2 two-Cr wards, 1 three Cr ward, | Computer PR | Postal |
| Horsham | 7 | Unsubdivided | Computer PR | Postal |
| Hume | 11 | 1 three-Cr ward, 2 four-Cr wards | Computer PR | Postal |
| Indigo | 7 | Unsubdivided | Computer PR | Postal |
| Kingston | 9 | 3 three-Cr wards | Computer PR | Postal |
| Knox | 9 | 9 single-Cr wards | Manual PD | Attendance |
| Latrobe | 9 | 1 single-Cr ward, 2 two-Cr wards, 1 four-Cr ward | Computer PR and Manual PD | Postal |
| Loddon | 5 | 5 single-Cr wards | Manual PD | Postal |
| Macedon Ranges | 9 | 3 three-Cr wards | Computer PR | Postal |
| Manningham | 9 | 3 three-Cr wards | Computer PR | Postal |
| Mansfield | 5 | 3 single-Cr wards, 1 two-Cr ward | Computer PR and Manual PD | Postal |
| Maribyrnong | 7 | 2 two-Cr wards, 1 three-Cr ward | Computer PR | Postal |
| Maroondah | 9 | 3 three-Cr wards | Computer PR | Postal |
| Melbourne | 2 + 9 | 1 Lord Mayor, 1 Deputy Lord Mayor 1 nine-Cr - unsubdivided | Computer PD and Computer PR | Postal |
| Melton | 7 | 1 three-Cr ward, 2 two-Cr wards | Computer PR | Postal |
| Mildura | 9 | Unsubdivided | Computer PR | Postal |
| Mitchell | 9 | 3 three-Cr wards | Computer PR | Postal |
| Moira | 9 | Unsubdivided | Computer PR | Postal |
| Monash | 11 | 1 two-Cr ward, 3 three-Cr wards | Computer PR | Postal |
| Moonee Valley | 9 | 3 three-Cr wards | Computer PR | Postal |
| Moorabool | 7 | 3 single-Cr wards, 1 four-Cr ward | Computer PR and Manual PD | Postal |
| Moreland | 11 | 1 three-Cr ward, 2 four-Cr wards | Computer PR | Attendance |
| Mornington Peninsula | 11 | 3 single-Cr wards, 1 two-Cr ward, 2 three-Cr wards | Computer PR and Manual PD | Postal |
| Mount Alexander | 7 | 4 single-Cr wards, 1 three-Cr ward | Computer PR and Manual PD | Postal |
| Moyne | 7 | Unsubdivided | Computer PR | Postal |
| Murrindindi | 7 | 7 single-Cr wards | Manual PD | Postal |
| Nillumbik | 7 | 7 single-Cr wards | Manual PD | Postal |
| Northern Grampians | 7 | 2 single-Cr wards, 1 two-Cr ward, 1 three-Cr ward | Computer PR and Manual PD | Postal |
| Port Phillip | 7 | 7 single-Cr wards | Manual PD | Attendance |
| Pyrenees | 5 | 5 single-Cr wards | Manual PD | Postal |
| Queenscliffe | 5 | Unsubdivided | Computer PR | Postal |
| South Gippsland | 9 | 3 three-Cr wards | Computer PR | Postal |
| Southern Grampians | 7 | Unsubdivided | Computer PR | Postal |
| Stonnington | 9 | 3 three-Cr wards | Computer PR | Attendance |
| Strathbogie | 7 | 3 single-Cr wards, 2 two-Cr wards | Computer PR and Manual PD | Postal |
| Surf Coast | 9 | 1 single-Cr ward, 2 two-Cr wards, 1 four-Cr ward | Computer PR and Manual PD | Postal |
| Swan Hill | 7 | 3 single-Cr wards, 1 four-Cr ward | Computer PR and Manual PD | Postal |
| Towong | 5 | Unsubdivided | Computer PR | Postal |
| Wangaratta | 7 | Unsubdivided | Computer PR | Postal |
| Warrnambool | 7 | Unsubdivided | Computer PR | Postal |
| Wellington | 9 | Unsubdivided | Computer PR | Postal |
| West Wimmera | 5 | Unsubdivided | Computer PR | Postal |
| Whitehorse | 10 | 5 two-Cr wards | Computer PR | Postal |
| Whittlesea | 11 | 1 three-Cr ward, 2 four-Cr wards | Computer PR | Postal |
| Wodonga | 7 | Unsubdivided | Computer PR | Postal |
| Wyndham | 11 | 1 three-Cr ward, 2 four-Cr wards | Computer PR | Postal |
| Yarra | 9 | 3 three-Cr wards | Computer PR | Attendance |
| Yarra Ranges | 9 | 9 single-Cr wards | Manual PD | Postal |
| Yarriambiack | 7 | 2 two-Cr wards, 1 three-Cr ward | Computer PR | Postal |

PD = Preference Distribution

PR = Proportional Representation

Appendix 13: Dates of declarations of results

| Municipality | Declaration date and time |
| --- | --- |
| Ararat Rural City Council (u) | 12 noon on Saturday, 27 October 2012 |
| Murrindindi Shire Council | 4.30 pm on Saturday, 27 October 2012 |
| Loddon Shire Council | 6.00 pm on Saturday, 27 October 2012 |
| Hindmarsh Shire Council | 7.00 pm on Saturday, 27 October 2012 |
| West Wimmera Shire Council | 7.00 pm on Saturday, 27 October 2012 |
| Mansfield Shire Council | 7.15 pm on Saturday, 27 October 2012 |
| Strathbogie Shire Council | 8.00 pm on Saturday, 27 October 2012 |
| Bass Coast Shire Council | 10.00 am on Sunday, 28 October 2012 |
| Wellington Shire Council | 10.00 am on Sunday, 28 October 2012 |
| Yarriambiack Shire Council | 10.00 am on Sunday, 28 October 2012 |
| Glenelg Shire Council | 11.00 am on Sunday, 28 October 2012 |
| Indigo Shire Council | 11.00 am on Sunday, 28 October 2012 |
| Southern Grampians Shire Council | 11.00 am on Sunday, 28 October 2012 |
| Gannawarra Shire Council | 12 noon on Sunday, 28 October 2012 |
| Pyrenees Shire Council | 12 noon on Sunday, 28 October 2012 |
| Towong Shire Council | 2.00 pm on Sunday, 28 October 2012 |
| Northern Grampians Shire Council | 2.00 pm on Sunday, 28 October 2012 |
| Benalla Rural City Council | 3.00 pm on Sunday, 28 October 2012 |
| Central Goldfields Shire Council | 3.00 pm on Sunday, 28 October 2012 |
| Buloke Shire Council | 4.00 pm on Sunday, 28 October 2012 |
| Corangamite Shire Council | 4.00 pm on Sunday, 28 October 2012 |
| Horsham Rural City Council | 5.00 pm on Sunday, 28 October 2012 |
| Swan Hill Rural City Council (r) | 5.00 pm on Sunday, 28 October 2012 |
| Mount Alexander Shire Council | 5.00 pm on Sunday, 28 October 2012 |
| Boroondara City Council | 6.00 pm on Sunday, 28 October 2012 |
| Yarra Ranges Shire Council | 6.00 pm on Sunday, 28 October 2012 |
| Nillumbik Shire Council | 8.00 pm on Sunday, 28 October 2012 |
| Mornington Peninsula Shire Council | 8.30 pm on Sunday, 28 October 2012 |
| Manningham City Council | 10.00 pm on Sunday, 28 October 2012 |
| Hepburn Shire Council | 9.00 am on Monday, 29 October 2012 |
| Baw Baw Shire Council | 9.00 am on Monday, 29 October 2012 |
| Wangaratta Rural City Council | 9.00 am on Monday, 29 October 2012 |
| Maribyrnong City Council | 9.00 am on Monday, 29 October 2012 |
| Wodonga City Council | 9.00 am on Monday, 29 October 2012 |
| Ballarat City Council | 9.30 am on Monday, 29 October 2012 |
| Moorabool Shire Council | 10.00 am on Monday, 29 October 2012 |
| South Gippsland Shire Council | 10.00 am on Monday, 29 October 2012 |
| Surf Coast Shire Council | 10.00 am on Monday, 29 October 2012 |
| Whitehorse City Council | 10.00 am on Monday, 29 October 2012 |
| Maroondah City Council | 10.00 am on Monday, 29 October 2012 |
| Alpine Shire Council (r) | 10.00 am on Monday, 29 October 2012 |
| East Gippsland Shire Council | 10.00 am on Monday, 29 October 2012 |
| Mildura Rural City Council | 10.00 am on Monday, 29 October 2012 |
| Moyne Shire Council | 10.00 am on Monday, 29 October 2012 |
| Borough of Queenscliffe Council | 10.30 am on Monday, 29 October 2012 |
| Moira Shire Council | 10.30 am on Monday, 29 October 2012 |
| Melton City Council | 11.00 am on Monday, 29 October 2012 |
| Latrobe City Council | 12 noon on Monday, 29 October 2012 |
| Mitchell Shire Council | 1.00 pm on Monday, 29 October 2012 |
| Greater Bendigo City Council | 2.00 pm on Monday, 29 October 2012 |
| Greater Shepparton City Council | 3.00 pm on Monday, 29 October 2012 |
| Macedon Ranges Shire Council (East & West Wards) | 4.00 pm on Monday, 29 October 2012 |
| Port Phillip City Council | 4.00 pm on Monday, 29 October 2012 |
| Cardinia Shire Council | 4.00 pm on Monday, 29 October 2012 |
| Warrnambool City Council | 5.00 pm on Monday, 29 October 2012 |
| Moonee Valley City Council | 5.00 pm on Monday, 29 October 2012 |
| Knox City Council (r) | 5.00 pm on Monday, 29 October 2012 |
| Wyndham City Council | 5.30 pm on Monday, 29 October 2012 |
| Yarra City Council | 5.30 pm on Monday, 29 October 2012 |
| Bayside City Council | 6.00 pm on Monday, 29 October 2012 |
| Colac Otway Shire Council | 6.00 pm on Monday, 29 October 2012 |
| Frankston City Council | 6.00 pm on Monday, 29 October 2012 |
| Hobsons Bay City Council | 6.00 pm on Monday, 29 October 2012 |
| Banyule City Council | 7.00 pm on Monday, 29 October 2012 |
| Darebin City Council | 7.00 pm on Monday, 29 October 2012 |
| Monash City Council | 7.00 pm on Monday, 29 October 2012 |
| Glen Eira City Council | 9.00 am on Tuesday, 30 October 2012 |
| Hume City Council | 9.00 am on Tuesday, 30 October 2012 |
| Greater Dandenong City Council | 10.00 am on Tuesday, 30 October 2012 |
| Melbourne City Council | 10.00 am on Tuesday, 30 October 2012 |
| Stonnington City Council | 10.00 am on Tuesday, 30 October 2012 |
| Golden Plains Shire Council (r) | 11.00 am on Tuesday, 30 October 2012 |
| Campaspe Shire Council | 3.00 pm on Tuesday, 30 October 2012 |
| Macedon Ranges Shire Council (South Ward) (r) | 5.00 pm on Tuesday, 30 October 2012 |
| Whittlesea City Council | 6.00 pm on Tuesday, 30 October 2012 |
| Kingston City Council | 6.00 pm on Tuesday, 30 October 2012 |
| Greater Geelong City Council | 9.00 am on Tuesday, 31 October 2012 |
| Casey City Council | 6.00 pm on Wednesday, 31 October 2012 |
| Moreland City Council (North West and South Wards) | 6.00 pm on Wednesday, 31 October 2012 |
| Moreland City Council (North East Ward) (r) | 7.05 pm on Friday, 2 November 2012 |

(r) recount conducted

(u) entirely uncontested

Appendix 14: Election details

| Council U= uncontested | Electorate | Elected | Number of vacancies | Number of candidates | % Voter turnout | % Informality rate | Number of electors | How-to-vote cards registered |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Alpine Shire Council 2012 - Postal | Unsubdivided |  | 7 | 13 | 75.64% | 3.93% | 11524 |  |
|  |  | ROPER, Peter |  |  |  |  |  |  |
|  |  | KEEBLE, Tony |  |  |  |  |  |  |
|  |  | JANAS, Ron |  |  |  |  |  |  |
|  |  | VONARX, Jan |  |  |  |  |  |  |
|  |  | FARRELL, Kate |  |  |  |  |  |  |
|  |  | FORSYTH, John |  |  |  |  |  |  |
|  |  | PEARCE, Daryl |  |  |  |  |  |  |
| Ararat Rural City Council 2012 – Postal [U] | Unsubdivided |  | 7 | 7 | 0.00% | 0.00% | 9081 |  |
|  |  | WOODS, Murray Winston |  |  |  |  |  |  |
|  |  | HULL, Fay |  |  |  |  |  |  |
|  |  | ALLGOOD, Gwenda Mary |  |  |  |  |  |  |
|  |  | HULL, Gary |  |  |  |  |  |  |
|  |  | McKENZIE, Colin |  |  |  |  |  |  |
|  |  | HARRIS, Ian George |  |  |  |  |  |  |
|  |  | WILSON, Ian Francis |  |  |  |  |  |  |
| Ballarat City Council 2012 - Postal |  |  | 9 | 22 | 77.51% | 2.70% | 72725 |  |
|  | Central Ward | McINTOSH, Samantha | 3 | 8 | 75.22% | 2.79% | 22818 |  |
|  |  | BURT, John Charles |  |  |  |  |  |  |
|  |  | COATES, Belinda |  |  |  |  |  |  |
|  | North Ward | COLTMAN, Vicki | 3 | 6 | 79.57% | 2.47% | 24803 |  |
|  |  | PHILIPS, John |  |  |  |  |  |  |
|  |  | JOHNSON, Amy |  |  |  |  |  |  |
|  | South Ward | HUDSON, Des | 3 | 8 | 77.55% | 2.86% | 25104 |  |
|  |  | MORRIS, Joshua |  |  |  |  |  |  |
|  |  | INNES, Peter |  |  |  |  |  |  |
| Banyule City Council 2012 - Attendance |  |  | 7 | 38 | 70.74% | 7.78% | 79172 | 68 |
|  | Bakewell Ward | DI PASQUALE, Mark | 1 | 9 | 70.57% | 11.12% | 12254 | 15 |
|  | Beale Ward | PHILLIPS, Wayne | 1 | 2 | 75.64% | 5.19% | 13336 | 3 |
|  | Griffin Ward | MULHOLLAND, Jenny | 1 | 8 | 69.18% | 7.13% | 13567 | 16 |
|  | Grimshaw Ward | GAROTTI, Rick | 1 | 7 | 71.20% | 8.83% | 13182 | 14 |
|  | Hawdon Ward | BRIFFA, Steven | 1 | 5 | 73.27% | 6.76% | 13678 | 10 |
|  | Ibbott Ward [U] | MELICAN, Tom | 1 | 1 | N/A | N/A | 0 | 0 |
|  | Olympia Ward | LANGDON, Craig | 1 | 6 | 64.45% | 8.21% | 13155 | 10 |
| Bass Coast Shire Council 2012 - Postal |  |  | 7 | 26 | 71.13% | 2.00% | 40887 |  |
|  | Anderson Ward | DREW, Bradley | 1 | 3 | 71.61% | 2.28% | 5889 |  |
|  | Churchill Ward | WRIGHT, Phil | 1 | 3 | 66.94% | 2.31% | 5296 |  |
|  | Hovell Ward | RANKINE, Neil | 1 | 4 | 72.80% | 1.54% | 5441 |  |
|  | Leadbeater Ward | LE SERVE, Clare | 1 | 5 | 72.34% | 2.58% | 5527 |  |
|  | McHaffie Ward | BROWN, Kimberley | 1 | 4 | 71.01% | 1.80% | 5789 |  |
|  | Thompson Ward | PHILLIPS, Andrew | 1 | 3 | 69.22% | 1.99% | 6526 |  |
|  | Townsend Ward | CRUGNALE, Jordan | 1 | 4 | 73.73% | 1.58% | 6419 |  |
| Baw Baw Shire Council 2012 - Postal |  |  | 9 | 26 | 77.28% | 2.83% | 34853 |  |
|  | Drouin Ward | JONES, Tricia | 2 | 5 | 71.36% | 2.35% | 8006 |  |
|  |  | WILLIAMSON, Terry |  |  |  |  |  |  |
|  | Mount Worth Ward | COOK, Murray | 2 | 6 | 79.81% | 2.33% | 7901 |  |
|  |  | HARRINGTON, Bill |  |  |  |  |  |  |
|  | North Ward | BALFOUR, David | 2 | 4 | 78.08% | 3.16% | 7861 |  |
|  |  | BROWN, Deborah Mary |  |  |  |  |  |  |
|  | Warragul Ward | GAUCI, Joe | 3 | 11 | 79.19% | 3.27% | 11085 |  |
|  |  | MURPHY, Gerard |  |  |  |  |  |  |
|  |  | POWER, Mikaela |  |  |  |  |  |  |
| Bayside City Council 2012 - Postal |  |  | 7 | 48 | 70.22% | 6.33% | 71176 |  |
|  | Central Ward | LONG, James | 3 | 20 | 69.54% | 7.53% | 29467 |  |
|  |  | HARTNEY, Stephen |  |  |  |  |  |  |
|  |  | FREDERICO, Felicity |  |  |  |  |  |  |
|  | Northern Ward | HEFFERNAN, Michael John | 2 | 16 | 68.37% | 5.90% | 21007 |  |
|  |  | DEL PORTO, Alex |  |  |  |  |  |  |
|  | Southern Ward | STEWART, Heather | 2 | 12 | 73.08% | 5.12% | 20702 |  |
|  |  | EVANS, Laurence |  |  |  |  |  |  |
| Benalla Rural City Council 2012 - Postal |  |  | 7 | 9 | 78.87% | 3.80% | 11335 |  |
|  | Benalla Rural City Council | KING, Justin R. | 7 | 9 | 78.87% | 3.80% | 11335 |  |
|  |  | DAVIS, Peter |  |  |  |  |  |  |
|  |  | DUNN, Peter |  |  |  |  |  |  |
|  |  | JENKINS, Ross |  |  |  |  |  |  |
|  |  | MARTIN, Suzy |  |  |  |  |  |  |
|  |  | ALEXANDER, Barbara |  |  |  |  |  |  |
|  |  | RICHARDS, Margaret |  |  |  |  |  |  |
| Boroondara City Council 2012 - Postal |  |  | 10 | 37 | 71.27% | 2.99% | 122821 |  |
|  | Bellevue Ward | PARKE, Jim | 1 | 4 | 76.02% | 2.44% | 11791 |  |
|  | Cotham Ward | VOCE, Judith | 1 | 5 | 73.77% | 3.51% | 12244 |  |
|  | Gardiner Ward | ROSS, Coral | 1 | 4 | 69.93% | 2.61% | 12145 |  |
|  | Glenferrie Ward | HURD, Steve | 1 | 3 | 58.87% | 2.54% | 13129 |  |
|  | Junction Ward | WEGMAN, Jack | 1 | 2 | 67.82% | 3.61% | 12564 |  |
|  | Lynden Ward | KREUTZ, Heinz | 1 | 2 | 75.88% | 3.29% | 12216 |  |
|  | Maling Ward | ADDIS, Jane | 1 | 6 | 73.93% | 2.93% | 12226 |  |
|  | Maranoa Ward | MALLIS, Philip | 1 | 2 | 74.10% | 3.19% | 11851 |  |
|  | Solway Ward | CHOW, Kevin | 1 | 7 | 76.87% | 2.40% | 12400 |  |
|  | Studley Ward | HEALEY, Phillip | 1 | 2 | 66.73% | 3.35% | 12255 |  |
| Borough of Queenscliffe Council 2012 – Postal | Unsubdivided |  | 5 | 7 | 75.94% | 2.72% | 4268 |  |
|  |  | MERRIMAN, Bob | 5 | 7 | 75.94% | 2.72% | 4268 |  |
|  |  | BUTLER, Hélène |  |  |  |  |  |  |
|  |  | SALTER, Susan |  |  |  |  |  |  |
|  |  | WASTERVAL, Sue |  |  |  |  |  |  |
|  |  | CHRISTIE, Graham |  |  |  |  |  |  |
| Buloke Shire Council 2012 - Postal |  |  | 7 | 11 | 81.41% | 1.05% | 4326 |  |
|  | Lower Avoca Ward | POLLARD, David Thomas | 2 | 3 | 79.96% | 0.95% | 1851 |  |
|  |  | McLEAN, Stuart John |  |  |  |  |  |  |
|  | Mallee Ward [U] | MATHER, Reid | 2 | 2 | N/A | N/A | 0 |  |
|  |  | WHITE, Ellen |  |  |  |  |  |  |
|  | Mount Jeffcott Ward | TELLEFSON, Leo John | 3 | 6 | 82.51% | 1.13% | 2475 |  |
|  |  | MILNE, Graeme |  |  |  |  |  |  |
|  |  | SHARP, Gail D. |  |  |  |  |  |  |
| Campaspe Shire Council 2012 - Postal |  |  | 9 | 22 | 78.44% | 2.56% | 28820 |  |
|  | Echuca Ward | MADDISON, Ian | 3 | 9 | 77.31% | 2.96% | 10194 |  |
|  |  | BRADBURY, Emma |  |  |  |  |  |  |
|  |  | JARMAN, Paul |  |  |  |  |  |  |
|  | Kyabram-Deakin Ward | DANIELI, Robert | 3 | 6 | 77.70% | 2.38% | 9030 |  |
|  |  | PANKHURST, Neil |  |  |  |  |  |  |
|  |  | HOWELL, Carol |  |  |  |  |  |  |
|  | Rochester Ward | WILSON, Leigh G. | 1 | 2 | 83.25% | 3.71% | 3242 |  |
|  | Waranga Ward | WESTON, Adrian | 1 | 3 | 78.65% | 0.99% | 3068 |  |
|  | Western Ward | TOLL, Greg | 1 | 2 | 79.03% | 2.08% | 3286 |  |
| Cardinia Shire Council 2012 - Postal |  |  | 9 | 20 | 70.17% | 3.62% | 56379 |  |
|  | Central Ward | ROSS, Collin | 4 | 9 | 64.77% | 4.71% | 25145 |  |
|  |  | OWEN, Jodie |  |  |  |  |  |  |
|  |  | BLENKHORN, George |  |  |  |  |  |  |
|  |  | LEMPRIERE, Kate |  |  |  |  |  |  |
|  | Port Ward | MOORE, Graeme | 2 | 4 | 77.90% | 2.36% | 11325 |  |
|  |  | YOUNG, David |  |  |  |  |  |  |
|  | Ranges Ward | OWEN, Brett | 3 | 7 | 72.60% | 3.18% | 19909 |  |
|  |  | WILMOT, Leticia |  |  |  |  |  |  |
|  |  | BAXTER, Tania |  |  |  |  |  |  |
| Casey City Council 2012 - Postal |  |  | 11 | 85 | 70.72% | 6.51% | 169519 |  |
|  | Balla Balla Ward | ABLETT, Geoff | 1 | 4 | 72.10% | 3.07% | 14596 |  |
|  | Edrington Ward | SEREY, Susan | 2 | 18 | 72.07% | 6.79% | 30823 |  |
|  |  | MORLAND, Mick |  |  |  |  |  |  |
|  | Four Oaks Ward | KAPLON, Rafal | 2 | 22 | 73.45% | 9.62% | 32726 |  |
|  |  | CRESTANI, Rosalie Bianca |  |  |  |  |  |  |
|  | Mayfield Ward | STAPLEDON, Amanda | 2 | 14 | 67.53% | 5.81% | 30312 |  |
|  |  | ROWE, Gary James |  |  |  |  |  |  |
|  | River Gum Ward | SMITH, Wayne | 2 | 16 | 68.66% | 7.07% | 32462 |  |
|  |  | ROSARIO, Damien |  |  |  |  |  |  |
|  | Springfield Ward | AZIZ, Sam | 2 | 11 | 71.15% | 4.40% | 28600 |  |
|  |  | WASS, Jo |  |  |  |  |  |  |
| Central Goldfields Shire Council 2012 - Postal |  |  | 7 | 13 | 80.08% | 2.06% | 10858 |  |
|  | Flynn Ward | SMITH, John | 1 | 2 | 74.06% | 2.30% | 1642 |  |
|  | Maryborough Ward | NIXON, Paula | 4 | 7 | 81.20% | 1.75% | 6036 |  |
|  |  | LOVETT, Geoff |  |  |  |  |  |  |
|  |  | McIVOR, Wendy |  |  |  |  |  |  |
|  |  | RINALDI, Barry |  |  |  |  |  |  |
|  | Paddys Ranges Ward | VAN BEVEREN, John Andrew | 1 | 2 | 82.91% | 2.30% | 1627 |  |
|  | Tullaroop Ward | ROBERTSON, Ian | 1 | 2 | 79.14% | 2.77% | 1553 |  |
| Colac Otway Shire Council 2012 - Postal | Unsubdivided |  | 7 | 14 | 78.17% | 4.48% | 19799 |  |
|  |  | WOODCROFT, Terry |  |  |  |  |  |  |
|  |  | SMITH, Chris |  |  |  |  |  |  |
|  |  | HART, Stephen |  |  |  |  |  |  |
|  |  | McCRICKARD, Mick |  |  |  |  |  |  |
|  |  | CROOK, Brian |  |  |  |  |  |  |
|  |  | DELAHUNTY, Michael |  |  |  |  |  |  |
|  |  | RUSSELL, Lyn |  |  |  |  |  |  |
| Corangamite Shire Council 2012 - Postal |  |  | 7 | 10 | 79.49% | 1.68% | 7728 |  |
|  | Central Ward | GSTREIN, Ruth | 3 | 5 | 79.28% | 1.40% | 5870 |  |
|  |  | O'CONNOR, Christopher John |  |  |  |  |  |  |
|  |  | OAKES, Wayne R. |  |  |  |  |  |  |
|  | Coastal Ward [U] | HARKIN, Peter | 1 | 1 | N/A | N/A | 0 |  |
|  | North Ward [U] | SMITH, Geoff | 1 | 1 | N/A | N/A | 0 |  |
|  | South-Central Ward [U] | BEARD, Joanne | 1 | 1 | N/A | N/A | 0 |  |
|  | South-West Ward | TROTTER, Neil David | 1 | 2 | 80.14% | 2.55% | 1858 |  |
| Darebin City Council 2012 - Postal |  |  | 9 | 52 | 67.53% | 7.72% | 102100 |  |
|  | Cazaly Ward | FONTANA, Vince | 3 | 18 | 67.55% | 7.73% | 34688 |  |
|  |  | WILLIAMS, Julie |  |  |  |  |  |  |
|  |  | LI, Bo |  |  |  |  |  |  |
|  | La Trobe Ward | GRECO, Gaetano | 3 | 17 | 71.14% | 7.59% | 31378 |  |
|  |  | LAURENCE, Tim |  |  |  |  |  |  |
|  |  | VILLELLA, Angela |  |  |  |  |  |  |
|  | Rucker Ward | McCARTHY, Trent | 3 | 17 | 64.36% | 7.82% | 36034 |  |
|  |  | TSITAS, Steven |  |  |  |  |  |  |
|  |  | WALSH, Oliver |  |  |  |  |  |  |
| East Gippsland Shire Council 2012 - Postal | Unsubdivided |  | 9 | 17 | 74.99% | 6.90% | 39645 |  |
|  |  | ELLIS, Dick |  |  |  |  |  |  |
|  |  | ROWE, Jane |  |  |  |  |  |  |
|  |  | NEAL, Peter |  |  |  |  |  |  |
|  |  | BUCKLEY, Ben |  |  |  |  |  |  |
|  |  | McNEILL, Jeff |  |  |  |  |  |  |
|  |  | FRESHWATER, Michael |  |  |  |  |  |  |
|  |  | REEVES, Mark |  |  |  |  |  |  |
|  |  | PELZ, Marianne |  |  |  |  |  |  |
|  |  | WILKIN, John |  |  |  |  |  |  |
| Frankston City Council 2012 - Postal |  |  | 9 | 21 | 67.44% | 3.87% | 97191 |  |
|  | North-East Ward | MAYER, Sandra | 3 | 5 | 68.83% | 3.35% | 33223 |  |
|  |  | HAMPTON, Colin |  |  |  |  |  |  |
|  |  | O'REILLY, Michael |  |  |  |  |  |  |
|  | North-West Ward | AITKEN, Glenn | 3 | 10 | 63.80% | 4.87% | 30843 |  |
|  |  | DOOLEY, James |  |  |  |  |  |  |
|  |  | SPELMAN, Rebekah |  |  |  |  |  |  |
|  | South Ward | CUNIAL, Brian | 3 | 6 | 69.44% | 3.53% | 33125 |  |
|  |  | TAYLOR, Darrel |  |  |  |  |  |  |
|  |  | TAYLER, Suzette |  |  |  |  |  |  |
| Gannawarra Shire Council 2012 - Postal |  |  | 7 | 9 | 80.83% | 1.69% | 7557 |  |
|  | Avoca Ward | GANNON, Neil W. | 1 | 2 | 79.30% | 2.69% | 1266 |  |
|  | Murray Ward [U] | AERTSSEN, Oscar | 1 | 1 | N/A | N/A | 0 |  |
|  | Patchell Ward [U] | den HOUTING, Keith | 3 | 3 | N/A | N/A | 3536 |  |
|  |  | ARIANS, Mark |  |  |  |  |  |  |
|  |  | GIBSON, Brian |  |  |  |  |  |  |
|  | Yarran Ward | GOULDING, Neville Charles | 2 | 3 | 81.52% | 1.25% | 2755 |  |
|  |  | LEARMONTH, Lorraine |  |  |  |  |  |  |
| Glen Eira City Council 2012 - Attendance |  |  | 9 | 33 | 68.03% | 10.58% | 98109 | 51 |
|  | Camden Ward | LIPSHUTZ, Michael | 3 | 11 | 66.72% | 9.75% | 31320 | 21 |
|  |  | DELAHUNTY, Mary |  |  |  |  |  |  |
|  |  | SOUNNESS, Thomas |  |  |  |  |  |  |
|  | Rosstown Ward | ESAKOFF, Margaret | 3 | 8 | 66.67% | 8.81% | 33482 | 10 |
|  |  | OKOTEL, Karina |  |  |  |  |  |  |
|  |  | PILLING, Neil |  |  |  |  |  |  |
|  | Tucker Ward | HYAMS, Jamie | 3 | 14 | 70.62% | 13.00% | 33307 | 20 |
|  |  | LOBO, Oscar |  |  |  |  |  |  |
|  |  | MAGEE, Jim |  |  |  |  |  |  |
| Glenelg Shire Council 2012 - Postal |  |  | 7 | 11 | 74.42% | 3.88% | 16811 |  |
|  | Glenelg Shire Council | WHITE, Geoff | 7 | 11 | 74.42% | 3.88% | 16811 |  |
|  |  | WILSON, Gilbert Desmond |  |  |  |  |  |  |
|  |  | RANK, Anita Maree |  |  |  |  |  |  |
|  |  | STEPHENS, Karen Anne |  |  |  |  |  |  |
|  |  | NORTHCOTT, John |  |  |  |  |  |  |
|  |  | HALLIDAY, Robert Reuben |  |  |  |  |  |  |
|  |  | OBERLANDER, Maxwell |  |  |  |  |  |  |
| Golden Plains Shire Council 2012 - Postal |  |  | 7 | 12 | 76.02% | 4.35% | 16098 |  |
|  | Golden Plains Shire Council | HANSFORD, Nathan John | 7 | 12 | 76.02% | 4.35% | 16098 |  |
|  |  | VAUGHAN, Greg |  |  |  |  |  |  |
|  |  | McARTHUR, Bill |  |  |  |  |  |  |
|  |  | BLAKE, Jenny |  |  |  |  |  |  |
|  |  | PHELAN, Des |  |  |  |  |  |  |
|  |  | CAMERON, Andrew |  |  |  |  |  |  |
|  |  | KIRBY, Helena Angela |  |  |  |  |  |  |
| Greater Bendigo City Council 2012 - Postal |  |  | 9 | 21 | 77.45% | 2.40% | 79736 |  |
|  | Eppalock Ward | CAMPBELL, Rod | 3 | 9 | 77.44% | 3.01% | 25340 |  |
|  |  | WERAGODA, Mark |  |  |  |  |  |  |
|  |  | LEACH, Helen |  |  |  |  |  |  |
|  | Lockwood Ward | FYFFE, Rod | 3 | 7 | 79.19% | 2.14% | 26947 |  |
|  |  | CHAPMAN, Elise |  |  |  |  |  |  |
|  |  | LYONS, Barry |  |  |  |  |  |  |
|  | Whipstick Ward | COX, Peter | 3 | 5 | 75.76% | 2.09% | 27449 |  |
|  |  | RUFFELL, Lisa |  |  |  |  |  |  |
|  |  | WILLIAMS, James |  |  |  |  |  |  |
| Greater Dandenong City Council 2012 - Attendance |  |  | 11 | 41 | 68.70% | 11.13% | 95503 | 82 |
|  | Lightwood Ward | O'REILLY, Sean | 3 | 7 | 71.63% | 8.26% | 25823 | 18 |
|  |  | CHEA, Youhorn |  |  |  |  |  |  |
|  |  | TRUONG, Loi |  |  |  |  |  |  |
|  | Paperbark Ward | BLADES, Roz | 3 | 14 | 71.24% | 13.40% | 26394 | 17 |
|  |  | BROWN, Peter |  |  |  |  |  |  |
|  |  | TAK, Meng Heang |  |  |  |  |  |  |
|  | Red Gum Ward | MEMETI, Jim | 3 | 11 | 60.24% | 11.46% | 25277 | 24 |
|  |  | KIRWAN, Matthew |  |  |  |  |  |  |
|  |  | LONG, Angela |  |  |  |  |  |  |
|  | Silverleaf Ward | SAMPEY, Maria | 2 | 9 | 72.64% | 11.52% | 18009 | 23 |
|  |  | KELLY, John |  |  |  |  |  |  |
| Greater Geelong City Council 2012 - Postal |  |  | 13 | 59 | 75.89% | 2.89% | 170,408 |  |
|  | Mayor | FAGG, Keith | 1 | 9 | 76.29% | 3.29% | 170408 |  |
|  | Austin Ward | IRVINE, John Robert | 1 | 5 | 73.55% | 2.24% | 13824 |  |
|  | Beangala Ward | FARRELL, Jan | 1 | 4 | 73.64% | 2.02% | 13492 |  |
|  | Brownbill Ward | HEAGNEY, Michelle | 1 | 6 | 72.70% | 2.95% | 13288 |  |
|  | Buckley Ward | RICHARDS, Andy | 1 | 5 | 76.74% | 2.29% | 15320 |  |
|  | Cheetham Ward | MACDONALD, Rod | 1 | 2 | 77.74% | 2.00% | 15139 |  |
|  | Corio Ward | FISHER, Kylie | 1 | 3 | 70.21% | 2.91% | 13791 |  |
|  | Coryule Ward | ELLIS, Lindsay | 1 | 5 | 72.03% | 2.43% | 14228 |  |
|  | Cowie Ward | KONTELJ, Eddy | 1 | 5 | 78.11% | 2.47% | 13785 |  |
|  | Deakin Ward | NELSON, Ron | 1 | 3 | 82.17% | 3.71% | 14724 |  |
|  | Kardinia Ward | HARWOOD, Bruce | 1 | 4 | 75.31% | 2.07% | 14449 |  |
|  | Kildare Ward | KONTELJ, Stretch | 1 | 2 | 76.63% | 1.87% | 12705 |  |
|  | Windermere Ward | ANSETT, Tony | 1 | 6 | 76.08% | 2.68% | 15663 |  |
| Greater Shepparton City Council 2012 - Postal | Unsubdivided |  | 7 | 26 | 80.10% | 9.53% | 43372 |  |
|  |  | OROSZVARY, Leslie Alexander |  |  |  |  |  |  |
|  |  | MUTO, Milvan |  |  |  |  |  |  |
|  |  | HOULIHAN, Jenny |  |  |  |  |  |  |
|  |  | SUMMER, Fern |  |  |  |  |  |  |
|  |  | PATTERSON, Dennis |  |  |  |  |  |  |
|  |  | RYAN, Kevin Gunna |  |  |  |  |  |  |
|  |  | POLAN, Michael |  |  |  |  |  |  |
| Hepburn Shire Council 2012 - Postal |  |  | 7 | 15 | 76.18% | 2.51% | 12613 |  |
|  | Birch Ward | REDWOOD, Kate | 2 | 6 | 72.57% | 2.17% | 4309 |  |
|  |  | NICLAS, Pierre |  |  |  |  |  |  |
|  | Cameron Ward | NEWITT, Neil | 1 | 2 | 78.51% | 2.58% | 2024 |  |
|  | Coliban Ward | KLEIN, Sebastian John | 1 | 2 | 74.69% | 2.38% | 2027 |  |
|  | Creswick Ward | HENDERSON, Don | 2 | 4 | 79.43% | 2.84% | 4253 |  |
|  |  | MAY, Greg |  |  |  |  |  |  |
|  | Holcombe Ward [U] | McCLENAGHAN, William Marks | 1 | 1 | N/A | N/A | 0 |  |
| Hindmarsh Shire Council 2012 - Postal |  |  | 6 | 11 | 81.27% | 2.61% | 3396 |  |
|  | East Ward | SCHNEIDER, Tony | 2 | 6 | 82.10% | 3.00% | 1665 |  |
|  |  | NELSON, Debra |  |  |  |  |  |  |
|  | North Ward [U] | LOWE, Ronald Edwin | 2 | 2 | N/A | N/A | 0 |  |
|  |  | CHIVELL, Elizabeth |  |  |  |  |  |  |
|  | West Ward | ROBINS, Wendy | 2 | 3 | 80.47% | 2.23% | 1731 |  |
|  |  | GERSCH, Rob |  |  |  |  |  |  |
| Hobsons Bay City Council 2012 - Postal |  |  | 7 | 41 | 71.57% | 5.69% | 63863 |  |
|  | Cherry Lake Ward | BRIFFA, Tony | 2 | 14 | 72.17% | 5.45% | 18047 |  |
|  |  | WILSON, Sandra |  |  |  |  |  |  |
|  | Strand Ward | ALTAIR, Angela | 3 | 16 | 69.52% | 6.77% | 25947 |  |
|  |  | HEMPHILL, Peter |  |  |  |  |  |  |
|  |  | MORGAN, Paul |  |  |  |  |  |  |
|  | Wetlands Ward | GRIGOROVITCH, Luba | 2 | 11 | 73.71% | 4.57% | 19869 |  |
|  |  | GATES, Colleen |  |  |  |  |  |  |
| Horsham Rural City Council 2012 - Postal |  |  | 7 | 11 | 81.79% | 2.50% | 15445 |  |
|  | Horsham Rural City Council | GRIMBLE, David | 7 | 11 | 81.79% | 2.50% | 15445 |  |
|  |  | EXELL, Susan Joy |  |  |  |  |  |  |
|  |  | RADFORD, Mark A. |  |  |  |  |  |  |
|  |  | CLARKE, Pamela Nance |  |  |  |  |  |  |
|  |  | BARBER, Robin Leslie |  |  |  |  |  |  |
|  |  | PHELAN, Tony |  |  |  |  |  |  |
|  |  | PHILLIPS, Heather R. |  |  |  |  |  |  |
| Hume City Council 2012 - Postal |  |  | 11 | 47 | 73.15% | 6.21% | 115039 |  |
|  | Aitken Ward | NUNN, Casey | 4 | 22 | 72.43% | 8.29% | 38649 |  |
|  |  | JESSOP, Drew |  |  |  |  |  |  |
|  |  | BAMUNUSINGHE, Chandra |  |  |  |  |  |  |
|  |  | BOLTON, Alan William |  |  |  |  |  |  |
|  | Jacksons Creek Ward | POTTER, Ann Therese Elizabeth | 3 | 10 | 72.41% | 3.97% | 32395 |  |
|  |  | OGILVIE, Jack |  |  |  |  |  |  |
|  |  | MEDCRAFT, Steve Jack |  |  |  |  |  |  |
|  | Meadow Valley Ward | PORTER, Geoff | 4 | 15 | 74.32% | 6.04% | 43995 |  |
|  |  | PATSIKATHEODOROU, Helen |  |  |  |  |  |  |
|  |  | DOUGALL, Vic |  |  |  |  |  |  |
|  |  | ATMACA, Adem |  |  |  |  |  |  |
| Indigo Shire Council 2012 - Postal | Unsubdivided |  | 7 | 17 | 77.72% | 6.56% | 12867 |  |
|  |  | CHAMBERS, Don |  |  |  |  |  |  |
|  |  | CROUCHER, Peter |  |  |  |  |  |  |
|  |  | MURDOCH, Barbara Joan |  |  |  |  |  |  |
|  |  | O'CONNOR, Jenny |  |  |  |  |  |  |
|  |  | GAFFNEY, Bernard |  |  |  |  |  |  |
|  |  | TRENERY, James |  |  |  |  |  |  |
|  |  | HORNE, Roberta |  |  |  |  |  |  |
| Kingston City Council 2012 - Postal |  |  | 9 | 52 | 71.25% | 6.31% | 112137 |  |
|  | Central Ward | GLEDHILL, Geoff | 3 | 28 | 70.64% | 9.40% | 37366 |  |
|  |  | BROWNLEES, Ron |  |  |  |  |  |  |
|  |  | WEST, Rosemary |  |  |  |  |  |  |
|  | North Ward | STAIKOS, Steve | 3 | 10 | 72.28% | 4.21% | 35832 |  |
|  |  | BARTH, Tamara |  |  |  |  |  |  |
|  |  | PEULICH, Paul |  |  |  |  |  |  |
|  | South Ward | BEARSLEY, Tamsin | 3 | 14 | 70.88% | 5.34% | 38939 |  |
|  |  | EDEN, David |  |  |  |  |  |  |
|  |  | RONKE, John Morgan |  |  |  |  |  |  |
| Knox City Council 2012 - Attendance |  |  | 9 | 26 | 74.04% | 7.57% | 90758 | 41 |
|  | Baird Ward | LOCKWOOD, Peter | 1 | 5 | 66.77% | 8.93% | 12432 | 9 |
|  | Chandler Ward | MORTIMORE, John | 1 | 2 | 68.95% | 8.00% | 11836 | 2 |
|  | Collier Ward [U] | COSSARI, Joe | 1 | 1 | N/A | N/A | 0 | 0 |
|  | Dinsdale Ward [U] | GILL, Adam | 1 | 1 | N/A | N/A | 2 | 0 |
|  | Dobson Ward | ORPEN, Karin | 1 | 3 | 72.93% | 7.42% | 13393 | 9 |
|  | Friberg Ward | HOLLAND, Tony | 1 | 6 | 77.75% | 8.75% | 13419 | 7 |
|  | Scott Ward | COOPER, David | 1 | 3 | 76.13% | 6.08% | 13087 | 7 |
|  | Taylor Ward | PEARCE, Darren | 1 | 2 | 79.71% | 6.55% | 13632 | 3 |
|  | Tirhatuan Ward | SEYMOUR, Nicole | 1 | 3 | 74.92% | 7.57% | 12957 | 4 |
| Latrobe City Council 2012 - Postal |  |  | 9 | 22 | 73.72% | 3.42% | 54385 |  |
|  | Central Ward | SINDT, Christine | 2 | 6 | 70.15% | 3.26% | 12239 |  |
|  |  | MIDDLEMISS, Graeme |  |  |  |  |  |  |
|  | East Ward | KAM, Sandy | 4 | 8 | 76.06% | 3.76% | 22983 |  |
|  |  | HARRIMAN, Dale |  |  |  |  |  |  |
|  |  | O'CALLAGHAN, Kellie |  |  |  |  |  |  |
|  |  | ROSSITER, Michael |  |  |  |  |  |  |
|  | South Ward | WHITE, Darrell Keith | 1 | 2 | 73.91% | 3.80% | 6333 |  |
|  | West Ward | GIBSON, Sharon | 2 | 6 | 72.81% | 2.75% | 12830 |  |
|  |  | GIBBONS, Peter |  |  |  |  |  |  |
| Loddon Shire Council 2012 - Postal |  |  | 5 | 7 | 75.50% | 1.87% | 2979 |  |
|  | Boort Ward [U] | BEATTIE, Neil | 1 | 1 | N/A | N/A | 0 |  |
|  | Inglewood Ward [U] | CONDLIFFE, Colleen | 1 | 1 | N/A | N/A | 0 |  |
|  | Tarnagulla Ward | CURNOW, Geoff | 1 | 2 | 76.25% | 2.04% | 1478 |  |
|  | Terrick Ward | McKINNON, Cheryl | 1 | 2 | 74.75% | 1.69% | 1501 |  |
|  | Wedderburn Ward [U] | HOLT, Gavan Lindsay | 1 | 1 | N/A | N/A | 0 |  |
| Macedon Ranges Shire Council 2012 - Postal |  |  | 9 | 29 | 74.04% | 3.87% | 33712 |  |
|  | East Ward | MORABITO, Joe | 3 | 8 | 73.55% | 3.25% | 10887 |  |
|  |  | HACKETT, Graham |  |  |  |  |  |  |
|  |  | McLAUGHLIN, Henry |  |  |  |  |  |  |
|  | South Ward | MOWATT, Russell Stewart | 3 | 15 | 75.19% | 5.53% | 11490 |  |
|  |  | PIPER, Sally |  |  |  |  |  |  |
|  |  | LETCHFORD, John |  |  |  |  |  |  |
|  | West Ward | JUKES, Roger | 3 | 6 | 73.36% | 2.74% | 11335 |  |
|  |  | ANDERSON, Jennifer |  |  |  |  |  |  |
|  |  | CONNOR, John |  |  |  |  |  |  |
| Manningham City Council 2012 - Postal |  |  | 9 | 35 | 75.62% | 5.04% | 87331 |  |
|  | Heide Ward | GOUGH, Geoff | 3 | 8 | 76.46% | 3.69% | 29310 |  |
|  |  | KLEINERT, Michelle |  |  |  |  |  |  |
|  |  | GRIVOKOSTOPOULOS, Jim |  |  |  |  |  |  |
|  | Koonung Ward | YANG, Jennifer | 3 | 12 | 74.20% | 4.85% | 28842 |  |
|  |  | O'BRIEN, Stephen |  |  |  |  |  |  |
|  |  | HAYNES, Dot |  |  |  |  |  |  |
|  | Mullum Mullum Ward | DOWNIE, Meg | 3 | 15 | 76.19% | 6.59% | 29179 |  |
|  |  | McLEISH, Paul |  |  |  |  |  |  |
|  |  | GALBALLY, Sophy |  |  |  |  |  |  |
| Mansfield Shire Council 2012 - Postal |  |  | 5 | 12 | 72.72% | 2.09% | 7944 |  |
|  | Bonnie Doon Ward | SLADDIN, Paul | 1 | 3 | 69.10% | 1.42% | 1942 |  |
|  | Jamieson Ward [U] | BATE, Russell William | 1 | 1 | N/A | N/A | 0 |  |
|  | Mansfield Ward | ROBINSON, Ray | 2 | 6 | 76.51% | 2.26% | 3925 |  |
|  |  | HOGAN, Ellen Joy |  |  |  |  |  |  |
|  | Tolmie Ward | ATTLEY, Margaret Colville | 1 | 2 | 68.95% | 2.37% | 2077 |  |
| Maribyrnong City Council 2012 - Postal |  |  | 7 | 29 | 63.90% | 4.17% | 53816 |  |
|  | River Ward | CARTER, Sarah | 2 | 7 | 64.48% | 3.19% | 15662 |  |
|  |  | McDONALD, Cameron |  |  |  |  |  |  |
|  | Stony Creek Ward | QUACH, Nam | 2 | 10 | 63.60% | 4.20% | 15902 |  |
|  |  | CUMMING, Catherine |  |  |  |  |  |  |
|  | Yarraville Ward | CLARKE, Michael | 3 | 12 | 63.69% | 4.85% | 22252 |  |
|  |  | ZAKHAROV, Martin |  |  |  |  |  |  |
|  |  | MILES, Grant |  |  |  |  |  |  |
| Maroondah City Council 2012 - Postal |  |  | 9 | 39 | 72.81% | 5.63% | 80417 |  |
|  | Arrabri Ward | THOMAS, Natalie | 3 | 10 | 73.36% | 4.73% | 27297 |  |
|  |  | GLEESON, Christina |  |  |  |  |  |  |
|  |  | DIB, Tony |  |  |  |  |  |  |
|  | Mullum Ward | LAMONT, Nora | 3 | 15 | 72.11% | 6.49% | 26370 |  |
|  |  | FRASER, Ann |  |  |  |  |  |  |
|  |  | MARKS, Samantha |  |  |  |  |  |  |
|  | Wyreena Ward | WILLMOTT, Les | 3 | 14 | 72.94% | 5.71% | 26750 |  |
|  |  | STEANE, Rob |  |  |  |  |  |  |
|  |  | FITZGERALD, Liam Francis |  |  |  |  |  |  |
| Melbourne City Council 2012 - Postal |  |  | 10 | 49 | 59.98% | 3.26% | 108,434 |  |
|  | Councillors | LOUEY, Kevin | 9 | 40 | 60.01% | 2.16% | 108434 |  |
|  |  | OKE, Cathy |  |  |  |  |  |  |
|  |  | ONG, Ken |  |  |  |  |  |  |
|  |  | WOOD, Arron |  |  |  |  |  |  |
|  |  | PINDER-MORTIMER, Beverley |  |  |  |  |  |  |
|  |  | FOSTER, Richard |  |  |  |  |  |  |
|  |  | WATTS, Jackie |  |  |  |  |  |  |
|  |  | MAYNE, Stephen |  |  |  |  |  |  |
|  |  | LEPPERT, Rohan |  |  |  |  |  |  |
|  | Leadership Team | DOYLE, Robert (Lord Mayor) | 1 | 9 | 59.94% | 4.35% |  |  |
|  |  | RILEY, Susan (Deputy Lord Mayor) |  |  |  |  |  |  |
| Melton City Council 2012 - Postal |  |  | 7 | 72 | 68.52% | 9.58% | 76026 |  |
|  | Cambridge Ward | MAJDLIK, Kathy | 2 | 22 | 68.46% | 8.48% | 23043 |  |
|  |  | DUNN, Nola |  |  |  |  |  |  |
|  | Coburn Ward | BORG, Broden | 3 | 30 | 66.75% | 11.25% | 33587 |  |
|  |  | RAMSEY, Sophie |  |  |  |  |  |  |
|  |  | TURNER, Bob |  |  |  |  |  |  |
|  | Watts Ward | CARLI, Lara | 2 | 20 | 71.66% | 8.14% | 19396 |  |
|  |  | CUGLIARI, Renata |  |  |  |  |  |  |
| Mildura Rural City Council 2012 - Postal | Unsubdivided |  | 9 | 14 | 76.02% | 5.06% | 38063 |  |
|  |  | CUPPER, Ali |  |  |  |  |  |  |
|  |  | ARNOLD, John |  |  |  |  |  |  |
|  |  | MILNE, Glenn |  |  |  |  |  |  |
|  |  | THORBURN, Max |  |  |  |  |  |  |
|  |  | JOSLYN, Jill |  |  |  |  |  |  |
|  |  | BROWN, Greg |  |  |  |  |  |  |
|  |  | PEART, Sharyon |  |  |  |  |  |  |
|  |  | HARRIS, Judi |  |  |  |  |  |  |
|  |  | ECKEL, Mark |  |  |  |  |  |  |
| Mitchell Shire Council 2012 - Postal |  |  | 9 | 22 | 72.75% | 2.98% | 26962 |  |
|  | Central Ward | PARKER, Rodney John | 3 | 7 | 76.13% | 2.97% | 9428 |  |
|  |  | STEWART, Kelley |  |  |  |  |  |  |
|  |  | LEE, Ross |  |  |  |  |  |  |
|  | North Ward | SANDERSON, Rhonda | 3 | 8 | 71.80% | 2.87% | 8598 |  |
|  |  | MELBOURNE, Bill |  |  |  |  |  |  |
|  |  | CHISHOLM, Bill |  |  |  |  |  |  |
|  | South Ward | CORNISH, Bob | 3 | 7 | 70.10% | 3.11% | 8936 |  |
|  |  | MULRONEY, Kevin |  |  |  |  |  |  |
|  |  | MARSTAELLER, Sue |  |  |  |  |  |  |
| Moira Shire Council 2012 - Postal | Unsubdivided |  | 9 | 18 | 75.95% | 6.72% | 23428 |  |
|  |  | BOURKE, Kevin Joseph |  |  |  |  |  |  |
|  |  | MONK, Alex |  |  |  |  |  |  |
|  |  | CLEVELAND, Gary Ronald |  |  |  |  |  |  |
|  |  | MANSFIELD, Peter |  |  |  |  |  |  |
|  |  | COX, Edward J. |  |  |  |  |  |  |
|  |  | BUCK, Wendy |  |  |  |  |  |  |
|  |  | KEENAN, Brian Francis |  |  |  |  |  |  |
|  |  | MARTIN, Marie Katharine |  |  |  |  |  |  |
|  |  | McPHEE, Don |  |  |  |  |  |  |
| Monash City Council 2012 - Postal |  |  | 11 | 58 | 73.88% | 5.59% | 121083 |  |
|  | Glen Waverley Ward | LAKE, Geoff | 2 | 9 | 78.74% | 3.02% | 20747 |  |
|  |  | NOLAN, Katrina |  |  |  |  |  |  |
|  | Mount Waverley Ward | LO, Jieh-Yung | 3 | 14 | 73.18% | 5.23% | 35397 |  |
|  |  | MORRISSEY, Tom |  |  |  |  |  |  |
|  |  | LITTLE, Brian |  |  |  |  |  |  |
|  | Mulgrave Ward | KLISARIS, Paul | 3 | 15 | 76.81% | 5.49% | 30549 |  |
|  |  | DAVIES, Robert |  |  |  |  |  |  |
|  |  | DRIEBERG, Micaela |  |  |  |  |  |  |
|  | Oakleigh Ward | DIMOPOULOS, Stephen | 3 | 20 | 69.06% | 7.86% | 34390 |  |
|  |  | PONTIKIS, Bill |  |  |  |  |  |  |
|  |  | ZOGRAPHOS, Theo |  |  |  |  |  |  |
| Moonee Valley City Council 2012 - Postal |  |  | 9 | 26 | 72.24% | 3.99% | 84740 |  |
|  | Buckley Ward | SHARPE, Narelle | 3 | 10 | 73.61% | 4.34% | 30295 |  |
|  |  | CHANTRY, Jan |  |  |  |  |  |  |
|  |  | GIULIANO, Paul |  |  |  |  |  |  |
|  | Myrnong Ward | NATION, Cam | 3 | 9 | 66.64% | 3.93% | 28762 |  |
|  |  | CUSACK, James |  |  |  |  |  |  |
|  |  | MARSHALL, Nicole |  |  |  |  |  |  |
|  | Rose Hill Ward | SIPEK, John | 3 | 7 | 76.89% | 3.67% | 25683 |  |
|  |  | SURACE, Andrea |  |  |  |  |  |  |
|  |  | CORNISH, Shirley |  |  |  |  |  |  |
| Moorabool Shire Council 2012 - Postal |  |  | 7 | 12 | 71.84% | 3.22% | 16906 |  |
|  | Central Moorabool Ward | TATCHELL, Paul | 1 | 4 | 76.19% | 3.88% | 3285 |  |
|  | East Moorabool Ward | DUDZIK, Tonia | 4 | 6 | 70.79% | 3.05% | 13621 |  |
|  |  | COMRIE, Allan Edmund |  |  |  |  |  |  |
|  |  | EDWARDS, David |  |  |  |  |  |  |
|  |  | SPAIN, John |  |  |  |  |  |  |
|  | West Moorabool Ward [U] | SULLIVAN, Thomas Gerard | 1 | 1 | N/A | N/A | 0 |  |
|  | Woodlands Ward [U] | TOOHEY, Pat | 1 | 1 | N/A | N/A | 0 |  |
| Moreland City Council 2012 - Attendance |  |  | 11 | 49 | 64.46% | 16.06% | 111987 | 106 |
|  | North-East Ward | BOLTON, Sue | 4 | 24 | 66.48% | 21.23% | 41221 | 55 |
|  |  | THOMPSON, Rob |  |  |  |  |  |  |
|  |  | TETI, Michael |  |  |  |  |  |  |
|  |  | THOMPSON, Lenka |  |  |  |  |  |  |
|  | North-West Ward | YILDIZ, Oscar | 4 | 17 | 68.21% | 15.42% | 41118 | 35 |
|  |  | KAVANAGH, John |  |  |  |  |  |  |
|  |  | DAVIDSON, Helen |  |  |  |  |  |  |
|  |  | GILLIES, Lita |  |  |  |  |  |  |
|  | South Ward | TAPINOS, Lambros | 3 | 8 | 56.44% | 8.65% | 29648 | 16 |
|  |  | RATNAM, Samantha |  |  |  |  |  |  |
|  |  | HOPPER, Meghan |  |  |  |  |  |  |
| Mornington Peninsula Shire Council 2012 - Postal |  |  | 11 | 43 | 68.52% | 4.37% | 145378 |  |
|  | Briars Ward | SHAW, Anne | 3 | 11 | 70.17% | 4.77% | 43179 |  |
|  |  | COLOMB, Bev |  |  |  |  |  |  |
|  |  | DIXON, Andrew |  |  |  |  |  |  |
|  | Cerberus Ward | GARNOCK, David | 1 | 3 | 68.21% | 2.38% | 12391 |  |
|  | Nepean Ward | RODGERS, Tim | 2 | 8 | 65.46% | 3.52% | 24560 |  |
|  |  | FRASER, Hugh |  |  |  |  |  |  |
|  | Red Hill Ward | MARTIN, Frank | 1 | 3 | 68.96% | 2.33% | 12349 |  |
|  | Seawinds Ward | PITTOCK, Graham | 3 | 14 | 67.63% | 6.26% | 40263 |  |
|  |  | GIBB, David |  |  |  |  |  |  |
|  |  | CELI, Antonella |  |  |  |  |  |  |
|  | Watson Ward | BOWDEN, Lynn | 1 | 4 | 71.53% | 2.61% | 12636 |  |
| Mount Alexander Shire Council 2012 - Postal |  |  | 7 | 23 | 79.00% | 2.26% | 13290 |  |
|  | Calder Ward | BARBER, Tim | 1 | 2 | 82.09% | 2.25% | 2055 |  |
|  | Castlemaine Ward | COLE, Chris | 3 | 10 | 79.67% | 2.42% | 7013 |  |
|  |  | BELL, Tony |  |  |  |  |  |  |
|  |  | HOWARD, Jessica |  |  |  |  |  |  |
|  | Coliban Ward | HENDERSON, Christine | 1 | 6 | 73.64% | 2.57% | 2166 |  |
|  | Loddon River Ward [U] | REDDEN, Michael | 1 | 1 | N/A | N/A | 0 |  |
|  | Tarrengower Ward | TELFORD, Sharon | 1 | 4 | 79.28% | 1.41% | 2056 |  |
| Moyne Shire Council 2012 - Postal | unsubdivided |  | 7 | 9 | 79.75% | 2.55% | 14108 |  |
|  |  | DOUKAS, Jim | 7 | 9 | 79.75% | 2.55% | 14108 |  |
|  |  | PURCELL, James |  |  |  |  |  |  |
|  |  | WOLFE, Mick |  |  |  |  |  |  |
|  |  | PARKER, Jill |  |  |  |  |  |  |
|  |  | RYAN, Colin |  |  |  |  |  |  |
|  |  | LEUTTON, Ralph |  |  |  |  |  |  |
|  |  | KEANE, Anthony |  |  |  |  |  |  |
| Murrindindi Shire Council 2012 - Postal |  |  | 7 | 12 | 73.44% | 1.82% | 5904 |  |
|  | Cathedral Ward | CHALLEN, Christine | 1 | 3 | 71.52% | 2.42% | 1791 |  |
|  | Cheviot Ward [U] | KENNEDY, John Wilson | 1 | 1 | N/A | N/A | 0 |  |
|  | Eildon Ward | MAGNER, Bernie | 1 | 2 | 74.40% | 1.62% | 1906 |  |
|  | King Parrot Ward [U] | RUHR, Cris | 1 | 1 | N/A | N/A | 0 |  |
|  | Kinglake Ward [U] | DERWENT, Andrew | 1 | 1 | N/A | N/A | 0 |  |
|  | Koriella Ward [U] | WALSH, John Christopher | 1 | 1 | N/A | N/A | 0 |  |
|  | Red Gate Ward | RAE, Margaret Ida | 1 | 3 | 74.17% | 1.53% | 2207 |  |
| Nillumbik Shire Council 2012 - Postal |  |  | 7 | 44 | 76.69% | 3.12% | 46373 |  |
|  | Blue Lake Ward | KLEIN, Meralyn | 1 | 3 | 77.53% | 3.10% | 6947 |  |
|  | Bunjil Ward | VAN HULSEN, Anika | 1 | 4 | 77.39% | 2.89% | 6343 |  |
|  | Edendale Ward | YOUNG, Michael Robert | 1 | 12 | 76.41% | 3.52% | 6983 |  |
|  | Ellis Ward | PERKINS, Peter | 1 | 6 | 77.82% | 3.26% | 6187 |  |
|  | Sugarloaf Ward | KING, Ken | 1 | 8 | 73.49% | 2.94% | 6907 |  |
|  | Swipers Gully Ward | HATTAM, Bronnie | 1 | 8 | 76.59% | 3.83% | 6605 |  |
|  | Wingrove Ward | COLEMAN, Helen | 1 | 3 | 77.85% | 2.25% | 6401 |  |
| Northern Grampians Shire Council 2012 - Postal |  |  | 7 | 11 | 78.31% | 1.96% | 7751 |  |
|  | Central Ward | ERWIN, Kevin A. | 1 | 2 | 78.55% | 1.76% | 1520 |  |
|  | Kara Kara Ward [U] | ANDERSON, Jim | 2 | 2 | N/A | N/A | 0 |  |
|  |  | DRISCOLL, Tony |  |  |  |  |  |  |
|  | South West Ward | RUSSELL, Paul | 1 | 2 | 78.09% | 3.58% | 1611 |  |
|  | Stawell Ward | RICE, Wayne | 3 | 5 | 78.31% | 1.46% | 4620 |  |
|  |  | EMERSON, Murray |  |  |  |  |  |  |
|  |  | HYSLOP, Karen |  |  |  |  |  |  |
| Port Phillip City Council 2012 - Attendance |  |  | 7 | 27 | 49.40% | 6.19% | 79618 | 83 |
|  | Albert Park Ward | STEVENS, Amanda | 1 | 4 | 57.28% | 6.02% | 11387 | 17 |
|  | Carlisle Ward | HUXLEY, Vanessa | 1 | 5 | 51.12% | 6.85% | 12340 | 19 |
|  | Catani Ward | THOMANN, Serge | 1 | 3 | 43.07% | 5.39% | 10943 | 5 |
|  | Emerald Hill Ward | HORVATH, Anita | 1 | 3 | 48.70% | 6.78% | 10207 | 8 |
|  | Junction Ward | BOND, Andrew | 1 | 6 | 38.11% | 7.97% | 12044 | 15 |
|  | Point Ormond Ward | TOUZEAU, Jane | 1 | 3 | 51.80% | 5.43% | 12091 | 11 |
|  | Sandridge Ward | VOSS, Bernadene | 1 | 3 | 56.24% | 5.23% | 10606 | 8 |
| Pyrenees Shire Council 2012 - Postal |  |  | 5 | 10 | 77.22% | 2.81% | 7103 |  |
|  | Avoca Ward | EASON, Ron | 1 | 2 | 78.24% | 4.19% | 1434 |  |
|  | Beaufort Ward | O'CONNOR, Michael | 1 | 2 | 79.50% | 2.64% | 1429 |  |
|  | De Cameron Ward | VANCE, Robert J. | 1 | 2 | 72.48% | 1.94% | 1421 |  |
|  | Ercildoune Ward | CLARK, David | 1 | 2 | 79.17% | 3.45% | 1426 |  |
|  | Mount Emu Ward | KEHOE, Tanya | 1 | 2 | 76.67% | 1.69% | 1393 |  |
| South Gippsland Shire Council 2012 - Postal |  |  | 9 | 13 | 74.72% | 2.05% | 18647 |  |
|  | Coastal-Promontory Ward | DAVIES, Mohya | 3 | 4 | 71.63% | 1.65% | 9280 |  |
|  |  | KENNEDY, Kieran |  |  |  |  |  |  |
|  |  | HARDING, Jeanette |  |  |  |  |  |  |
|  | Strzelecki Ward | BRUNT, Lorraine | 3 | 6 | 77.78% | 2.40% | 9367 |  |
|  |  | NEWTON, Bob |  |  |  |  |  |  |
|  |  | McEWEN, Andrew |  |  |  |  |  |  |
|  | Tarwin Valley Ward [U] | HUTCHINSON-BROOKS, Nigel | 3 | 3 | N/A | N/A | 0 |  |
|  |  | HILL, Don |  |  |  |  |  |  |
|  |  | FAWCETT, James David |  |  |  |  |  |  |
| Southern Grampians Shire Council 2012 - Postal | Unsubdivided |  | 7 | 10 | 81.65% | 3.84% | 13406 |  |
|  |  | CALVANO, Albert | 7 | 10 | 81.65% | 3.84% | 13406 |  |
|  |  | DARK, Peter |  |  |  |  |  |  |
|  |  | ARMSTRONG, Cathy |  |  |  |  |  |  |
|  |  | BATTISTA, Paul |  |  |  |  |  |  |
|  |  | DAWSON, Dennis |  |  |  |  |  |  |
|  |  | COLLITON, Bruach |  |  |  |  |  |  |
|  |  | RAINSFORD, Katrina |  |  |  |  |  |  |
| Stonnington City Council 2012 - Attendance |  |  | 9 | 36 | 56.20% | 10.31% | 80674 | 43 |
|  | East Ward | DAVIE, Erin | 3 | 8 | 64.37% | 9.11% | 27005 | 10 |
|  |  | McMORROW, John |  |  |  |  |  |  |
|  |  | STUBBS, Adrian |  |  |  |  |  |  |
|  | North Ward | CHANDLER, John | 3 | 15 | 49.41% | 11.52% | 28345 | 20 |
|  |  | KLISARIS, Jami |  |  |  |  |  |  |
|  |  | KOCE, Matthew |  |  |  |  |  |  |
|  | South Ward | SEHR, Melina | 3 | 13 | 55.08% | 10.58% | 25324 | 13 |
|  |  | ULLIN, Claude |  |  |  |  |  |  |
|  |  | HIBBINS, Sam |  |  |  |  |  |  |
| Strathbogie Shire Council 2012 - Postal |  |  | 7 | 14 | 78.92% | 2.25% | 8051 |  |
|  | Honeysuckle Creek Ward | STORER, Patrick | 1 | 2 | 79.82% | 2.18% | 1323 |  |
|  | Hughes Creek Ward [U] | LITTLE, Malcolm | 1 | 1 | N/A | N/A | 0 |  |
|  | Lake Nagambie Ward | PURBRICK, Alister John | 2 | 4 | 75.95% | 1.54% | 2649 |  |
|  |  | SWAN, Debra Elaine |  |  |  |  |  |  |
|  | Mount Wombat Ward | WEATHERALD, Robin Hull | 1 | 2 | 77.16% | 4.34% | 1375 |  |
|  | Seven Creeks Ward | FURLANETTO, Colleen | 2 | 5 | 82.29% | 1.93% | 2704 |  |
|  |  | WILLIAMS, Graeme Mick |  |  |  |  |  |  |
| Surf Coast Shire Council 2012 - Postal |  |  | 9 | 25 | 74.84% | 2.92% | 26502 |  |
|  | Anglesea Ward | COKER, Libby | 2 | 6 | 71.85% | 1.91% | 6864 |  |
|  |  | SMITH, Margot Ann |  |  |  |  |  |  |
|  | Lorne Ward [U] | GOLDSWORTHY, Clive | 1 | 1 | N/A | N/A | 0 |  |
|  | Torquay Ward | FISHER, Eve | 4 | 11 | 73.37% | 3.52% | 13168 |  |
|  |  | BELL, David K. |  |  |  |  |  |  |
|  |  | HODGE, Rose |  |  |  |  |  |  |
|  |  | McKITERICK, Brian |  |  |  |  |  |  |
|  | Winchelsea Ward | NOCKLES, Rod | 2 | 7 | 80.99% | 2.79% | 6470 |  |
|  |  | WELLINGTON, Heather |  |  |  |  |  |  |
| Swan Hill Rural City Council 2012 - Postal |  |  | 7 | 18 | 78.51% | 2.61% | 14471 |  |
|  | Central Ward | CRUICKSHANK, Greg | 4 | 10 | 80.18% | 2.63% | 8386 |  |
|  |  | KILEY, Jessie |  |  |  |  |  |  |
|  |  | CROWE, Jim |  |  |  |  |  |  |
|  |  | ADAMSON, Michael |  |  |  |  |  |  |
|  | Lakes Ward | McPHEE, Les | 1 | 4 | 80.65% | 1.35% | 2016 |  |
|  | Murray-Mallee Ward | NORTON, Gary W. | 1 | 2 | 77.71% | 3.95% | 2019 |  |
|  | Robinvale Ward | KATIS, John Nicholas | 1 | 2 | 70.34% | 2.50% | 2050 |  |
| Towong Shire Council 2012 - Postal | Unsubdivided |  | 5 | 12 | 78.03% | 3.34% | 5486 |  |
|  |  | WORTMANN, David John |  |  |  |  |  |  |
|  |  | FRASER, Mary |  |  |  |  |  |  |
|  |  | JOYCE, Peter Anthony |  |  |  |  |  |  |
|  |  | SCALES, Aaron I. |  |  |  |  |  |  |
|  |  | GADD, Debi |  |  |  |  |  |  |
| Wangaratta Rural City Council 2012 - Postal | Unsubdivided |  | 7 | 19 | 82.70% | 6.63% | 21738 |  |
|  |  | JOYCE, Don |  |  |  |  |  |  |
|  |  | PARISOTTO, Rozi |  |  |  |  |  |  |
|  |  | FIDGE, Julian |  |  |  |  |  |  |
|  |  | ATKINS, Tammy |  |  |  |  |  |  |
|  |  | AMERY, Noel |  |  |  |  |  |  |
|  |  | McINERNEY, Lisa |  |  |  |  |  |  |
|  |  | O'BRIEN, Paul |  |  |  |  |  |  |
| Warrnambool City Council 2012 - Postal | Unsubdivided |  | 7 | 12 | 81.61% | 3.54% | 25133 |  |
|  |  | ERMACORA, Jacinta |  |  |  |  |  |  |
|  |  | NEOH, Michael |  |  |  |  |  |  |
|  |  | HULIN, Peter |  |  |  |  |  |  |
|  |  | ASKEW, Robert |  |  |  |  |  |  |
|  |  | KELSON, Brian |  |  |  |  |  |  |
|  |  | SYCOPOULIS, Peter |  |  |  |  |  |  |
|  |  | GASTON, Kylie |  |  |  |  |  |  |
| Wellington Shire Council 2012 - Postal | Unsubdivided |  | 9 | 14 | 68.77% | 5.45% | 42181 |  |
|  |  | ROSSETTI, Scott Andrew |  |  |  |  |  |  |
|  |  | DAVINE, Emilie |  |  |  |  |  |  |
|  |  | McCUBBIN, Darren |  |  |  |  |  |  |
|  |  | HOLE, Malcolm |  |  |  |  |  |  |
|  |  | McIVOR, Patrick |  |  |  |  |  |  |
|  |  | CROSSLEY, Carolyn |  |  |  |  |  |  |
|  |  | CLEARY, Peter John |  |  |  |  |  |  |
|  |  | WENGER, Bob |  |  |  |  |  |  |
|  |  | DUNCAN, John F. |  |  |  |  |  |  |
| West Wimmera Shire Council 2012 - Postal | Unsubdivided |  | 5 | 8 | 76.85% | 2.46% | 4018 |  |
|  |  | MEYER, Bruce |  |  |  |  |  |  |
|  |  | HAWKINS, Ron |  |  |  |  |  |  |
|  |  | JONES, Annette |  |  |  |  |  |  |
|  |  | WAIT, Warren |  |  |  |  |  |  |
|  |  | WAIT, Richard |  |  |  |  |  |  |
| Whitehorse City Council 2012 - Postal |  |  | 10 | 30 | 74.17% | 3.35% | 112490 |  |
|  | Central Ward | MUNROE, Andrew | 2 | 5 | 74.63% | 3.59% | 22144 |  |
|  |  | MASSOUD, Denise |  |  |  |  |  |  |
|  | Elgar Ward | CHONG, Robert | 2 | 4 | 71.43% | 2.54% | 23469 |  |
|  |  | HARRIS, Helen |  |  |  |  |  |  |
|  | Morack Ward | CARR, Raylene | 2 | 5 | 77.73% | 2.94% | 22008 |  |
|  |  | BENNETT, Bill |  |  |  |  |  |  |
|  | Riversdale Ward | ELLIS, Sharon | 2 | 8 | 72.17% | 3.77% | 21739 |  |
|  |  | DAVENPORT, Andrew |  |  |  |  |  |  |
|  | Springfield Ward | STENNETT, Ben | 2 | 8 | 75.01% | 3.94% | 23130 |  |
|  |  | DAW, Philip |  |  |  |  |  |  |
| Whittlesea City Council 2012 - Postal |  |  | 11 | 48 | 74.30% | 7.02% | 116548 |  |
|  | North Ward | KIRKHAM, Ricky | 3 | 11 | 71.30% | 4.02% | 30318 |  |
|  |  | GRIFFIN, Rex |  |  |  |  |  |  |
|  |  | DAVIS, Nicola |  |  |  |  |  |  |
|  | South East Ward | LALIOS, Mary | 4 | 22 | 76.32% | 9.03% | 44987 |  |
|  |  | ALESSI, Sam |  |  |  |  |  |  |
|  |  | KELLY, Norm |  |  |  |  |  |  |
|  |  | HARRIS, Ken |  |  |  |  |  |  |
|  | South West Ward | KOZMEVSKI, Stevan | 4 | 15 | 74.31% | 6.89% | 41243 |  |
|  |  | PAVLIDIS, Kris |  |  |  |  |  |  |
|  |  | SINCLAIR, Darryl |  |  |  |  |  |  |
|  |  | SPINELLI, Adrian |  |  |  |  |  |  |
| Wodonga City Council 2012 - Postal | Unsubdivided |  | 7 | 13 | 73.06% | 5.43% | 27078 |  |
|  |  | BYATT, Mark Anthony |  |  |  |  |  |  |
|  |  | WANGMAN, Rodney |  |  |  |  |  |  |
|  |  | SPEEDIE, Anna |  |  |  |  |  |  |
|  |  | MAHOOD, Lisa |  |  |  |  |  |  |
|  |  | KERR, Eric |  |  |  |  |  |  |
|  |  | FRASER, Michael John |  |  |  |  |  |  |
|  |  | WATSON, John K. D. |  |  |  |  |  |  |
| Wyndham City Council 2012 - Postal |  |  | 11 | 46 | 67.13% | 6.79% | 114376 |  |
|  | Chaffey Ward | BOURKE, Shane Peter | 4 | 19 | 67.95% | 8.30% | 42524 |  |
|  |  | GUPTA, Gautam |  |  |  |  |  |  |
|  |  | GIBBONS, John |  |  |  |  |  |  |
|  |  | BRITTAN, Marie |  |  |  |  |  |  |
|  | Harrison Ward | FAIRCLOUGH, Bob | 4 | 18 | 63.58% | 7.32% | 40079 |  |
|  |  | GOODFELLOW, Glenn |  |  |  |  |  |  |
|  |  | HEGEDICH, Adele |  |  |  |  |  |  |
|  |  | KHAN, Intaj |  |  |  |  |  |  |
|  | Iramoo Ward | MARCUS, Heather | 3 | 9 | 70.50% | 4.25% | 31773 |  |
|  |  | GIBBONS, Peter |  |  |  |  |  |  |
|  |  | MAYNARD, Peter John |  |  |  |  |  |  |
| Yarra City Council 2012 - Attendance |  |  | 9 | 21 | 51.72% | 7.55% | 66518 | 32 |
|  | Langridge Ward | JOLLY, Stephen | 3 | 7 | 52.38% | 6.59% | 20981 | 10 |
|  |  | STONE, Amanda |  |  |  |  |  |  |
|  |  | BARBOUR, Geoff |  |  |  |  |  |  |
|  | Melba Ward | HUGGINS, Simon | 3 | 7 | 51.16% | 8.68% | 22934 | 10 |
|  |  | COLEMAN, Misha |  |  |  |  |  |  |
|  |  | VLAHOGIANNIS, Phillip |  |  |  |  |  |  |
|  | Nicholls Ward | GAYLARD, Sam | 3 | 7 | 51.67% | 7.32% | 22603 | 12 |
|  |  | FRISTACKY, Jackie |  |  |  |  |  |  |
|  |  | COLANZI, Roberto |  |  |  |  |  |  |
| Yarra Ranges Shire Council 2012 - Postal |  |  | 9 | 39 | 73.15% | 3.42% | 108942 |  |
|  | Billanook Ward | McCARTHY, Maria | 1 | 10 | 74.93% | 3.76% | 12559 |  |
|  | Chandler Ward | CALLANAN, Jason | 1 | 3 | 74.29% | 3.08% | 11362 |  |
|  | Chirnside Ward | WITLOX, Andy | 1 | 2 | 77.57% | 3.20% | 12300 |  |
|  | Lyster Ward | DUNN, Samantha | 1 | 2 | 70.84% | 3.72% | 11420 |  |
|  | Melba Ward | AVERY, Terry | 1 | 3 | 73.94% | 2.51% | 12510 |  |
|  | O'Shannassy Ward | CHILD, Jim | 1 | 3 | 68.24% | 3.26% | 12305 |  |
|  | Ryrie Ward | McALLISTER, Fiona | 1 | 12 | 73.10% | 3.65% | 12196 |  |
|  | Streeton Ward | CLIFF, Noel | 1 | 2 | 72.90% | 4.25% | 11435 |  |
|  | Walling Ward | COX, Len | 1 | 2 | 72.42% | 3.41% | 12855 |  |
| Yarriambiack Shire Council 2012 - Postal |  |  | 7 | 11 | 80.36% | 1.49% | 4598 |  |
|  | Dunmunkle Ward | KINGSTON, Raymond John | 2 | 3 | 79.80% | 1.84% | 1906 |  |
|  |  | GRANGE, Terry |  |  |  |  |  |  |
|  | Hopetoun Ward [U] | McLEAN, Andrew Robert | 2 | 2 | N/A | N/A | 0 |  |
|  |  | BALLENTINE, Helen |  |  |  |  |  |  |
|  | Warracknabeal Ward | ZANKER, Kylie Louise | 3 | 6 | 80.76% | 1.24% | 2692 |  |
|  |  | MASSEY, W. Graeme |  |  |  |  |  |  |
|  |  | WOODS, Lisa Maree |  |  |  |  |  |  |

Appendix 15: Snapshot of results

All councils

| Sate-wide | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| All Councils (ex City of Melbourne Leadership Team and Geelong Mayor) | 2012 | 628 | 271 | 1,973 | 7.28 | 70.96 | 5.51 | 3,993,895 | 156,240 | 2,834,064 | 2008 | 629 | 1,953 | 74.68 | 4.99 | 3,704,057 | 2,766,310 | -3.72 | 0.52 |
| All Councils (ex City of Melbourne Leadership Team) | 2012 | 629 | 272 | 1,982 | 7.29 | 71.18 | 5.42 | 4,164,303 | 160,512 | 2,964,073 | 2008 | 629 | 1,953 | 74.68 | 4.99 | 3,704,057 | 2,766,310 | -3.5 | 0.43 |
| All Councils (ex Geelong Mayor) | 2012 | 630 | 272 | 1,991 | 7.32 | 70.67 | 5.49 | 4,102,329 | 159,067 | 2,899,060 | 2008 | 631 | 1,975 | 74.36 | 4.98 | 3,801,904 | 2,827,113 | -3.69 | 0.51 |
| All Councils (inc City of Melbourne Leadership Team and Geelong Mayor) | 2012 | 631 | 273 | 2,000 | 7.33 | 70.89 | 5.39 | 4,272,737 | 163,339 | 3,029,069 | 2008 | 631 | 1,975 | 74.36 | 4.98 | 3,801,904 | 2,827,113 | -3.47 | 0.41 |
| Attendance | 2012 | 72 | 39 | 271 | 6.95 | 63.62 | 10.09 | 702,337 | 45,099 | 446,811 | 2008 | 81 | 341 | 70.03 | 9.9 | 797,604 | 558,557 | -6.41 | 0.19 |
| Postal (ex City of Melbourne Leadership Team and Geelong Mayor) | 2012 | 556 | 232 | 1,702 | 7.34 | 72.53 | 4.66 | 3,291,558 | 111,141 | 2,387,253 | 2008 | 548 | 1,612 | 75.96 | 3.75 | 2,906,453 | 2,207,753 | -3.43 | 0.91 |
| Postal (ex City of Melbourne Leadership Team) | 2012 | 557 | 233 | 1,711 | 7.34 | 72.71 | 4.58 | 3,461,966 | 115,413 | 2,517,262 | 2008 | 548 | 1,612 | 75.96 | 3.75 | 2,906,453 | 2,207,753 | -3.25 | 0.83 |
| Postal (ex Geelong Mayor) | 2012 | 558 | 233 | 1,720 | 7.38 | 72.13 | 4.65 | 3,399,992 | 113,968 | 2,452,249 | 2008 | 550 | 1,634 | 75.51 | 3.77 | 3,004,300 | 2,268,556 | -3.38 | 0.88 |
| Postal (inc City of Melbourne Leadership Team and Geelong Mayor) | 2012 | 559 | 234 | 1,729 | 7.39 | 72.32 | 4.58 | 3,570,400 | 118,240 | 2,582,258 | 2008 | 550 | 1,634 | 75.51 | 3.77 | 3,004,300 | 2,268,556 | -3.19 | 0.81 |

| Melbourne City Council | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Leadership Team | 2012 | 2 | 1 | 18 | 18 | 59.94 | 4.35 | 108,434 | 2,827 | 64,996 | 2008 | 2 | 22 | 62.14 | 4.67 | 97,847 | 60,803 | -2.2 | -0.32 |
| Councillors | 2012 | 9 | 1 | 40 | 40 | 60.01 | 2.16 | 108,434 | 1,407 | 65,071 | 2008 | 7 | 32 | 62.26 | 2.64 | 97,847 | 60,923 | -2.25 | -0.48 |

| Greater Geelong City Council | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mayor | 2012 | 1 | 1 | 9 | 9 | 76.29 | 3.29 | 170,408 | 4,272 | 130,009 |  |  |  |  |  |  |  | 76.29 | 3.29 |
| Councillors | 2012 | 12 | 12 | 50 | 4.17 | 75.48 | 2.48 | 170,408 | 3,190 | 128,620 | 2008 | 12 | 43 | 75.91 | 2.35 | 107,826 | 81,849 | -0.43 | 0.13 |

Attendance elections – metropolitan

| Attendance Metropolitan | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Banyule City Council | 2012 | 7 | 7 | 38 | 6.33 | 70.74 | 7.78 | 79,172 | 4,357 | 56,006 | 2008 | 7 | 42 | 75.11 | 6.93 | 91,904 | 69,033 | -4.37 | 0.85 |
| Glen Eira City Council | 2012 | 9 | 3 | 33 | 11.00 | 68.03 | 10.58 | 66,743 | 7,063 | 59,680 | 2008 | 9 | 26 | 69.22 | 8.06 | 95,406 | 66,039 | -1.19 | 2.52 |
| Greater Dandenong City Council | 2012 | 11 | 4 | 41 | 10.25 | 68.70 | 11.13 | 95,503 | 7,299 | 65,607 | 2008 | 11 | 40 | 71.90 | 10.09 | 91,593 | 65,859 | -3.2 | 1.04 |
| Knox City Council | 2012 | 9 | 9 | 26 | 3.71 | 74.04 | 7.57 | 90,756 | 5,085 | 67,199 | 2008 | 9 | 31 | 76.37 | 6.37 | 99,487 | 75,974 | -2.33 | 1.2 |
| Moreland City Council | 2012 | 11 | 3 | 49 | 16.33 | 64.46 | 16.06 | 111,987 | 11,592 | 72,185 | 2008 | 11 | 50 | 68.41 | 15.34 | 105,116 | 71,910 | -3.95 | 0.72 |
| Port Phillip City Council | 2012 | 7 | 7 | 27 | 3.86 | 49.40 | 6.19 | 79,618 | 2,434 | 39,333 | 2008 | 7 | 42 | 51.29 | 6.63 | 64,944 | 33,309 | -1.89 | -0.44 |
| Stonnington City Council | 2012 | 9 | 3 | 36 | 12.00 | 56.20 | 10.31 | 80,674 | 4,672 | 45,336 | 2008 | Stonnington City Council held its elections by postal voting in 2008 | -8.9 | 5.26 |
| Yarra City Council | 2012 | 9 | 3 | 21 | 7.00 | 51.72 | 7.55 | 66,518 | 2,597 | 34,402 | 2008 | 9 | 22 | 54.88 | 6.94 | 63,577 | 34,891 | -3.16 | 0.61 |

Postal elections – metropolitan

| Postal Metropolitan | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Bayside City Council | 2012 | 7 | 3 | 48 | 16 | 70.22 | 6.33 | 71,176 | 3,164 | 49,981 | 2008 | 7 | 33 | 74.18 | 4.42 | 69,010 | 51,191 | -3.96 | 1.91 |
| Boroondara City Council | 2012 | 10 | 10 | 37 | 3.7 | 71.27 | 2.99 | 122,821 | 2,615 | 87,539 | 2008 | 10 | 32 | 74.16 | 2.7 | 96,040 | 71,228 | -2.89 | 0.29 |
| Brimbank City Council | 2012 | There were no elections held for Brimbank City Council in 2012 | 2008 | 11 | 55 | 77.87 | 15.17 | 123,412 | 96,095 | N/A | N/A |
| Casey City Council | 2012 | 11 | 6 | 85 | 14.17 | 70.72 | 6.51 | 169,519 | 7,807 | 119,887 | 2008 | 11 | 52 | 74.84 | 3.93 | 153,374 | 114,792 | -4.12 | 2.58 |
| Darebin City Council | 2012 | 9 | 3 | 52 | 17.33 | 67.53 | 7.72 | 102,100 | 5,320 | 68,945 | 2008 | 9 | 48 | 72.76 | 6.18 | 98,694 | 71,805 | -5.23 | 1.54 |
| Frankston City Council | 2012 | 9 | 3 | 21 | 7 | 67.44 | 3.87 | 97,191 | 2,535 | 65,547 | 2008 | 9 | 29 | 71.88 | 4.02 | 90,848 | 65,305 | -4.44 | -0.15 |
| Hobsons Bay City Council | 2012 | 7 | 3 | 41 | 13.67 | 71.57 | 5.69 | 63,863 | 2,602 | 45,709 | 2008 | 7 | 37 | 73.11 | 7.57 | 62,165 | 45,447 | -1.54 | -1.88 |
| Hume City Council | 2012 | 11 | 3 | 47 | 15.67 | 73.15 | 6.21 | 115,039 | 5,228 | 84,150 | 2008 | 9 | 46 | 76.58 | 3.43 | 105,504 | 80,795 | -3.43 | 2.78 |
| Kingston City Council | 2012 | 9 | 3 | 52 | 17.33 | 71.25 | 6.31 | 112,137 | 5,045 | 79,897 | 2008 | 9 | 53 | 74.62 | 6.47 | 108,591 | 81,031 | -3.37 | -0.16 |
| Manningham City Council | 2012 | 9 | 3 | 35 | 11.67 | 75.62 | 5.04 | 87,331 | 3,329 | 66,041 | 2008 | 9 | 40 | 79.19 | 4.94 | 85,881 | 68,013 | -3.57 | 0.1 |
| Maribyrnong City Council | 2012 | 7 | 3 | 29 | 9.67 | 63.9 | 4.17 | 53,816 | 1,434 | 34,386 | 2008 | 7 | 38 | 66.89 | 2.51 | 50,375 | 33,696 | -2.99 | 1.66 |
| Maroondah City Council | 2012 | 9 | 3 | 39 | 13 | 72.81 | 5.63 | 80,417 | 3,296 | 58,553 | 2008 | 9 | 36 | 75.87 | 4.71 | 78,139 | 59,285 | -3.06 | 0.92 |
| Monash City Council | 2012 | 11 | 4 | 58 | 14.5 | 73.88 | 5.59 | 121,083 | 5,005 | 89,458 | 2008 | 11 | 43 | 78.84 | 3.7 | 119,575 | 94,271 | -4.96 | 1.89 |
| Moonee Valley City Council | 2012 | 9 | 3 | 26 | 8.67 | 72.24 | 3.99 | 84,740 | 2,444 | 61,214 | 2008 | 9 | 19 | 73.62 | 2.95 | 81,330 | 59,874 | -1.38 | 1.04 |
| Nillumbik Shire Council | 2012 | 7 | 7 | 44 | 6.29 | 76.69 | 3.12 | 46,373 | 1,109 | 35,564 | 2008 | 7 | 57 | 80.88 | 2.48 | 45,374 | 36,698 | -4.19 | 0.64 |
| Stonnington City Council | 2012 | Stonnington City Council held its elections by attendance voting in 2012 | 2008 | 9 | 36 | 65.10 | 5.05 | 76,004 | 49,475 | -8.9 | 5.26 |
| Whitehorse City Council | 2012 | 10 | 5 | 30 | 6 | 74.17 | 3.35 | 112,490 | 2,796 | 83,436 | 2008 | 10 | 33 | 77.43 | 3.05 | 111,639 | 86,445 | -3.26 | 0.3 |
| Whittlesea City Council | 2012 | 11 | 3 | 48 | 16 | 74.3 | 7.02 | 116,548 | 6,080 | 86,595 | 2008 | 9 | 32 | 79.46 | 3.51 | 96,638 | 76,789 | -5.16 | 3.51 |
| Wyndham City Council | 2012 | 11 | 3 | 46 | 15.33 | 67.13 | 6.79 | 114,376 | 5,216 | 76,777 | 2008 | 9 | 22 | 73.89 | 2.91 | 86,495 | 63,915 | -6.76 | 3.88 |

Postal elections – Regional and outer metropolitan

| Postal Regional and outer Metropolitan | Year | Number of vacancies | Number of elections | Number of candidates | Average # candidates /election | % voter turnout | % informal votes | Voters in contested elections | # informal votes | Votes | Year | Number of vacancies | Number of candidates | % voter turnout | % informal votes | Voters in contested elections | Votes | change in % voter turnout | change in % informal votes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Alpine Shire Council | 2012 | 7 | 1 | 13 | 13 | 75.64 | 3.93 | 11,524 | 343 | 8,717 | 2008 | 7 | 15 | 78.47 | 4.67 | 11,224 | 8,808 | -2.83 | -0.74 |
| Ararat Rural City Council | 2012 | 7 | 1 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 2008 | 7 | 12 | 81.77 | 3.16 | 9,053 | 7,403 | -81.77 | -3.16 |
| Ballarat City Council | 2012 | 9 | 3 | 22 | 7.33 | 77.51 | 2.7 | 72,725 | 1,524 | 56,367 | 2008 | 9 | 40 | 79.53 | 3.84 | 67,624 | 53,783 | -2.02 | -1.14 |
| Bass Coast Shire Council | 2012 | 7 | 7 | 26 | 3.71 | 71.13 | 2 | 40,887 | 581 | 29,082 | 2008 | 7 | 17 | 76.12 | 2.13 | 16,613 | 12,645 | -4.99 | -0.13 |
| Baw Baw Shire Council | 2012 | 9 | 4 | 26 | 6.5 | 77.28 | 2.83 | 34,853 | 762 | 26,935 | 2008 | 9 | 25 | 81.89 | 2.03 | 31,042 | 25,420 | -4.61 | 0.8 |
| Benalla Rural City Council | 2012 | 7 | 1 | 9 | 9 | 78.87 | 3.8 | 11,335 | 340 | 8,940 | 2008 | 7 | 14 | 81.79 | 2.92 | 11,265 | 9,214 | -2.92 | 0.88 |
| Borough of Queenscliffe | 2012 | 5 | 1 | 7 | 7 | 75.94 | 2.72 | 4,268 | 88 | 3,241 | 2008 | 5 | 9 | 78.12 | 1.34 | 4,196 | 3,278 | -2.18 | 1.38 |
| Buloke Shire Council | 2012 | 7 | 3 | 11 | 3.67 | 81.41 | 1.05 | 4,326 | 37 | 3,522 | 2008 | 7 | 9 | 84.92 | 0.77 | 4,422 | 3,755 | -3.51 | 0.28 |
| Campaspe Shire Council | 2012 | 9 | 5 | 22 | 4.4 | 78.44 | 2.56 | 28,820 | 578 | 22,606 | 2008 | 9 | 16 | 81.06 | 1.89 | 24,758 | 20,070 | -2.62 | 0.67 |
| Cardinia Shire Council | 2012 | 9 | 3 | 20 | 6.67 | 70.17 | 3.62 | 56,379 | 1,434 | 39,562 | 2008 | 7 | 17 | 75.54 | 2.48 | 45,215 | 34,156 | -5.37 | 1.14 |
| Central Goldfields Shire Council | 2012 | 7 | 4 | 13 | 3.25 | 80.08 | 2.06 | 10,858 | 179 | 8,695 | 2008 | 7 | 13 | 81.83 | 1.7 | 9,293 | 7,604 | -1.75 | 0.36 |
| Colac Otway Shire Council | 2012 | 7 | 1 | 14 | 14 | 78.17 | 4.48 | 19,799 | 693 | 15,477 | 2008 | 7 | 21 | 83.01 | 6.1 | 19,225 | 15,958 | -4.84 | -1.62 |
| Corangamite Shire Council | 2012 | 7 | 5 | 10 | 2 | 79.49 | 1.68 | 7,728 | 103 | 6,143 | 2008 | 7 | 11 | 82.94 | 1.41 | 7,671 | 6,362 | -3.45 | 0.27 |
| East Gippsland Shire Council | 2012 | 9 | 1 | 17 | 17 | 74.99 | 6.9 | 39,645 | 2,050 | 29,729 | 2008 | 9 | 29 | 77.53 | 9.58 | 37,586 | 29,139 | -2.54 | -2.68 |
| Gannawarra Shire Council | 2012 | 7 | 4 | 9 | 2.25 | 80.83 | 1.69 | 4,021 | 55 | 3,250 | 2008 | 7 | 10 | 82.86 | 1.48 | 7,665 | 6,351 | -2.03 | 0.21 |
| Glenelg Shire Council | 2012 | 7 | 1 | 11 | 11 | 74.42 | 3.88 | 16,811 | 486 | 12,510 | 2008 | 7 | 17 | 78.83 | 5.22 | 16,504 | 13,010 | -4.41 | -1.34 |
| Golden Plains Shire Council | 2012 | 7 | 1 | 12 | 12 | 76.02 | 4.35 | 16,098 | 532 | 12,237 | 2008 | 7 | 11 | 77.26 | 3.06 | 14,447 | 11,162 | -1.24 | 1.29 |
| Greater Bendigo City Council | 2012 | 9 | 3 | 21 | 7 | 77.45 | 2.4 | 79,736 | 1,482 | 61,755 | 2008 | 9 | 40 | 80.03 | 1.63 | 66,193 | 52,976 | -2.58 | 0.77 |
| Greater Shepparton City Council | 2012 | 7 | 1 | 26 | 26 | 80.1 | 9.53 | 43,372 | 3,312 | 34,740 | 2008 | 7 | 19 | 82.45 | 6.98 | 41,198 | 33,967 | -2.35 | 2.55 |
| Hepburn Shire Council | 2012 | 7 | 5 | 15 | 3 | 76.18 | 2.51 | 12,613 | 241 | 9,608 | 2008 | 7 | 14 | 78.49 | 1.33 | 9,959 | 7,817 | -2.31 | 1.18 |
| Hindmarsh Shire Council | 2012 | 6 | 3 | 11 | 3.67 | 81.27 | 2.61 | 3,396 | 72 | 2,760 | 2008 | 6 | 7 | 84.98 | 1.86 | 1,711 | 1,454 | -3.71 | 0.75 |
| Horsham Rural City Council | 2012 | 7 | 1 | 11 | 11 | 81.79 | 2.5 | 15,445 | 316 | 12,632 | 2008 | 7 | 13 | 84.94 | 3.47 | 14,978 | 12,722 | -3.15 | -0.97 |
| Indigo Shire Council | 2012 | 7 | 1 | 17 | 17 | 77.72 | 6.56 | 12,867 | 656 | 10,000 | 2008 | 7 | 16 | 80.9 | 6.22 | 12,049 | 9,748 | -3.18 | 0.34 |
| Latrobe City Council | 2012 | 9 | 4 | 22 | 5.5 | 73.72 | 3.42 | 54,385 | 1,373 | 40,090 | 2008 | 9 | 34 | 77.86 | 2.1 | 46,809 | 36,445 | -4.14 | 1.32 |
| Loddon Shire Council | 2012 | 5 | 5 | 7 | 1.4 | 75.5 | 1.87 | 2,979 | 42 | 2,249 | 2008 | 5 | 8 | 80.73 | 0.85 | 3,207 | 2,589 | -5.23 | 1.02 |
| Macedon Ranges Shire Council | 2012 | 9 | 3 | 29 | 9.67 | 74.04 | 3.87 | 33,712 | 966 | 24,961 | 2008 | 9 | 36 | 79.06 | 3.56 | 31,235 | 24,695 | -5.04 | 0.34 |
| Mansfield Shire Council | 2012 | 5 | 4 | 12 | 3 | 72.72 | 2.09 | 7,944 | 121 | 5,777 | 2008 | 5 | 8 | 77.26 | 1.35 | 5,739 | 4,434 | -4.54 | 0.74 |
| Melton City Council | 2012 | 7 | 3 | 72 | 24 | 68.52 | 9.58 | 76,026 | 4,991 | 52,093 | 2008 | 7 | 34 | 72.57 | 5.17 | 63,369 | 45,986 | -4.05 | 4.41 |
| Mildura Rural City Council | 2012 | 9 | 1 | 14 | 14 | 76.02 | 5.06 | 38,063 | 1,463 | 28,936 | 2008 | 9 | 17 | 80.79 | 5 | 36,906 | 29,817 | -4.77 | 0.06 |
| Mitchell Shire Council | 2012 | 9 | 3 | 22 | 7.33 | 72.75 | 2.98 | 26,962 | 585 | 19,615 | 2008 | 9 | 24 | 77.48 | 2.53 | 24,229 | 18,772 | -4.73 | 0.45 |
| Moira Shire Council | 2012 | 9 | 1 | 18 | 18 | 75.95 | 6.72 | 23,428 | 1,196 | 17,793 | 2008 | 9 | 13 | 79.73 | 4.11 | 22,477 | 17,920 | -3.78 | 2.61 |
| Moorabool Shire Council | 2012 | 7 | 4 | 12 | 3 | 71.84 | 3.22 | 16,906 | 391 | 12,145 | 2008 | 7 | 11 | 76.52 | 2.86 | 15,138 | 11,584 | -4.68 | 0.36 |
| Mornington Peninsula Shire Council | 2012 | 11 | 6 | 43 | 7.17 | 68.52 | 4.37 | 145,378 | 4,350 | 99,616 | 2008 | 11 | 28 | 74.18 | 2.63 | 63,558 | 47,145 | -5.66 | 1.74 |
| Mount Alexander Shire Council | 2012 | 7 | 5 | 23 | 4.6 | 79 | 2.26 | 13,290 | 237 | 10,499 | 2008 | 7 | 22 | 80.36 | 1.95 | 14,917 | 11,988 | -1.36 | 0.31 |
| Moyne Shire Council | 2012 | 7 | 1 | 9 | 9 | 79.75 | 2.55 | 14,108 | 287 | 11,251 | 2008 | 7 | 16 | 82.62 | 4.41 | 13,486 | 11,142 | -2.87 | -1.86 |
| Murrindindi Shire Council | 2012 | 7 | 7 | 12 | 1.71 | 73.44 | 1.82 | 5,904 | 79 | 4,336 | 2008 | 7 | 13 | 78.53 | 2.49 | 8,075 | 6,341 | -5.09 | -0.67 |
| Northern Grampians Shire Council | 2012 | 7 | 4 | 11 | 2.75 | 78.31 | 1.96 | 7,751 | 119 | 6,070 | 2008 | 7 | 7 | 0 | 0 | 0 | 0 | 78.31 | 1.96 |
| Pyrenees Shire Council | 2012 | 5 | 5 | 10 | 2 | 77.22 | 2.81 | 7,103 | 154 | 5,485 | 2008 | 5 | 8 | 80.21 | 2 | 4,124 | 3,308 | -2.99 | 0.81 |
| South Gippsland Shire Council | 2012 | 9 | 3 | 13 | 4.33 | 74.72 | 2.05 | 18,647 | 285 | 13,933 | 2008 | 9 | 16 | 79.7 | 1.88 | 27,052 | 21,560 | -4.98 | 0.17 |
| Southern Grampians Shire Council | 2012 | 7 | 1 | 10 | 10 | 81.65 | 3.84 | 13,406 | 420 | 10,946 | 2008 | 7 | 12 | 85.68 | 2.85 | 13,329 | 11,420 | -4.03 | 0.99 |
| Strathbogie Shire Council | 2012 | 7 | 5 | 14 | 2.8 | 78.92 | 2.25 | 8,051 | 143 | 6,354 | 2008 | 7 | 15 | 82.66 | 1.53 | 7,572 | 6,259 | -3.74 | 0.72 |
| Surf Coast Shire Council | 2012 | 9 | 4 | 25 | 6.25 | 74.84 | 2.92 | 26,502 | 580 | 19,834 | 2008 | 9 | 15 | 74.54 | 4.76 | 27,389 | 20,415 | 0.3 | -1.84 |
| Swan Hill Rural City Council | 2012 | 7 | 4 | 18 | 4.5 | 78.51 | 2.61 | 14,471 | 297 | 11,361 | 2008 | 7 | 14 | 79.22 | 2.45 | 12,418 | 9,837 | -0.71 | 0.16 |
| Towong Shire Council | 2012 | 5 | 1 | 12 | 12 | 78.03 | 3.34 | 5,486 | 143 | 4,281 | 2008 | 5 | 15 | 81.63 | 4.23 | 5,416 | 4,421 | -3.6 | -0.89 |
| Wangaratta Rural City Council | 2012 | 7 | 1 | 19 | 19 | 82.7 | 6.63 | 21,738 | 1,192 | 17,978 | 2008 | 7 | 13 | 81.32 | 3.82 | 20,979 | 17,061 | 1.38 | 2.81 |
| Warrnambool City Council | 2012 | 7 | 1 | 12 | 12 | 81.61 | 3.54 | 25,133 | 726 | 20,512 | 2008 | 7 | 18 | 82.6 | 5.48 | 23,931 | 19,767 | -0.99 | -1.94 |
| Wellington Shire Council | 2012 | 9 | 1 | 14 | 14 | 68.77 | 5.45 | 42,181 | 1,581 | 29,009 | 2008 | 9 | 12 | 70.74 | 3.79 | 41,779 | 29,553 | -1.97 | 1.66 |
| West Wimmera Shire Council | 2012 | 5 | 1 | 8 | 8 | 76.85 | 2.46 | 4,018 | 76 | 3,088 | 2008 | 5 | 11 | 80.23 | 2.15 | 4,052 | 3,251 | -3.38 | 0.31 |
| Wodonga City Council | 2012 | 7 | 1 | 13 | 13 | 73.06 | 5.43 | 27,078 | 1,075 | 19,784 | 2008 | 7 | 20 | 76.68 | 7.37 | 25,331 | 19,424 | -3.62 | -1.94 |
| Yarra Ranges Shire Council | 2012 | 9 | 9 | 39 | 4.33 | 73.15 | 3.42 | 108,942 | 2,722 | 79,690 | 2008 | 9 | 41 | 77.46 | 2.78 | 94,394 | 73,113 | -4.31 | 0.64 |
| Yarriambiack Shire Council | 2012 | 7 | 3 | 11 | 3.67 | 80.36 | 1.49 | 4,598 | 55 | 3,695 | 2008 | 7 | 12 | 82.33 | 0.92 | 6,467 | 5,324 | -1.97 | 0.57 |

# Footnotes

There were no elections for Brimbank City Council, which currently has a Panel of Administrators and is scheduled to hold a general election in March 2015.

The legislation was before Parliament during the lead up to the elections, but did not receive Royal Assent until after election day.

At this time, it was not known that the Local Government (Brimbank City Council) Amendment Act 2012 would amend the Local Government (Brimbank City Council) Act 2009 to delay the Brimbank City Council’s general election to March 2015.

This does not include Brimbank City Council, where the Panel of Administrators acting as the Council had resolved to change to a postal method of voting prior to legislative changes that rescheduled the Council’s next general election to March 2015.

The election for councillors at Melbourne City Council General Elections allows voters to vote in favour of their preferred group by placing a ‘1’ next to the group’s name in the above-the-line section of the ballot paper.

This election was subject to an inquiry by the Municipal Electoral Tribunal. The decision of the Municipal Electoral Tribunal made a minor change to the margin from the recount, which is not reflected in Figure 4.

Penalties paid to the VEC up to 2 September 2009.

Includes the sum of costs invoiced for stage one and an estimate of stage two costs.

Penalties paid to the VEC up to 16 April 2013.